## Table 1
ITP No: | R33 (Ed 4 / Rev 5) |  | Process: |  | Trench Drains |  | Project: |  | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Process Step |  |  |  | Reference documents |  | Criteria/Test Method/Spec |  | Inspection/Test Frequency |  | Inspection/ Test by: | Responsible Position |  | Type of Record |  | Acceptance/Comments Completed Not completed
1. Submit material compliance/test certificates for approval. - Corrugated plastic slotted pipe - Seamless tubular filter fabric - Geotextile - Filter Material – Aggregate |  |  |  | R33.2.1 R33.2.2 R33.2.3 R33.2.4 |  | RMS 3552 RMS 3553 RMS R63 RMS 3580 MD.R33.A06 Release of Hold Point |  | In accordance with Annexure R33/L |  | PV | PV/PE PV |  | HPR Form |  | Initials:  Initials:  Initials:  Initials:  Initials: 
2. Excavate trench to line, grade, width & depth shown on drawings. |  |  |  | R33.3.2 |  | Minimum grade 0.5% |  | After excavation |  | SS/Surveyor | PE/SS |  | As-builts |  | Initials: 
5. Place geotextile in trench. |  |  |  | R33.3.3 |  | Visual inspection |  | After geotextile placement |  | SS | PE/SS |  |  |  | Initials: 
6. Lay pipe on 50mm bed of filter material. |  |  |  | R33.3.4 |  | Visual inspection |  | After bedding placement |  | SS/PV | PE/SS |  |  |  | Initials: 
7. Verify that pipe laying, jointing & bedding are complete & conforming |  |  |  | R33.3.5 |  | R33 Cl 3.5 Release of Hold Point |  | At completion laying, jointing & bedding |  | PV | PV/PE |  | HPR Form |  | Initials: 
8. Backfill pipe with filter material, compact to avoid consolidation & lap geotextile. |  |  |  | R33.3.5 |  | Visual inspection |  | After HP release |  | SS | PE/SS |  |  |  | Initials: 
9. Install flush point covers and outlet in batter, structure including connections to pits. |  |  |  | R33.4.2 R33.4.3 R33.5.2.1 R33.5.2.2 |  | Visual inspection |  |  |  | SS | PE/SS |  |  |  | Initials: 
10. Marking trench drain and submit WAE drawings to Principal <28 days of completion |  |  |  | R33.6 |  | R33 Cl 6 |  | <28days of completion |  | SS | PE/SS |  | WAE dwgs |  | Initials: 
ITP No: | R33 (Ed 4 / Rev 5) |  | Process: |  | Trench Drains |  | Project: |  | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
REVIEW BY PROJECT MANAGER
Have materials been accepted? | [7 empty] | YES/NO
Is all testing as per specified frequency? | [7 empty] | YES/NO
Are subsurface within location and level tolerances? | [7 empty] | YES/NO
Have all RMS Hold Points been released? | [7 empty] | YES/NO
Any non-conformances? | [7 empty] | YES/NO Sign: For Closed Out: YES/NO
All work has been satisfactorily completed. | [7 empty] | YES/NO
Project Manager Date
Prepared By: |  | M Winchester |  | Approved By: |  |  |  | Date Approved