## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - R142 - Retroreflective Raised Pavement Markers | itp |  |  |  |  | ITP - R142 - Retroreflective Raised Pavement Markers
section | Retroreflective Raised Pavement Markers
checkpoint | 1. Prepare Safe Work Method Statement.
label | Criteria/Test Method/Spec - WHS Act 2011, WHS Regs 2017
label | Inspection/Test Frequency - Prior to commencing
label | Inspection/ Test by - PV
label | Responsible Position - SS/PE
label | Type of Record - SWMS, HPR Form
textbox | Initials:
checkpoint | 2. Approval of materials to be used; Retroreflective markers – Adhesive
label | Criteria/Test Method/Spec - AS1906.3 & ATD2015/01 RMS 3354
label | Inspection/Test Frequency - Prior to commencing
label | Inspection/ Test by - Supplier
label | Responsible Position - SS/PE
label | Type of Record - Certificate of conformity
textbox | Initials:
checkpoint | 3. Setting out
label | Criteria/Test Method/Spec - RMS R142 Clause 3.1, Release of Hold Point
label | Inspection/Test Frequency - Application of retroreflective raised pavement markers
label | Inspection/ Test by - PV
label | Responsible Position - PE
label | Type of Record - Client notification
textbox | Initials:
checkpoint | 4. Set out for retroreflective raised pavement marker.
label | Criteria/Test Method/Spec - RMS R142 Appendix 1, Release of Hold Point
label | Inspection/Test Frequency - Completion of setout
label | Inspection/ Test by - PV
label | Responsible Position - PE/Surveyor
label | Type of Record - HPR Form
textbox | Initials:
checkpoint | 5. Install retroreflective raised pavement marker
label | Criteria/Test Method/Spec - Visual inspection R142 Cl 3.2.1
label | Inspection/Test Frequency - Completion of Installation
label | Inspection/ Test by - SS
label | Responsible Position - PE
label | Type of Record - As-built
textbox | Initials:
checkpoint | 6. Remove redundant markers
label | Criteria/Test Method/Spec - Visual inspection
label | Inspection/Test Frequency - Completion of removal
label | Inspection/ Test by - SS
label | Responsible Position - SS/PE
label | Type of Record - ITP
textbox | Initials: