## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - R143 - Signposting | itp |  |  |  |  | ITP - R143 - Signposting
section | Signposting
checkpoint | 1. Prepare Safe Work Method Statement.
label | Criteria/Test Method/Spec - WHS Act 2011, WHS Regs 2017
label | Inspection/Test Frequency - Prior to commencing
label | Inspection/ Test by - PV
label | Responsible Position - Site Supervisor (SS)
label | Type of Record - HPR Form
textbox | Initials:
checkpoint | 2. Approval of signs for use
label | Criteria/Test Method/Spec - RMS 3400 Contract Drawings
label | Inspection/Test Frequency - Prior to commencing
label | Inspection/ Test by - PV
label | Responsible Position - SS/PE
label | Type of Record - HPR Form
textbox | Initials:
checkpoint | 3. Set out for new signs.
label | Criteria/Test Method/Spec - RMS R143 Clause 3.2 Contract Drawings Release of Hold Point
label | Inspection/Test Frequency - Completion of setout
label | Inspection/ Test by - PV
label | Responsible Position - PE/Surveyor
label | Type of Record - HPR Form
textbox | Initials:
checkpoint | 4. Install Signs as per Contract Drawings
label | Criteria/Test Method/Spec - Visual inspection
label | Inspection/Test Frequency - Completion of Installation
label | Inspection/ Test by - SS
label | Responsible Position - PE/Surveyor
label | Type of Record - As-built
textbox | Initials: