## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - R145 - Pavement Marking | itp |  |  |  |  | ITP - R145 - Pavement Marking
section | Pavement Marking
checkpoint | 1. Underlying lot conformance (if applicable)
textbox | Lot No:
label | Criteria/Test Method/Spec - Underlying lots conform to applicable specifications
label | Reference document - Previous Lot Record
label | Record of conformity - Lot conformance
label | Type of Record - Record
label | Responsible Position - Project engineer
checkpoint | 2. Check if traffic controls are in place
label | Criteria/Test Method/Spec - Road Occupancy License Obtained if required.
label | ○ Pedestrian and vehicular public traffic control planning measures established
label | Reference document - G10.2.4
label | Record of conformity - Approved TCP
label | Type of Record - IP
label | Responsible Position - Project engineer
checkpoint | 3. Painting Contractor Certification
label | Criteria/Test Method/Spec - ○ Works carried out by organization that is accredited to the “Painting Contractors Certification Program
label | Reference document - R145.1.4
label | Record of conformity - Certification
label | Type of Record - IP
label | Responsible Position - Project engineer
checkpoint | 4. Verify type of marking material as shown in drawings Waterborne paint thermoplastic paint
label | Criteria/Test Method/Spec - On concrete surfaces in the main carriageway and all local road – waterborne paint
label | ○ Asphalt surface on the main carriageway – thermoplastic paint
label | ○ Type as per relevant design drawings & R145 appendices
label | ○ provide the RMS representative a list of material proposed for use and limitation to be used
label | Reference document - R145.1.4, R145.2.1, AS 4049.3, AS 4049.2, 3359, 3360
label | Record of conformity - Verification Checklist
label | Type of Record - IP
label | Responsible Position - Project engineer
checkpoint | 5. Verify the reflective glass beads conform to specs requirements
label | Criteria/Test Method/Spec - (APAS) Specification APS0042 Clause 6.2 “Heavy metal content”. Obtain evidence of compliance
label | Reference document - R145.2.4
label | Record of conformity - Verification Checklist
label | Type of Record - IP
label | Responsible Position - Project engineer
checkpoint | 6. Verify conformance of raised pavement markers & Adhesive
label | Criteria/Test Method/Spec - ○ Use only retroreflective raised pavement markers prequalified by the RMS. Prequalified retroreflective raised pavement markers are listed in ATD 2015/01
label | ○ For new installation and complete replacement works, all markers must be identifiable for at least twelve months after the initial installation.
label | ○ For the adhesive and RRPM (retroreflective raised pavement markers) provide a certificate of compliance verifying that the product complies with the specification, together with the results of the relevant tests.
label | Reference document - R142.2.1 3354.7
label | Record of conformity - Verification Test Certificate
label | Type of Record - IP
label | Responsible Position - Project engineer
checkpoint | 7. Sampling and Testing Plan
label | Criteria/Test Method/Spec - Submit to PV contractors proposed sampling plan for assessing the pavement marking
label | Reference document - R145.5
label | Record of conformity - Sampling Plan
label | Type of Record - IP
label | Responsible Position - Project engineer
section | Application
checkpoint | 8. Prepare the Surface for marking
label | Criteria/Test Method/Spec - The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
label | ○ The area around making area is also clean to avoid tracking into the marking area
label | ○ Curing compound on marking areas of concrete pavements is removed by grinding or blasting.
label | ○ Surface is compatible to the new line marking materials.
label | Reference document - R145.3.1
label | Record of conformity - Verification Checklist
label | Type of Record - IP
label | Responsible Position - Project engineer
checkpoint | 9. Set out the works for installation of pavement markings / raised markers
label | Criteria/Test Method/Spec - Notification made to the Project Verifier that the setting out to pavement markings and markers have been done in according with the design drawings
label | Reference document - R145.3.2.4 R142.3.1
label | Record of conformity - Hold Point
label | Type of Record - HP
label | Responsible Position - PV/Project engineer
holdpoint | HOLD POINT
checkpoint | 10. Supervise the application of pavement marking / markers
label | Criteria/Test Method/Spec - Paints and markers installed as per manufacturer’s recommendations
label | ○ The same materials used with those nominated in the certifications
label | ○ All longitudinal lines have been applied by the nominated machine unless approved by Independent Verifier
label | ○ Markings are straight or with smooth, even curves where intended
label | ○ Edges are clean sharp cut off
label | ○ Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
label | ○ Beads uniformly applied onto the material immediately after it has been applied to the pavement & while the material is still molten
label | ○ Retention of bead material is achieved
label | ○ Markings are neat & free from traffic damage or other defects
label | Reference document - R145.3.2.2, R145.3.4, R145.3.6, R145.4, R142.3, R142.4
label | Record of conformity - Verification Checklist
label | Type of Record - IP
label | Responsible Position - Project engineer
checkpoint | 11. Field test of the paint performance. Provide the results of your testing to the Nominated Authority within 10 working days of carrying out the test
label | Criteria/Test Method/Spec - Thickness of non-profile marking≤6mm
label | ○ Dry Retroreflectivity: min.250 mcd/lux/m2 up to 20 days after opening to traffic.
label | ○ Wet Retroreflectivity: min.80 mcd/lux/m2
label | ○ Skid resistance: min. 40BPN
label | ○ Colour change: min.3
label | ○ Luminance factor: ≥S 2500-N
label | ○ the pavement marking tested must be “70% of area intact” or better
label | Reference document - R145.4, R145.5 AS 4049.5
label | Record of conformity - Test Report
label | Type of Record - TP
label | Responsible Position - Project engineer
checkpoint | 12. Reinstatement of Pavement Markings After Road Works
label | Criteria/Test Method/Spec - Reinstate the pavement markings as soon as possible after road works where the pavement markings have been removed or damaged, to maintain the delineation for road safety purposes Temporary raised pavement markers can be used for delineation for up to 10 days after opening to traffic, after which the pavement markings must be reinstated.
label | Reference document - R145 CL3.5, R145 Cl 3.5.2
label | Record of conformity - ITP
label | Type of Record - IP
label | Responsible Position - Project engineer