## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - R33 - Trench Drains | itp |  |  |  |  | ITP - R33 - Trench Drains
section | Trench Drains
checkpoint | 1. Submit material compliance/test certificates for approval.
label | ○ Corrugated plastic slotted pipe
label | ○ Seamless tubular filter fabric
label | ○ Geotextile
label | ○ Filter Material – Aggregate
label | Reference documents - R33.2.1, R33.2.2, R33.2.3, R33.2.4
label | Criteria/Test Method/Spec - RMS 3552, RMS 3553, RMS R63, RMS 3580 MD.R33.A06
label | ○ Release of Hold Point
label | Inspection/Test Frequency - In accordance with Annexure R33/L
label | Inspection/Test by - PV
label | Responsible Position - PV/PE, PV
label | Type of Record - HPR Form
textbox | Initials:
checkpoint | 2. Excavate trench to line, grade, width & depth shown on drawings.
label | Reference documents - R33.3.2
label | Criteria/Test Method/Spec - Minimum grade 0.5%
label | Inspection/Test Frequency - After excavation
label | Inspection/Test by - SS/Surveyor
label | Responsible Position - PE/SS
label | Type of Record - As-builts
textbox | Initials:
checkpoint | 5. Place geotextile in trench.
label | Reference documents - R33.3.3
label | Criteria/Test Method/Spec - Visual inspection
label | Inspection/Test Frequency - After geotextile placement
label | Inspection/Test by - SS
label | Responsible Position - PE/SS
textbox | Initials:
checkpoint | 6. Lay pipe on 50mm bed of filter material.
label | Reference documents - R33.3.4
label | Criteria/Test Method/Spec - Visual inspection
label | Inspection/Test Frequency - After bedding placement
label | Inspection/Test by - SS/PV
label | Responsible Position - PE/SS
textbox | Initials:
checkpoint | 7. Verify that pipe laying, jointing & bedding are complete & conforming
label | Reference documents - R33.3.5
label | Criteria/Test Method/Spec - R33 Cl 3.5
label | ○ Release of Hold Point
label | Inspection/Test Frequency - At completion laying, jointing & bedding
label | Inspection/Test by - PV
label | Responsible Position - PV/PE
label | Responsible Position - HPR Form
textbox | Initials:
checkpoint | 8. Backfill pipe with filter material, compact to avoid consolidation & lap geotextile.
label | Reference documents - R33.3.5
label | Criteria/Test Method/Spec - Visual inspection
label | Inspection/Test Frequency - After HP release
label | Inspection/Test by - SS
label | Responsible Position - PE/SS
textbox | Initials:
checkpoint | 9. Install flush point covers and outlet in batter, structure including connections to pits.
label | Reference documents - R33.4.2, R33.4.3, R33.5.2.1, R33.5.2.2
label | Criteria/Test Method/Spec - Visual inspection
label | Inspection/Test by - SS
label | Responsible Position - PE/SS
textbox | Initials:
checkpoint | 10. Marking trench drain and submit WAE drawings to Principal <28 days of completion
label | Reference documents - R33.6
label | Criteria/Test Method/Spec - R33 Cl 6
label | Inspection/Test Frequency - <28days of completion
label | Inspection/Test by - SS
label | Responsible Position - PE/SS
label | Type of Record - WAE dwgs
textbox | Initials: