## zres_siteapp
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Concrete Pours - 305 - Rev B | itp |  |  |  | Yes | ITP - Concrete Pours - 305 - Rev B | f4452fa0-0b64-4a26-9cec-fdbba71d55d5
checkpoint-group |  |  | section | 10.01 Concrete Pours
checkpoint-status |  |  | checkpoint | 10.01.1 - Construction Joint Locations
label | 77c3fee4-3014-56c6-8958-0d2d7a21c949 |  | note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
label | 6299b251-e253-5d7b-8616-e6d1bbed7943 |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | 50bf4ba8-d836-5923-81e4-c26e161e1c9a |  | note | Verifying Document - Approval
label | 05f5dfe5-3fe3-5f13-b20c-b50dc3ae4f02 |  | note | Frequency - Prior to Pour
label | 58791a38-7c74-516f-9592-b9c501d97dde |  | note | Verification Activity: Activity - HP
label | af220b77-4659-5d55-bbdd-bd932a951939 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.01.2 - Dry Pack Mortar
label | ab50827c-4169-56dc-bc37-97b6801b7c23 |  | note | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
label | 7d76b01f-021d-541d-87c6-6e0cfc1a23be |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | 4e642898-e8f4-5e6e-b7e4-0be5d2cbbc37 |  | note | Verifying Document - Pre pour
label | 18092f30-659a-50eb-bb1c-1341356f36c3 |  | note | Frequency - Before Works
label | 03cef8c8-2bbb-5d8c-8af4-5cff17d157b9 |  | note | Verification Activity: Activity - R
label | 88967d4c-4cb9-5844-a2d1-5ad02b659fd0 |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.3 - Blinding Concrete Subgrade Inspection
label | c27bb992-036f-58e6-a2bc-8dc864d5017c |  | note | Acceptance / Conformance Criteria - A subgrade inspection is required by the Engineer prior to the pouring of the blinding concrete layer.
label | f8224316-bb48-5c28-b1df-6d4ce286636d |  | note | Standard / Specification - PS 19.5.1
label | 0657d05f-d3a2-5eee-89cb-bf76b2773c41 |  | note | Verifying Document - Pre Pour Checksheet
label | f9f6390f-ac06-5617-a6ac-1ff0ced3910c |  | note | Frequency - Prior to Pour
label | 4b684efa-b574-5c3f-b1f9-774bb9e155cb |  | note | Verification Activity: Activity - HP
label | ae9f9c1a-49fd-5b3b-b7b9-03e0b1555f17 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.01.4 - Reinforcement Pre Pour Inspection
label | 216b0e83-62ef-52ac-af74-d6794062d74e |  | note | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
label | 3da9c5cd-ed47-55a2-b596-7ef74d68b10c |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | de11a607-05ad-5602-85fd-9eef77824afe |  | note | Verifying Document - Pre pour
label | 5c96772c-9d17-5174-b301-2ab930ac5395 |  | note | Frequency - Each Pour
label | 2e28d195-174a-5fb5-83e7-4a90c3fcd018 |  | note | Verification Activity: Activity - R
label | 2ae9c6f6-d823-5e84-b6c0-0aedb8a51d81 |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.5 - Pre-Pour Inspection
label | e1188bd7-cc46-5105-bfdb-d5350d5ff461 |  | note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | aeeffd21-0668-5cf1-8d4b-5601c15ee835 |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | 73087163-48f0-5a5b-b952-d8685fe9b685 |  | note | Verifying Document - Signed Pre-Pour
label | f9fdd6cd-bafe-5618-b702-df89114ab36a |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | b1c9cd0e-fd05-5a18-8b07-935a95968af7 |  | note | Verification Activity: Activity - HP
label | ab527aeb-64a7-59e2-ac55-1624ec07938f |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.01.6 - Delivery Dockets
label | 34e8d0f8-5f3f-549a-a77e-38a16662f869 |  | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | d15bdb02-9ce3-544a-8d0c-0c3219a7a6e5 |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | 03f7f30a-6956-548b-b24b-8e234f7bc47c |  | note | Verifying Document - Dockets
label | 9f333b98-7da3-5067-b90d-39fbed92f3f8 |  | note | Frequency - Each Pour
label | 0e25c498-578f-5f20-9989-a086b9428134 |  | note | Verification Activity: Activity - R
label | 16bfb57d-ab84-556e-bd07-1daeb5da06e3 |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.7 - Slump Testing
label | 651b607c-4d94-5df9-97ef-609a228db4a7 |  | note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
label | 72bd8ce1-89f9-5b13-8e4b-df7548c6a14a |  | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
label | f1f6bea3-6dfd-59e2-8322-5c84efbe099b |  | note | Verifying Document - Pre Pour
label | 052e3185-a0b9-52b2-9547-ad396b28fb3e |  | note | Frequency - Each Pour
label | baaef303-0d09-53ac-87ea-41a32b441645 |  | note | Verification Activity: Activity - R
label | cdce4799-a636-5b6a-b73d-ceef88b632b2 |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.8 - Compression Testing Insutu Concrete
label | abf0a42b-8816-5000-b618-2db993fbfae6 |  | note | Acceptance / Conformance Criteria - The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting.
label | 6a74b721-efda-532c-b476-6bfba71717be |  | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2, PS 19.8.7
label | 5d095a00-f6af-56dd-91e2-f8996967bb37 |  | note | Verifying Document - IANZ Test Results
label | d9eb6ebe-16df-5faa-8657-5c2ecc5c56ce |  | note | Frequency - One Set Daily consist of at least six field specimens
label | 03fdcca1-9688-5095-a292-952a5b7e0bdf |  | note | Verification Activity: Activity - R
label | b5de1487-a723-51c5-a611-07d5b4bf5cfd |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.9 - Compression Testing Precast Concrete
label | 20f3bc5d-f827-554e-bf54-0d26b9f4fe89 |  | note | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
label | 66ac3f96-f3e2-5246-9916-942853821161 |  | note | ○ For repetitive small pours (e.g., precast concrete barrier pours) undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 days compressive strength in an approved laboratory.
label | c7d1e12d-4a77-5562-8943-817544d4c727 |  | note | Standard / Specification - PS 19.8.7, PS 19.8.8, PS 19.8.9, PS 19.8.10, PS 19.8.11
label | 425fe4c0-3998-54a6-9db8-d263bd46a41e |  | note | Verifying Document - Plant Test Results
label | 8505799b-7ca7-5805-a4ee-c8f37ee8c946 |  | note | Frequency - 1 set per 50m3 or part therefor of / First Five then every 5th
label | 2e7def74-19db-501b-83e4-f1cd772a2f0e |  | note | Verification Activity: Activity - R
label | 446ec503-bb3b-5e52-8c6f-3e4135ad37af |  | note | Verification Activity: By - PE
checkpoint-group |  |  | section | 10.02 Post Pours
checkpoint-status |  |  | checkpoint | 10.02.1 - Post Pour Inspection
label | bb73d605-2d35-5658-8d71-f816cd27d198 |  | note | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | e0b99469-16c1-5899-9486-eba94ee8639c |  | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
label | 1a9a3066-00b1-5cdb-9045-523d177d9011 |  | note | Verifying Document - Post Pour
label | d69124ed-2c9a-571e-b980-f4472fb9b6c1 |  | note | Frequency - Each Pour
label | 2c9b75b6-3ae5-5516-84f7-286b062ea42f |  | note | Verification Activity: Activity - R
label | a6c2f255-940e-59b9-a4cc-2264904b06da |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.2 - Construction joints
label | 34f04b18-ee80-5818-877f-db6024f366bd |  | note | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
label | c3622fe1-5cc2-5751-8395-573d7c1f22df |  | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
label | 5cfb1266-1870-5e58-93f2-162495d47f5f |  | note | Verifying Document - Post Pour
label | 4aa7e96c-7a36-5bc8-80c4-297767529f7d |  | note | Frequency - Each Pour
label | 4d36cdc4-19cf-5ba3-8981-4e89a4cde94c |  | note | Verification Activity: Activity - R
label | 3cf6fe6a-fd2f-5b98-973f-d9a12d7151d7 |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.3 - Concrete Curing
label | 088b2548-38a5-5d7b-b847-2006507623db |  | note | Acceptance / Conformance Criteria - Concrete shall be cured for at least 7 days as per the drawings / specification.
label | 3a296e1d-1d18-55ae-835f-4df4cab41907 |  | note | Standard / Specification - PS 18.2, PS 19, PS 19.12
label | 82d6a528-31ea-504d-bac1-c4c1d6655dc8 |  | note | Verifying Document - Post Pour
label | 740c48b2-402d-5e91-86e3-b86d7114416d |  | note | Frequency - At least 7 days after pour
label | 5b6e6d37-e249-5c36-bdce-b545d1e37b88 |  | note | Verification Activity: Activity - R
label | 6c8f0a8d-c100-5b7c-b97a-d68c713568b5 |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.4 - Stripping
label | 33296847-d9c7-5203-83e4-0572e5713c35 |  | note | Acceptance / Conformance Criteria - No formwork shall be stripped until at least 3 days have elapsed from time of pouring concrete.
label | 52deacb3-ef2c-5cb0-ae4b-435066cb833f |  | note | Standard / Specification - PS 18.2, PS 19
label | e0a48761-de40-5585-a079-f12fa1539d0c |  | note | Verifying Document - Post Pour
label | cb20615b-9fe3-57e3-b0c4-3937e018f4f5 |  | note | Frequency - At least 3 days after pour
label | 221d0b33-5dd5-5e32-ba5b-53dbe02d7eed |  | note | Verification Activity: Activity - R
label | d1e75c53-a4d2-5f7b-9e34-42bb173834ca |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.5 - Protection of Completed Works
label | f2d0fc54-a351-54f3-92d2-2d6781fe43e7 |  | note | Acceptance / Conformance Criteria - Protect the completed work from damage and from dropping other materials during the remainder of the construction period. Do not use the completed work as a building platform or for material storage.
label | c7daff67-593c-5040-b967-62f080cc6d57 |  | note | Standard / Specification - PS 18.2, PS 19
label | ded691a8-9762-5ef0-bbea-0036cd5bc84c |  | note | Verifying Document - Post Pour
label | 4af66c1c-feae-570a-8fbb-2dc2be5082c7 |  | note | Frequency - During the remainder of the construction period
label | d248199b-b113-598a-8fb0-18d22822b007 |  | note | Verification Activity: Activity - R
label | 0e58fe0e-f00d-5611-9373-bc80dca87f3c |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.6 - Defective Concrete Finishes
label | bd5e44b7-a215-5e63-ad70-3206a3ae6e4d |  | note | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | 5fadb43e-0d37-57e4-84e1-1afde5844eb2 |  | note | Standard / Specification - PS 18.2, PS 19, PS 19.13
label | 8bcc5cd6-e69d-5ed1-8ae6-be46264c2bd2 |  | note | Verifying Document - NCR
label | cc604e63-458a-5084-b33f-e825e4fb7b6e |  | note | Frequency - Prior to non Minor Repair
label | 471ca773-ed4b-5c35-9040-94e8be6b70b2 |  | note | Verification Activity: Activity - V
label | b6d0af65-6a06-53bc-a406-7b3b165d5b95 |  | note | Verification Activity: By - SE
checklist-sectioned |  |  | checklist | ITP - Fall Protection Fencing - 304 - Rev B | itp |  |  |  | Yes | ITP - Fall Protection Fencing - 304 - Rev B | 35ffaef1-7203-47f9-a441-2bc38b2305b1
checkpoint-group |  |  | section | 4.20 Fall Protection Materials
checkpoint-status |  |  | checkpoint | 4.20.1 - Fall Protection Fence Materials
label | d534393e-c98b-5a5f-88e5-64e66d165722 |  | note | Acceptance / Conformance Criteria - Safety fence design load shall be in accordance with NZS1170.1: Table 3.3 Type C3. All steelwork shall be hot-dip galvanised in accordance with AS/NZS 4680:2006.
label | 12d18b70-4754-54df-b0ff-579be8bd10d9 |  | note | Standard / Specification - PS 18.6.1, PS 19.25.1
label | 90acc04b-3d0d-5510-8d15-444e09a6130d |  | note | Verifying Document - Datasheets and Mill Certs
label | 6f9bf2a8-5f37-5ea8-96fd-e2d3b5780181 |  | note | Frequency - Prior to use
label | d48e1a79-c7aa-5ef1-a62c-d564c2cf9fec |  | note | Verification Activity: Activity - R
label | f7301aa3-b12f-5a7d-9e03-de6ee2710e05 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.20.2 - Fall Protection Fence Epoxy
label | 3ffc1176-4a53-5979-a72b-936c446736ff |  | note | Acceptance / Conformance Criteria - SikaDur UA Epoxy Repair Mortar or a similar approved mortar.
label | 888857b2-3f93-58fe-89ac-a581671c2523 |  | note | Standard / Specification - PS 18.6.1, PS 19.25.1
label | 392e97e3-2841-5c62-b773-b72f484c18da |  | note | Verifying Document - Datasheets
label | 40f5841d-63d4-5d85-b325-fa88721ace0b |  | note | Frequency - Prior to use
label | 4fdf8ad1-79ab-520b-9bfd-d56df3e219ec |  | note | Verification Activity: Activity - R
label | 06fbaaf7-5803-56b0-8dff-d480289c2989 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.20.3 - Fall Protection Fence Base plates
label | c6075165-c7cf-5771-a980-559c64682dfc |  | note | Acceptance / Conformance Criteria - Mild steel baseplate with holes shall be Hot Rolled Grade 250 complying with AS/NZS3678:2016 (AS/NZS3678-350).
label | 4b41d91b-c9a0-5537-9d27-94e2b233a4e8 |  | note | Standard / Specification - PS 18.6.1, PS 19.25.1
label | e3de1f7a-75d1-5e92-a5f5-25a2f3f42cae |  | note | Verifying Document - Datasheets and Mill Certs
label | feb96f00-8423-5b78-8e42-23e3024b5011 |  | note | Frequency - Prior to use
label | 548f3da1-c304-57d3-ad68-0a54878b7681 |  | note | Verification Activity: Activity - R
label | 98c6c5e0-35ec-5a25-a348-f81fafe1cdd7 |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 11.01 Fall Protection Fence
checkpoint-status |  |  | checkpoint | 11.01.1 - Fall Protection Fence Installation
label | 5e78e5a0-023d-5358-87d2-60f1d570d583 |  | note | Acceptance / Conformance Criteria - Safety fence system shall be Webforge and shall be installed in accordance with Manufacturers Specification. Posts are to be positioned vertically in both the longitudinal and transverse directions. All rough or sharp edges or protrusions to be buffed smooth. All rails should be jointed within post sphere. Rails should be fixed to spheres at every post by welding.
label | 58981d55-b82d-5013-be23-19f6a0267f28 |  | note | Standard / Specification - PS 18.6.1
label | f67d5198-9982-5f30-a180-5d651f23c570 |  | note | Verifying Document - Site Records
label | dff54f59-1628-534e-baf3-fba07a7a30f1 |  | note | Frequency - Each Fence
label | e9a223e5-bd46-5699-8728-f4c94082ad53 |  | note | Verification Activity: Activity - S
label | ded1d516-b4e0-5a76-9117-231f6508bb02 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 11.01.2 - Remedial Painting
label | 59882d18-98a9-5b49-9eca-a354a36e21e3 |  | note | Acceptance / Conformance Criteria - Damaged galvanizing shall be coated / repaired in accordance with Appendix E of AS/NZS 4680, e.g., painted with 2 coats of an approved zinc rich paint, such as Resene AmorZinc110.
label | a7c73dbf-05f7-5c63-a377-239927478c22 |  | note | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | 3a5234fa-ebd5-563a-ba5c-4f8600ceb0c9 |  | note | Verifying Document - Site Records
label | 5a7b2e2d-a230-5478-a31c-3f8c81bc4ccb |  | note | Frequency - Each Occurance
label | a56d27ed-980e-5558-9655-59ad0eed1938 |  | note | Verification Activity: Activity - S
label | 85fd877f-efe2-5dd3-87b6-85be6753d510 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 11.01.3 - Fall Protection Fence Post Spacing
label | f639cf18-f630-5fb8-906a-fed0ebdeef22 |  | note | Acceptance / Conformance Criteria - Post spacing shall not be larger than 2m. Posts should not be placed closer than 200mm from the edge of the wall joints.
label | 3fca7d61-5a9f-5414-8dd6-69d272fe991f |  | note | Standard / Specification - PS 18.6.1, PS 19.25.1
label | 3cc53b4f-b9f6-57c2-933c-b08339d96eed |  | note | Verifying Document - Site Records
label | dade21b3-c1a5-500b-81be-06503d6f7c03 |  | note | Frequency - Each Fence
label | bbda1d13-8103-5702-bf81-4e5c8bb99689 |  | note | Verification Activity: Activity - S
label | f40856f5-5826-5d3a-b06c-42750adb6290 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 11.01.4 - Fall Protection Fence Reinforcement scanning
label | db453017-d7c8-589f-b7ad-7c09b620e0d9 |  | note | Acceptance / Conformance Criteria - Reinforcement scanning shall be carried out at every post location. If clashes with reinforcement are identified, the following amendments shall be taken, posts at which the rail is not spliced shall be moved +/- 50mm along the handrail alignment.
label | 3e78432c-2413-5ef8-8642-0819e67f694d |  | note | Standard / Specification - PS 18.6.1, PS 19.25.1
label | 072b2370-4443-5d28-afb5-f91880ef6c56 |  | note | Verifying Document - Site Records
label | b56d3717-9372-545d-b5df-1f4d2ea9a0c6 |  | note | Frequency - Each Hole
label | 393d8ad4-7644-53f4-b957-61455f4e1e00 |  | note | Verification Activity: Activity - S
label | a2e7cf3f-513b-52b3-9d45-b6c04ed64340 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 11.01.5 - Fall Protection Fence Drilling
label | c29235a9-78ce-5757-a844-f72a53d871a1 |  | note | Acceptance / Conformance Criteria - Holes for fixings shall be formed using a rotary hammer drill. It is not permissible to cut or core through reinforcement. Should reinforcing steel be struck, the hole shall be abandoned, cleaned out using compressed air and backfilled with SikaDur UA Epoxy Repair Mortar or a similar approved mortar.
label | b8afa223-5de7-5985-a995-a1efb68e2212 |  | note | Standard / Specification - PS 18.6.1, PS 19.25.1
label | 4ead022c-6ddc-53fb-8d95-666535df23e7 |  | note | Verifying Document - Site Records
label | db05bafc-3fc0-5f5b-80be-cc5c53ad72dc |  | note | Frequency - Each Hole
label | d3d31e7f-a8cd-59f8-bb88-21465b794f98 |  | note | Verification Activity: Activity - S
label | 78441b7e-6dcf-5ac2-9c0c-7c3e7e63037d |  | note | Verification Activity: By - SE
checklist-sectioned |  |  | checklist | ITP - Kerb & Channel and Footpaths - 301 - Rev B | itp |  |  |  | Yes | ITP - Kerb & Channel and Footpaths - 301 - Rev B | d0f1ba3e-857d-468b-8f0d-fde3bcf9d9c8
checkpoint-group |  |  | section | 4.18 Kerb and Channel Materials
checkpoint-status |  |  | checkpoint | 4.18.1 - Water and Aggregate
label | be5bf2bf-b7f0-553d-83fd-4c6e95443422 |  | note | Acceptance / Conformance Criteria - Water and aggregate for concrete shall comply with NZS 3121.
label | 5a215f1b-60ab-5c36-8525-8b0602449b77 |  | note | Standard / Specification - PS 17.2.1
label | fda426a2-2352-550f-b2c8-50864efc9fcc |  | note | Verifying Document - Details / Mix Design / datasheet
label | a7b1ae37-fc22-543f-b1d3-4864d8108f54 |  | note | Frequency - Prior to use
label | 804542b6-ac6f-57a6-815d-65b2be7fb0d1 |  | note | Verification Activity: Activity - R
label | 88323dcb-a549-55e0-ba7f-64f6f54c6551 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.18.2 - Cement
label | 168d81c6-7590-50a7-bc31-f1df0b22573b |  | note | Acceptance / Conformance Criteria - Cement shall comply with NZS 3122 Type GP.
label | 47946d15-6767-522f-905e-650595871273 |  | note | Standard / Specification - PS 17.2.2
label | 1bb1304b-581f-57e7-8463-f7b63841a3ff |  | note | Verifying Document - Details / Mix Design / datasheet
label | 3f218ca8-5cf7-51b5-91a0-f270d456e597 |  | note | Frequency - Prior to use
label | ad10425b-eb9e-52cc-9512-c56a26e05be0 |  | note | Verification Activity: Activity - R
label | e5bafb61-d22b-553b-a482-ccf2fd6dbf5f |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.18.3 - Concrete
label | 227321ad-dc4f-52ca-ab2b-079a97c9e522 |  | note | Acceptance / Conformance Criteria - All concrete, except site concrete, shall be manufactured by an approved ready-mix plant unlesspecifically approved otherwise in writing by the Engineer.
label | 3c29ede9-eb8d-5b0c-a580-771b54e061d9 |  | note | Standard / Specification - PS 17.2.3
label | d883e904-0de5-5c98-8acd-8a15771c8b41 |  | note | Verifying Document - Plant Details
label | fd1acf21-653e-50a9-b2c2-9d03c424a8a3 |  | note | Frequency - Prior to use
label | e4958fc7-50a3-53c4-b04c-4aad3883f610 |  | note | Verification Activity: Activity - R
label | 3f63c732-b5ee-518a-b1d2-2547da65fffd |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.18.4 - 20MPa Concrete
label | 49e8710c-e912-56d0-84c4-7f14e1a3a5e0 |  | note | Acceptance / Conformance Criteria - Concrete for structures shall be grade 20 and have a minimum crushing strength of 20MPa at 28 days except where otherwise specified.
label | 7f6fde25-0b51-5845-bc7e-432bd0881a6a |  | note | Standard / Specification - PS 17.2.3
label | 12af8429-6be2-5d4a-a9c7-aef78900c312 |  | note | Verifying Document - Mix Design
label | d46ad03e-e442-57f8-8c2f-a00bc533f7bd |  | note | Frequency - before the commencement of works
label | 81dc0405-1c0c-59f1-ba45-d508b45ea5c4 |  | note | Verification Activity: Activity - HP
label | 5adc0e8e-6297-512f-8d8e-5d474eaffb9f |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.18.5 - Mortar
label | f13f815f-73dc-584b-af5f-bbd24ddfb71d |  | note | Acceptance / Conformance Criteria - Mortar shall consist of two parts of fine, sharp, well graded sand to one part of cement measured by dry loose volume and well mixed by hand (unless otherwise specified), or in a suitable mechanical mixer, with just sufficient water to make it slightly moist. It shall be mixed in small quantities as required. Any mortar not used within 30 minutes of mixing shall be discarded.
label | baf0b90d-092b-59bc-91b6-922b136ee6fe |  | note | Standard / Specification - PS 17.2.4
label | 8c2a6dd2-146a-5386-91e1-f7c230a1f3c3 |  | note | Verifying Document - Datasheets
label | 79cf7990-0f77-5910-bca1-ced6eac4b2e8 |  | note | Frequency - Prior to use
label | ac70cd69-2d3d-5d3b-b9a0-1d2b899ab081 |  | note | Verification Activity: Activity - R
label | d6bbbb21-09d2-5a4d-9a76-8b39050a0877 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.18.6 - Reinforcing
label | ff92cf45-0025-5a84-91c8-81c914c5f593 |  | note | Acceptance / Conformance Criteria - Reinforcing shall be Grade 300 bars unless otherwise shown. Grade 430 bars shall not be substituted for Grade 300 bars without the approval of the Engineer. Welded wire fabric shall comply with AS/NZS 4671.
label | cbc4f871-bb3b-53d2-8fd2-aa68bcd6e3c5 |  | note | Standard / Specification - PS 17.2.5
label | 7144abc7-39d1-5902-a41f-9bbf5ba47cd5 |  | note | Verifying Document - Mill Certs
label | 63d97bf9-bbec-5bd7-8aaa-babd2a61ba77 |  | note | Frequency - Prior to Completion
label | f695a162-111a-506d-956a-f243031a6d81 |  | note | Verification Activity: Activity - R
label | 9c1d510f-44be-57cd-a684-8ced0992afb4 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.18.7 - Kerb and Channel Concrete
label | 301cae98-ba6b-5281-8689-8a0f2e97c0d5 |  | note | Acceptance / Conformance Criteria - Kerb and channel shall be cast in-situ using 20MPa concrete placed by an approved extruding machine operated by skilled personnel. The profiles shall be in accordance with the Drawings and shall be specifically approved by the Engineer before work is commenced.
label | 11f4d84b-5222-5f86-bbb8-64be43567616 |  | note | Standard / Specification - PS 17.3.2
label | 6eba89d2-e1c8-5397-a80b-112ca3a5ed28 |  | note | Verifying Document - Mix Design
label | 3c80a496-6a9b-5a7d-a7cb-f78ed4bc7cff |  | note | Frequency - Before the commencement of works
label | 57e0fae1-6728-5210-a269-e5cceec88611 |  | note | Verification Activity: Activity - HP
label | 0556b86b-9ea7-56ec-8a94-d445ba637060 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.18.8 - Machine Laid Kerb Channel Concrete
label | e2a5b46a-847e-5b91-a116-a5c909b5a2e8 |  | note | Acceptance / Conformance Criteria - Kerb and/or channel may be cast in situ using 25MPa concrete placed by an approved machine operated by skilled personnel. The profiles shall be in accordance with the Drawings and shall be specifically approved by the Engineer before work is commenced.
label | 17fc7fde-b7bf-5be7-88ac-db875767918b |  | note | Standard / Specification - PS 17.3.4
label | a0092dbf-4d58-5fd0-ba55-413ac82fe9f0 |  | note | Verifying Document - Mix Design
label | 623459f0-de21-548e-9fd0-f1e396ca6e98 |  | note | Frequency - Before the commencement of works
label | 1b2840d4-40c0-57db-9e09-8657b5e31b83 |  | note | Verification Activity: Activity - HP
label | e250af6d-e43e-534d-acd9-295bbfa2d112 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.18.9 - Island Infill Concrete
label | 1bc18213-9965-59f0-a752-bdbc99c136e6 |  | note | Acceptance / Conformance Criteria - The new concrete shall be 100mm in depth, coloured “Indian Summer” and constructed in accordance with NZS 3109. The concrete shall have a 28-day compressive strength of 17.5 MPa.
label | 9fa6b8e0-0d32-5722-ac4f-0e31cc08df16 |  | note | Standard / Specification - PS 17.3.6
label | ab2a4764-9abe-5a1a-94b3-deb0fb9548d1 |  | note | Verifying Document - Mix Design
label | a2c750b5-f76c-5b94-9d1d-1a28389700d3 |  | note | Frequency - Before the commencement of works
label | 0f30ea9d-5e10-553e-80d8-41515e9e77bd |  | note | Verification Activity: Activity - HP
label | 52fb4a28-a308-58c9-abab-fedeee00ff87 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.18.10 - Kerb Profiles
label | b6789f3f-2dc7-56e7-adfc-de20535a70df |  | note | Acceptance / Conformance Criteria - The profiles shall be in accordance with the Drawings and shall be specifically approved by the Engineer before work is commenced.
label | 3a6a6bf3-6a4e-57ab-8fd7-e8a05dee9457 |  | note | Standard / Specification - PS 17.3.2
label | 0a1ea561-82d1-5dfe-9d07-f94f1c30de00 |  | note | Verifying Document - Profile Details
label | 292014f1-d25d-5286-88c0-16dc1fe23e88 |  | note | Frequency - Prior to use
label | 969fae7e-4f30-5f20-889f-e7e9bea01b8b |  | note | Verification Activity: Activity - R
label | 99b9e027-ce62-531f-a250-c932b8c2431e |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.18.11 - Shared Paths Concrete
label | 336da877-4274-5646-a908-483d70472279 |  | note | Acceptance / Conformance Criteria - Shared path shall be constructed from 25MPa concrete and shall be 100mm thick. The concrete shall include 3% black oxide colouring.
label | cfd70809-dc89-5fae-b0ee-a90c9a0af3fb |  | note | Standard / Specification - PS 17.4
label | 94cf8b49-2984-5f0c-9c3c-a956101bfa2a |  | note | Verifying Document - Mix Design
label | 4a4b9333-bba9-534d-b5bd-6c4478603453 |  | note | Frequency - Before the commencement of works
label | 67fd99e5-ccdf-50e0-a9c4-7e1bd95f0398 |  | note | Verification Activity: Activity - HP
label | 1c89ba5d-b267-5685-9dcb-f33588dff937 |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.18.12 - Roundabout Concrete Apron Concrete
label | 8e723ab7-1a0e-52db-8492-2b1f660e2485 |  | note | Acceptance / Conformance Criteria - The roundabout apron shall be constructed from 40MPa concrete
label | 0415aa84-ec35-538f-a33f-7a42c0f1614d |  | note | Standard / Specification - PS 17.4.2
label | 33376cf6-bf6f-529f-b63f-c5e35f1fb2a3 |  | note | Verifying Document - Mix Design
label | fcd8e624-e658-568b-b5ec-2fa27884debb |  | note | Frequency - Before the commencement of works
label | ee3a082f-0b68-5e93-bdf5-6806930d96f2 |  | note | Verification Activity: Activity - HP
label | 9d65e1c2-0fea-5572-b98f-53f823a97a1d |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.18.13 - Driveway Access Concrete
label | 23bdcb9d-be54-55d1-b6f6-e5a465ff4df2 |  | note | Acceptance / Conformance Criteria - The access roads shall be constructed from 20MPa concrete
label | 1ce09dd8-83b2-59f9-aa2f-e97000d682d1 |  | note | Standard / Specification - PS 17.4.3
label | 2f47e730-8ec2-5767-a520-82f8caf3613d |  | note | Verifying Document - Mix Design
label | aa13488a-cedd-5490-8f51-bab837f693dc |  | note | Frequency - Before the commencement of works
label | f70645f3-9a77-50da-9c97-0fa1aed37eaf |  | note | Verification Activity: Activity - HP
label | 85a21515-fcda-5209-b5d8-499da012d0aa |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8.01 Kerb and Channel
checkpoint-status |  |  | checkpoint | 8.01.1 - Saw Cutting
label | 6cf388df-fc35-577f-8623-a9ae5415c96b |  | note | Acceptance / Conformance Criteria - Existing surfaces shall be sawcut at the limits of excavation if they are not to be reconstructed following the construction of the concrete kerbs and channels etc. Existing kerbs to remain shall be sawcut to 50mm depth on all exposed faces.
label | fd944808-c904-556d-9003-66844ce3abfc |  | note | Standard / Specification - Downer
label | f37553f4-4f0c-504b-891e-702ec78f0031 |  | note | Verifying Document - Photos
label | a6737b47-b898-54f9-804d-ee23eb45ecd0 |  | note | Frequency - Each Kerb
label | 440f2025-0800-58df-945e-60a4604eea68 |  | note | Verification Activity: Activity - I
label | 50af0888-61f8-5a50-bf06-6ec504987962 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.2 - Foundations
label | 4c5a2760-066e-5ad6-bfca-1a62c5b87c61 |  | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label | f1812c29-8ce2-536d-9038-19f6976fddce |  | note | Standard / Specification - Downer
label | 6f0d0614-8f41-5a90-b2c6-a7ce7800124c |  | note | Verifying Document - Scala Report
label | 5a7ae900-9a07-5858-9fba-6483e4ad7ead |  | note | Frequency - 20m
label | ab818df7-34f7-50dc-a738-458d1c5b1d0f |  | note | Verification Activity: Activity - I
label | d07cca8e-1f04-5a6e-a090-ab094b5b081d |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.3 - Fill Compaction Testing
label | 96c76541-70a9-5ddc-bc06-40876208d04c |  | note | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
label | 0e8a6669-19b2-51d1-870a-b7cf1120bc31 |  | note | Standard / Specification - Downer
label | 091b9c17-3d9c-530a-96d8-d96b7621d660 |  | note | Verifying Document - IANZ NDM Report
label | 4c9b04b3-3871-5d07-a893-69209b12996c |  | note | Frequency - 20m
label | 30df1319-c430-5cc1-92a8-22c0227339e7 |  | note | Verification Activity: Activity - I
label | 1813f515-4dd0-5552-9ba9-3f6b928d5db2 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.4 - Kerb String Line Inspection
label | b8f2be67-5b40-54a6-bb25-343c9a6892a1 |  | note | Acceptance / Conformance Criteria - Prior to laying, string lines will be inspected by the Engineer.
label | f9fe1f4a-7271-5167-9011-e9ccd9a91992 |  | note | Standard / Specification - PS 17.3.2
label | 9525a333-b1b7-5f1d-8d92-0b3f08be853f |  | note | Verifying Document - Pre Pour
label | 3c84b669-10a9-59d2-a22d-eca89b7e7e0e |  | note | Frequency - Prior to Pour
label | b3d3945b-0b9e-5b48-81c7-47814d539999 |  | note | Verification Activity: Activity - W
label | 3a4d1cd0-9f74-5254-ab3f-6618a9593bbf |  | note | Verification Activity: By - ENG
checkpoint-status |  |  | checkpoint | 8.01.5 - Kerb
label | cf73faef-e540-5849-b69c-edb922217c89 |  | note | Acceptance / Conformance Criteria - Contraction joints (saw cut joints) in channels shall be formed at maximum 4m spacings, at right angles to the kerb line. The joint material shall be set flush with the surface and shall be a minimum of 25mm deep.
label | 3b7bee5f-ec28-5670-a9b0-162a41ac7961 |  | note | Standard / Specification - PS 17.3.2
label | 1871c867-9fbd-5095-9585-ab4979a4eba9 |  | note | Verifying Document - Post Pour
label | d5ae75e3-8b02-5d40-855a-358a0739a8c6 |  | note | Frequency - Every 4m
label | 5ea0feee-daf3-5823-a1c4-11849ac257a3 |  | note | Verification Activity: Activity - R
label | 03f736ba-659b-5415-9e01-938f755c4258 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.6 - Kerb Finish
label | 09194d76-f3f8-5f5f-88c7-622da6846cf3 |  | note | Acceptance / Conformance Criteria - Concrete surfaces, un-trafficked by vehicles or pedestrians exposed to view above ground level, shall be smooth and comply with Finish F4 in NZS 3114. Horizontal concrete surfaces, trafficked by vehicles or pedestrians, shall be wood floated to comply with Finish U2 in NZS 3114.
label | 4670f226-4665-5002-bcc4-c097779bbc4d |  | note | Standard / Specification - PS 17.3.2
label | 19100c72-136c-58fd-b28e-756c9a3fe382 |  | note | Verifying Document - Post Pour
label | 33d58e13-2895-54d6-ace2-f475631baf6e |  | note | Frequency - Each pour
label | c9cbb6b8-c929-58f4-b127-5575052cdbb8 |  | note | Verification Activity: Activity - R
label | ff1848a5-c378-5162-b126-789cbdfc678c |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.7 - Unreinforced Channel Contraction Joints
label | 9f78cf9a-ae0e-583c-9e95-e8352c662cf7 |  | note | Acceptance / Conformance Criteria - Contraction joints in unreinforced channels shall be formed at 4-metre centres, at right-angles to the kerb line, by insertion of “Malthoid” D.P.C or equivalent strip. The joint material shall be set flush with the surface and shall be a minimum of 25mm deep. Contraction joints shall be coincident with joints in precast kerb blocks.
label | 2671738c-5b2b-5942-9452-c0cd8e0aea0b |  | note | Standard / Specification - PS 17.3.3
label | 6c0ffcb7-bfc7-5d67-ab83-b465840ad68c |  | note | Verifying Document - Post Pour
label | 0c22e6e5-4adc-5007-8e46-93d65daa1d4b |  | note | Frequency - Every 4m
label | 1ee9f524-dcef-5412-babb-9004ad3a35cf |  | note | Verification Activity: Activity - R
label | 1c588ba7-2104-55c5-a002-3f4c5081a940 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.8 - Channel Finish
label | 86a4fd35-0386-5850-bf2f-e8d1f84edc5a |  | note | Acceptance / Conformance Criteria - The top surface of channels shall be finished smooth and even with a steel trowel. Channels shallnot pond water at any point.
label | a2adc760-7f94-585d-8642-8cfc96ad41f4 |  | note | Standard / Specification - PS 17.3.3
label | b69d16dc-634c-5c18-8c1b-3156e67fa753 |  | note | Verifying Document - Post Pour
label | 399bace6-1acd-51ea-99bc-53a7e493f7cc |  | note | Frequency - Each pour
label | 299d4570-263b-5430-bcde-f27115376a61 |  | note | Verification Activity: Activity - R
label | 9bdcf3b9-1899-5e46-803f-f059da4cb580 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.9 - Kerb and Channel Tolerances
label | 7681ee2c-753c-5398-be80-ca1e5f8c5446 |  | note | Acceptance / Conformance Criteria - Tolerances for kerb and channel shall be ±5.0mm vertically and ±10mm horizontally. The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | 0a82f234-6521-5757-9e64-8ff3c6d2bdb1 |  | note | Standard / Specification - 16.34.3
label | b2a381fd-0ffd-520e-b316-d9e8fed212cc |  | note | Verifying Document - Survey Records
label | 3a1e17ef-29dc-572b-bc81-840e0123ba92 |  | note | Frequency - At the completion of the construction of kerb and channel
label | f46406e3-9b07-5481-b8bc-1043b1654325 |  | note | Verification Activity: Activity - I
label | d447dc3b-47b3-557f-ba1a-e609a62176ab |  | note | Verification Activity: By - SV
checkpoint-status |  |  | checkpoint | 8.01.10 - Kerb and Channel Completion Inspection
label | 5408ae0a-475b-5086-a22f-754d47964805 |  | note | Acceptance / Conformance Criteria - Engineer to review completed works including kerb and channel position, level and grade, and transitions between kerb types and at catchpit and catchpit manhole aprons / back entry lintels.
label | 90e04a6b-59dc-5114-8cfc-346671ae967f |  | note | Standard / Specification - PS 16.38, PS 17.3.2
label | 42b1bb3f-73ec-5cef-9526-91d9bdd32a65 |  | note | Verifying Document - K&C QA
label | c96872cf-a48f-5ee7-8611-2f1e440d9fe0 |  | note | Frequency - Upon compltion of K&C
label | 5bcd98a0-64d4-5d95-879e-f2bae62d525a |  | note | Verification Activity: Activity - W
label | 97fbd497-e3b9-548e-847e-f8493d868715 |  | note | Verification Activity: By - ENG
checkpoint-group |  |  | section | 8.01.11 Machine Laid Kerb and Channel
checkpoint-status |  |  | checkpoint | 8.01.12 - Foundations
label | 0637c5eb-4570-5075-8771-27849dd5b730 |  | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label | fe69352d-1dd2-531e-81b8-ce7913674002 |  | note | Standard / Specification - Downer
label | 4f3e049f-1f30-51e8-97c3-3b77fe9d957e |  | note | Verifying Document - Scala Report
label | e00a2479-009e-5b29-88ec-367c2d347db2 |  | note | Frequency - 20m
label | a1985640-a8f1-5da8-8f11-c9b42709fe12 |  | note | Verification Activity: Activity - I
label | 4ccaba2e-1ba2-5f72-9251-9260f7751bb3 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.13 - Fill Compaction Testing
label | dc81a3fb-411a-578e-8519-ed2c71b001e6 |  | note | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
label | 2ff72dd9-5771-53f9-b7e2-ec4efc8ab6a6 |  | note | Standard / Specification - Downer
label | bd32a2f0-9d9e-5840-aca9-736e93236514 |  | note | Verifying Document - IANZ NDM Report
label | 910c3bcd-2faf-590a-8bac-122f33f1cbb7 |  | note | Frequency - 20m
label | 90cf80d4-f619-5f80-94b4-7761d4affdad |  | note | Verification Activity: Activity - I
label | f6a97e80-c74d-525e-8048-fbf657b5ea60 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.14 - Machine Laid Kerb Channel - Concrete island infill
label | a9218090-c26d-5c43-a0f9-b560445017fc |  | note | Acceptance / Conformance Criteria - The base of the infill area shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved AP40 granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 100mm. Where infill is to be placed directly onto pavement surfacing, a 25mm thick sand bedding layer is to be provided. The base layer shall be well wetted with water immediately prior to the placing of concrete.
label | b03620f6-20d8-5e7f-bc3f-671857fa23b5 |  | note | Standard / Specification - PS 17.3.6
label | 5e0b6178-81b3-52d1-86cc-c154143364a3 |  | note | Verifying Document - Pre Pour
label | 279af7ab-efc4-50ce-8a31-5a81ce5674c5 |  | note | Frequency - Prior to Pour
label | 2040fd97-cf60-58eb-91ff-3a01a56fae6c |  | note | Verification Activity: Activity - R
label | 61e671a0-ffd4-537d-9670-50a43ab0fca5 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.15 - Machine Laid Kerb and Channel - Contraction joints
label | f67c11ce-d078-5bb6-be23-58627d58e939 |  | note | Acceptance / Conformance Criteria - Contraction joints shall be formed at 5-metre maximum centres and at right-angles to the kerb line, by saw cutting or other approved method. Where a footpath adjoins the kerb, Contraction joints shall be coincident with joints in the footpath.
label | c3b57f4a-aca9-5acb-9f84-cff72a877fc3 |  | note | Standard / Specification - PS 17.3.4
label | 953e8842-fbce-5bba-a8bc-f4f70dad761d |  | note | Verifying Document - Post Pour
label | 4791aeff-a766-55cf-8daf-905e01973ee2 |  | note | Frequency - Every 5m
label | af0b2243-51da-5eab-886d-cd2541ca4305 |  | note | Verification Activity: Activity - R
label | bb116a0c-9d63-58ac-96ac-0e610137c703 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.16 - Machine Laid Kerb Channel - Pin on kerb
label | 43351789-aaf9-5fe4-b583-966a3e639136 |  | note | Acceptance / Conformance Criteria - Kerb installed on top of pavement surfaces shall be pinned using reinforcing pins, drilled, and epoxied into the existing pavement at a maximum spacing as specified in the drawings. Additional pins are to be installed at discontinuities or tight radius within the proposed kerb alignment.
label | aac2f4e0-1c3f-5e40-a899-27ec400f3c76 |  | note | Standard / Specification - PS 17.3.5
label | edc03c20-fe6e-572c-a7c8-16503a5017e4 |  | note | Verifying Document - Post Pour
label | aeccb51f-83b3-53e0-8ff3-559311067d42 |  | note | Frequency - As Required
label | 0615f53d-5de8-5911-8cca-85e29a3d8465 |  | note | Verification Activity: Activity - R
label | 6ac37496-be1f-5fe4-a29d-4dbd0a70a4cd |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 8.01.17 Concrete Island Infill
checkpoint-status |  |  | checkpoint | 8.01.18 - Foundations
label | 45ac8a1b-e867-523b-8641-81c5447d04b3 |  | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label | 58377c51-3af0-59a4-9de7-36b0eaa9ca75 |  | note | Standard / Specification - Downer
label | e2372d6a-ec23-5fe9-81aa-7de02fae6a31 |  | note | Verifying Document - Scala Report
label | 9369a171-89fb-56ad-8246-bc0f422ba36f |  | note | Frequency - 20m
label | 64400ba3-e1ab-5f12-908d-ae4de590e967 |  | note | Verification Activity: Activity - I
label | c2e74d2a-8f64-5be4-b600-b1662c8429d2 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.19 - Concrete Island Infill Bedding
label | 7d020bae-a73f-577c-9d73-91e1ce8349f8 |  | note | Acceptance / Conformance Criteria - The base of the infill area shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved AP40 granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 100mm.
label | d964d4b0-20e6-5dcb-9a00-c1428a5bae96 |  | note | Standard / Specification - PS 17.3.6
label | 90f7bca8-f724-5566-be5b-5d284ca36b6b |  | note | Verifying Document - Pre Pour
label | 438316db-a124-5837-bfb8-0e5dbcb0b645 |  | note | Frequency - Prior to Pour
checkpoint-status |  |  | checkpoint | 8.01.20 - Fill Compaction Testing
label | 3cdb3d31-8ad2-59a5-abcb-0cdcc7cd8aa3 |  | note | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
label | 76141d2f-ac44-5b87-8be7-c20e17a3e414 |  | note | Standard / Specification - Downer
label | 98cf1747-ebf0-5dcd-9ba5-ed75e9bf7e51 |  | note | Verifying Document - IANZ NDM Report
label | bfdc6180-085f-5a2a-bad8-39c0f845327c |  | note | Frequency - 20m
label | 4bca33e9-c28c-5d56-b9df-aebe683591c4 |  | note | Verification Activity: Activity - I
label | 259ababb-a4b6-582c-97b3-7cd46f60ec65 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.21 - Concrete Island Infill Concrete Placement
label | f39d72e9-51c7-5dbe-9fe9-79935ef98311 |  | note | Acceptance / Conformance Criteria - The new concrete shall be 100mm in depth, coloured “Indian Summer” and constructed in accordance with NZS 3109.
label | dd077481-7e3f-5d35-8864-a7f450b23d08 |  | note | Standard / Specification - PS 17.3.6
label | fe48b36b-dfe1-58a8-afcd-cf17edb91710 |  | note | Verifying Document - Pre Pour
label | d0aef5ed-7622-542e-8129-ee41be18fcda |  | note | Frequency - Prior to Pour
label | abd4ca6c-508a-5186-9216-28d93cf8bf46 |  | note | Verification Activity: Activity - R
label | d547e7f6-8cb2-5f69-a2e2-5cf6aac1f7d4 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.22 - Concrete Island Infill - Construction Joints
label | 5f9d1881-009f-52d2-aace-82cc7e165b20 |  | note | Acceptance / Conformance Criteria - The Contractor shall form construction joints every 4m by saw cutting or other approved method.
label | 83cd5651-ef99-5fde-85f1-8a4f35051006 |  | note | Standard / Specification - PS 17.3.6
label | 365062e5-0bdc-5923-9dd7-d044c9fea4f7 |  | note | Verifying Document - Post Pour
label | dd392e34-0959-5fc4-bf64-29fb16003a22 |  | note | Frequency - Every 4m
label | 649d978a-47b2-5f80-b0e8-10463d3986cf |  | note | Verification Activity: Activity - R
label | b083edbb-9e50-580d-9627-61f0fd9d8b60 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.23 - Concrete Island Infill Finishing
label | cb0454b8-f237-51fc-a779-883a893c21e2 |  | note | Acceptance / Conformance Criteria - The edges of the infill shall be neatly chamfered. Concrete shall be poured in one operation and without interruption between formed construction joints. The whole of the surface shall be screeded, and after the initial set, it shall be carefully broomed to achieve a NZS 3114 class U5 finish.
label | e536d3dc-6b1d-5731-9271-53b8690478f6 |  | note | Standard / Specification - PS 17.3.6
label | 5cb91d59-5c6c-5712-baaa-1b69f621e389 |  | note | Verifying Document - Post Pour
label | e6283326-9423-54c3-b702-3315f8a13520 |  | note | Frequency - Prior to Pour
label | 5daeb881-a07f-5710-a24b-6b807388e919 |  | note | Verification Activity: Activity - R
label | f8b50a23-ada9-594b-9abc-4852f4081398 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.01.24 - Concrete Island Infill Curing
label | 5d12cbd2-1e02-5cc0-97e5-9d85903d605c |  | note | Acceptance / Conformance Criteria - The finished work shall be kept continuously wet by approved means and shall be thoroughly protected from frost, from direct rays of the sun, and from drying winds, for at least seven days after pouring. The concrete shall be laid so no water ponding occurs on the surface after completion.
label | 770b8af7-0c5e-57c7-9e79-c5f0b0c49477 |  | note | Standard / Specification - PS 17.3.6
label | a0e479b1-c22d-53d2-be9c-6f02db565afb |  | note | Verifying Document - Post Pour
label | 5c9713bf-181d-599d-b2a9-fab942ce4f84 |  | note | Frequency - At least seven days after pouring
label | deda4d81-8392-5ad9-93ba-62f63ce84512 |  | note | Verification Activity: Activity - R
label | 6694150b-a490-52c5-9c4e-b18b561cd6f3 |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 8.04 Shared Paths, Roundabout Concrete Apron and Driveway Access Road
checkpoint-status |  |  | checkpoint | 8.04.1 - Foundations
label | f08c83ca-4bb7-5da0-b22b-b9d2d09c14b7 |  | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label | d92d4daf-c764-5d55-b62a-abd5013aec6e |  | note | Standard / Specification - Downer
label | f386da98-7a87-5f0a-b3dc-ef9b4eed966e |  | note | Verifying Document - Scala Report
label | 5fa3a5e3-1e5b-5f1f-b72f-045b52690b5e |  | note | Frequency - 20m
label | b41311d1-96d8-5c01-939f-817d25d1243e |  | note | Verification Activity: Activity - I
label | 84852e88-df43-598d-a014-37f231ab905e |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.04.2 - Driveway Access Subgrade and Subbase
label | 68c8c3e9-a5b1-5d0b-a463-c3515454afc4 |  | note | Acceptance / Conformance Criteria - As per Pavement Type D, the subgrade shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved NZTA M/4 (≥ 100MPa) granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 100mm. The granular base layer shall be well wetted with water immediately prior to the placing of concrete.
label | 265724b3-ddc6-5994-9f9b-7dbfcd06b7c2 |  | note | Standard / Specification - PS 17.4.3
label | bf67cd14-ff1d-54f3-bf33-1a78578b94f1 |  | note | Verifying Document - Pre Pour
label | fafc2a03-f89f-5b9f-b8bc-e53f18b66a38 |  | note | Frequency - Prior to Pour
label | 6dc85bf0-d621-5885-bfc4-19fda4752216 |  | note | Verification Activity: Activity - R
label | 193bca02-6e85-5b70-b820-4875117dd1cd |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.04.3 - Shared Paths and Roundabout Concrete Apron Subgrade and Subbase Installation
label | b10fdcb4-131f-518c-9c24-3aa4b082c157 |  | note | Acceptance / Conformance Criteria - The subgrade shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved AP20 granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 500mm.
label | daff9e8e-2ee4-5700-872d-53e7f15ef866 |  | note | Standard / Specification - PS 17.4
label | 12e803a9-44ea-5e1a-b14f-b11601d296d3 |  | note | Verifying Document - Pre Pour
label | aaec6e4e-9b35-55e8-ba14-85930c0fb2e2 |  | note | Frequency - Prior to Pour
label | 2a302336-9f71-5939-b37e-4f9bcafd338f |  | note | Verification Activity: Activity - R
label | dd30b4a1-8dbc-597f-8316-5fc0af41a302 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.04.4 - Fill Compaction Testing
label | be1674fb-8758-55db-9c6f-71e0700ea0ce |  | note | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
label | ffef5c7c-6c83-54d5-9599-6567d656b348 |  | note | Standard / Specification - Downer
label | 8576edbd-e726-5b87-a4ee-bbf2d0f8f8f5 |  | note | Verifying Document - IANZ NDM Report
label | 7a6eede5-30d6-5879-bfdb-497da1a3ebed |  | note | Frequency - 20m
label | c459f722-9f93-5c9c-98d6-e47a2b4f1312 |  | note | Verification Activity: Activity - I
label | c502c423-f9fc-5af5-b8e8-c68cf234305f |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.04.5 - Granular Base Prep
label | 36e0f658-9afa-524b-b152-13e219705318 |  | note | Acceptance / Conformance Criteria - The granular base layer shall be well wetted with water immediately prior to the placing of concrete.
label | c9a6687c-7c2c-51c8-be70-d86cf36f2718 |  | note | Standard / Specification - PS 17.4
label | 14edf572-db73-502b-9c2f-823f94987a8d |  | note | Verifying Document - Pre Pour
label | 0d0845c5-9db4-53bd-b843-5c38f76c1ff5 |  | note | Frequency - Prior to Pour
label | fa4dabba-a159-5c98-941c-4c26708cbff9 |  | note | Verification Activity: Activity - R
label | 744ccad1-2fd5-5020-b40e-ab0d1d095162 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.04.6 - Shared Paths, Roundabout Concrete Apron and Driveway Access - Construction Joints
label | 0b882b1a-54ed-57de-b2ef-1a900961c4af |  | note | Acceptance / Conformance Criteria - The Contractor shall form construction joints every 4m by saw cutting or other approved method. Concrete shall be poured in one operation and without interruption between formed construction joints.
label | 9cafa865-1754-5522-b566-e7614e98b275 |  | note | Standard / Specification - PS 17.4
label | eb12bbad-e734-5c68-bb76-45e1465ed3cd |  | note | Verifying Document - Pre Pour
label | 9fc046fb-8005-549a-bf1e-58887a8a6394 |  | note | Frequency - Every 4m
label | b4651f5b-9f01-55f5-a66c-90ea5ec3cda8 |  | note | Verification Activity: Activity - R
label | fab696dc-0501-54e9-9b6e-48de8ebfebbd |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.04.7 - Roundabout Concrete Apron - Reinforcing Placement
label | d8a8bb25-3650-50a2-8864-9ed882e5cb00 |  | note | Acceptance / Conformance Criteria - D12 reinforcing bars spaced at 400mm centres radially and D12 reinforcing bars spaced 300mm centres centrally placed as per the drawings and shall be 200mm thick.
label | 786087d0-e7d3-5049-ace2-1f0437dc445d |  | note | Standard / Specification - PS 17.4.2
label | 2d08e922-7f39-57cd-9c58-8b7287186b5b |  | note | Verifying Document - Pre Pour
label | ab0164af-b5f5-5e5a-a789-b5cab5c805e8 |  | note | Frequency - Prior to Pour
label | e8c24c0e-12b8-5896-acc5-a2cea17ef3f8 |  | note | Verification Activity: Activity - R
label | 503e75d7-fe14-576c-8d97-c183402b2cb8 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.04.8 - Roundabout Concrete Apron - Expansion Joints
label | d5683c9d-716e-503c-bf42-cfd7f4f2dba8 |  | note | Acceptance / Conformance Criteria - Expansion joints shall be formed at maximum spacings of 21m.
label | bc28bd0f-ed2f-55ca-b2ee-628ec7c95ec3 |  | note | Standard / Specification - PS 17.4.2
label | 03c26c18-06fe-522a-9c2c-338ef3cd8ea1 |  | note | Verifying Document - Post Pour
label | b6b7b8bc-93f9-5d93-a88c-0416afe24063 |  | note | Frequency - Every 21m
label | e47d62e9-1384-570c-a2d0-12b44b9456ab |  | note | Verification Activity: Activity - R
label | 420a722a-821b-52e2-bd00-c839bcfe93a8 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.04.9 - Shared Paths, Roundabout Concrete Apron and Driveway Access - Finishing
label | c2bcbca2-eeb5-5f52-8f10-6c1783c780ac |  | note | Acceptance / Conformance Criteria - The edges of the paths shall be neatly chamfered. The whole of the surface shall be screeded and after the initial set it shall be carefully broomed transversely to present a non-skid surface. The surface shall comply with NZS 3114 class U5.
label | e06d7939-8b7f-5f39-9d45-79238a9bdc61 |  | note | Standard / Specification - PS 17.4
label | f005448d-8f90-5551-ba48-cfe3c1597707 |  | note | Verifying Document - Post Pour
label | 76ad6bf5-12e7-52f9-a20a-d2d7b70027a3 |  | note | Frequency - Prior to Pour
label | 6e4308fd-c142-5fa2-8ce3-8908f7da2d56 |  | note | Verification Activity: Activity - R
label | 9519d298-1154-58db-81f2-dda793bc14c3 |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 8.04.10 - Shared Paths, Roundabout Concrete Apron and Driveway Access - Curing
label | 8fa66357-cfdc-5fb2-b31c-b58102f29038 |  | note | Acceptance / Conformance Criteria - The finished work shall be kept continuously wet by approved means and shall be thoroughly protected from frost, from direct rays of the sun, and from drying winds for at least seven days after pouring. The boxing supporting the vertical faces shall not be removed for at least 36 hours after the concrete is placed.
label | df9d0a8b-72ae-5b46-b0b3-52f1a2b364a2 |  | note | Standard / Specification - PS 17.4
label | 3629b9ac-7c68-58c6-92ad-2ceda059e4f8 |  | note | Verifying Document - Post Pour
label | 823cc156-5bf2-5c6d-8ecd-3c65163fa854 |  | note | Frequency - At least seven days after pouring
label | b42fd021-fde1-5e65-84e5-c2aed2377d6f |  | note | Verification Activity: Activity - R
label | 373f7378-24bb-5c2c-98c4-b80a37141cc5 |  | note | Verification Activity: By - SE