## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP009 - Unbound Pavements (FCR & RCC) | itp |  |  |  |  | FH-ZU2-QU-ITP009 - Unbound Pavements (FCR & RCC) - Rev 0
section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | Reference Documents - Aconex
label | Inspection/Test Method - Visual inspecti on
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls, weather, and material properties.
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | ○ Check weather prior to starting any works.
label | ○ FCR material used for the works in accordance to VicRoads Class 2 Crushed Rock.
label | ○ RCC material to be used for the Works in accordance with VicRoads Class 3 Crushed Rock.
label | ○ Checking underlying layer ITP’s (subgrade ITP008 and select fill ITP004 has been completed)
label | Reference Documents - PSP, EMP, TMP, WP SWMS, Spec Cl 4.19, Spec cl. 4.1, VicRoads Technical Note 107 Spec cl. 4.6
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
checkpoint | 1.3 - Material Report - Fine Crushed Rock (FCR) Material & Recycle Crushed Concrete (RCC)
label | Frequency - 7 Days - Prior to works
label | Acceptance Criteria - Material Report to be submitted 7 days prior to works to include;
label | ○ Source and Quarry location
label | ○ Quarry material is sourced from.
label | ○ Material rock type and petrographic description
label | ○ Historical test results
label | ○ Method of processing and transportation
label | ○ Material summary of the results of recent test on samples of the material from the source
label | Reference Documents - Spec cl 4.20.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principles Rep
date | Date Completed:
label | Principal’s Representative - Aconex Ref: Holcim RCC Class 3 - DCWC Mgt-GCOR-009582
label | ○ Holcim FRC Class 2 - DCWC Mgt-GCOR-009581
label | ○ Stirling Class 3 - DCWC Mgt-GCOR-009565
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Reference Samples
label | Frequency - 5 Days prior to works
label | Acceptance Criteria - Reference samples to be submitted 5 days prior to works commencing. Two bags to be taken each weighing 25kg. One bag submitted to Client, one retained by Contractor
label | Reference Documents - Spec cl. 4.20.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principles Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Trial Section
label | Frequency - Prior to works
label | Acceptance Criteria - Trial section to be completed with Principles Representative approving the use of the spreading machine.
label | Reference Documents - Spec cl. 4.7
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principles Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Compaction Equipment
label | Frequency - Prior to works
label | Acceptance Criteria - Pneumatic tyred rollers having a weight of 27t (min roller weight can be 7t spread across 7 wheels). Tyre inflation pressure to be checked. A 15t to 20t smooth drum roller to be used.
label | Reference Documents - Spec Cl 2.4.3 Item 84 Tender Clarificatio ns
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project/Site Engineer, Principles Rep
date | Date Completed:
section | 2.0 - Placement of Sub-basecourse and Basecourse
checkpoint | 2.1 - Layer Placement Parameters
label | Frequency - Every Lot
label | Acceptance Criteria - Summary of Parameters for each Lot;
label | ○ A lot is defined as one layer placed in a single days production of uniform material
label | ○ Max Layer is 200mm
label | ○ Min Layer is 75mm
label | ○ Final Surface Level +0mm, -10mm (excluding intermediate layers)
label | ○ Shape: every 10m intervals, <7mm deviation over 3.5m straight edge (excluding intermediate layers)
label | ○ Material to be batched within 1% of OMC
label | Reference Documents - Spec Cl4.8, cl 4.21.2, cl 4.13
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.2 - Placement Checks
label | Frequency - Every Lot
label | Acceptance Criteria - During placement of the material check;
label | ○ Deliveries do not disturb underlying layer
label | ○ Spreading starts from crown / high side where practical.
label | ○ Material does not get contaminated during placement / delivery
label | ○ Watercart is present to condition material as required
label | ○ Edges are cut / removed if dry of not compacted with abutting lots
label | Reference Documents - Spec Cl 4.8
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.3 - Compaction Check
label | Frequency - Every Lot
label | Acceptance Criteria - During Compaction check;
label | ○ Heavy smooth drum roller of 15t to 20t is used for initial compaction
label | ○ Pneumatic roller of 27t will compact material for final consolidation.
label | ○ A heavy smooth drum roller (in static mode) may also be used for final consolidation
label | ○ Watercart Present onsite for conditioning
label | ○ Materials are trimmed to required shape and level
label | Reference Documents - Cl 4.10
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.4 - Services & Culverts
label | Frequency - Every Lot
label | Acceptance Criteria - Check if any culverts or services are with the influence zone for compaction.
label | ○ A general rule, FH will seek advice from the Principles Representative if any culverts, duct banks or RCP pipe are identified closer than 1m from pavement layer surface. If identified, Fulton Hogan will maintain a 1m exclusion zone either side from centre of service for vibrating compaction activities. Hand held DPU’s/whacker plate to be used in lieu of rollers in restricted areas.
label | Reference Documents - CL4.10
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.5 - Protection of Layer
label | Frequency - Every Lot
label | Acceptance Criteria - Protect area from undue deterioration by;
label | ○ Section off area for at least 12 to 48 hours to allow material to dry back.
label | ○ If unable to do so, keep traffic to a minimum
label | ○ Or ensure any traffic that has to cross pavement layers, do not follow the same driving line.
label | Reference Documents - Cl4.17
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.6 - Proof Rolling
label | Frequency - Every Lot
label | Acceptance Criteria - Proof rolling will be undertaken at the top layer surface of the imported select fill material for under pavements using a 16T smooth drum roller (minimum), or a 15kL watercart (minimum).
label | ○ Principles Representative to be invited to proof roll 24 hours prior to inspection.
label | ○ Principles Representative must witness the proof roll.
label | ○ Following completion of the successful Proof Roll, Principles Representative will approve Fulton Hogan to place the next layer.
label | ○ Placement of next layer can occur once lot is accepted following proof roll. Proof roll inspection will satisfy pre-placement CTB inspection
label | Reference Documents - CL 4.11, CL 4.8, CL 4.16, CL 5.9
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP, HP, WP, HP, HP
label | Responsibility - Project/Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Completion of Remedial Works (if required)
label | Frequency - As required
label | Acceptance Criteria - Completion of remedial works or nonconforming Sub-Basecourse and/or Basecourse to be approved by Principal’s Representative before proceeding with the next layer of pavement Works.
label | Reference Documents - Spec cl. 4.21.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project Engineer, Principal’s Representative
date | Date Completed:
label | Principal’s Representative - (if required)
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Testing, Lot Size and Compliance
checkpoint | 3.1 - Survey Conformance
label | Frequency - Every Lot
label | Acceptance Criteria - Final survey level to be checked in a 5mx5m grid to conform with -10mm to +0mm.
label | ○ Survey report not provided for intermediate layers of the same material type (i.e. for PT2 where multiple layers of same material type placed).
label | Reference Documents - Cl 4.13
label | Inspection/Test Method - Survey Report
label | Record of conformity - This ITP signed
label | SCP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.2 - Surface Smoothness
label | Frequency - Every Lot
label | Acceptance Criteria - Surface smoothness to be checked every 10m by placing a 3.5m long straight edged on the ground a checking any deviations over 7mm. Complete within 7 days of completion of each section. Document results.
label | ○ Intermediate layers and shoulder pavements are not required to be checked.
label | Reference Documents - Cl 4.14
label | Inspection/Test Method - Verify
label | Record of conformity - Report
label | TP, HP
label | Responsibility - Project/Site Engineer, Principles Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Layer Thickness
label | Frequency - Every Lot
label | Acceptance Criteria - Check thickness of layer using survey at the frequency of field dry density determinations. Thickness shall not be less than what is shown on the design documentation other than allowable construction tolerances.
label | ○ Total pavement thickness is to be checked. Intermediate layers, no check is required.
label | Reference Documents - CL 4.12, CL4.21.1
label | Inspection/Test Method - Survey
label | Record of conformity - Survey Report
label | SCP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.4 - Degree of Saturation - Sub-Basecourse or Basecourse
label | Frequency - Every Lot
label | Acceptance Criteria -  Degree of Saturation to be tested for information.
label | ○ Target less than 70% Mean Moisture Ratio.
label | ○ Test to be taken the shift prior
label | ○ If lot gets impacted by significant wet weather, tests to be re-taken
label | Reference Documents - Cl 4.9
label | Inspection/Test Method - Test
label | Record of conformity - Test Report
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.5 - Field Dry Density
label | Frequency - Every Lot
label | Acceptance Criteria - Dry density for basecourse layer has the following acceptance criteria:
label | ○ Average of 5 consecutive tests exceeding 100% MMDD.
label | ○ No individual test result less than 98% MMDD.
label | ○ Principal’s Representative approval based on the results of proof rolling.
label | Dry density for sub-basecourse layer has the following acceptance criteria:
label | ○ Average of 5 consecutive tests exceeding 98% MMDD.
label | ○ No individual test result less than 95% of MMDD.
label | Principal’s Representative approval based on the results of proof rolling.
label | Reference Documents - CL4.10 Cl4.21.1
label | Inspection/Test Method - Test
label | Record of conformity - Report
label | TP, HP
label | Responsibility - Project/Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Quality Assurance Records
label | Frequency - Each Lot
label | Acceptance Criteria - Submit test results on Aconex for every lot of Sub Base and Basecourse. Results to summarise each test (Moister content, field dry density and layer thickness).
label | ○ Aconex ref to be submitted as Hold Point sign off.
label | Reference Documents - Cl4.21.2
label | Inspection/Test Method - Verify
label | Record of conformity - Summary of results
label | HP
label | Responsibility - Project/Site Engineer
date | Date Completed:
text | Aconex Ref:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: