## ITP
|  | Inspection and Test Plan | [7 empty] | Document # 1145-C200-FUL-QAC-ITP-0015
[10 empty] | Revision: 00 | Date: 21/05/2024
Client: | MRPV | Construction Process: | Structural Grout (Pedestals, Bearings, Base-plates & Pockets) |  | Prepared by: |  | Reviewed by: |  |  | Approved by:
Project: | Craigieburn Road Upgrade | Specifications: | Department of Transport & Planning Specification 610 - February 2020 Department of Transport & Planning Bridge Technical Note (BTN) 024 |  | Name: Mike Freeman |  | Name: Karim Habib |  |  | Name: Dirk Slabbert
Contract No: | 1145 | Structure / Component: | Miscellaneous Structures |  | Position: Special Projects Manager |  | Position: Graduate Engineer |  |  | Position: Quality Manager
|  | Location: | Project-wide |  | Date : 27.08.2020 |  | Date : 9.01.2024 |  |  | Date : 21.05.2024
Lot No: | ITP-015-AX-LOT-XXX | Lot Details: | ITP-015-AX-LOT-XXX - Description |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminaries - Materials
1.1 | Product Selection | Once, for each product, prior to placement of product | Product to be selected based on the following criteria: i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar ii. have the required strength at 28 days as noted on the IFC drawings. iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings. Note: Pedestals 200mm or greater shall be constructed from concrete - use the Structural Concrete ITP instead Enter: Teambinder Material Approval number [free text box] | IFC Drawings 610.28 610.33 | Document Review | This ITP | AP | Superintendent
1.2 | Curing Compound | Once, for each product, prior to placement of product | Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Note: This may be the same product used for the concrete curing Enter: Teambinder Material Approval number [free text box] | 610.23 (d) | Document Review | This ITP | AP | Superintendent
2 | Preliminaries - Procedures & Documentation
2.1 | Curing Methodology (for Concrete, Grout and Mortar) | Once, 4 weeks prior to placement of product | Curing methodology/procedure to be submitted for review to the Nominated Authority. Note: This may be the same document used for the concrete curing. Enter: Teambinder Correspondence Approval number [free text box] | 610.23 (a) | Document Review | ConQA Hold Point Release | HP | Superintendent
3 | Pre-construction Activities
3.1 | IFC Drawings | Prior to starting Works and at regular intervals | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | FH Quality Management Plan | Document Review | This ITP | HP* | All
3.2 | Survey Set-out | Each element | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.472 as applicable to the element. | IFC Drawings 610.47 (a) Table 610.472 | Measure Visual | This ITP | SCP | Surveyor SE/PE/SPE
3.3 | Construction Joint | Each element | Where required, the concrete substrate is to be roughened / scabbled in accordance with the drawings and or Product TDS. Pedestals shall be rebated to 20mm minimum below top of the crosshead / abutment. Where required, any reinforcement shall be adjusted to suit the depth of the pedestal and nominated cover. Concrete substrate surface saturated with water for several hours in accordance with the selected product TDS prior to pouring product. | IFC Drawings Product TDS 610.20 BTN 024 Note 4 | Measure Visual | This ITP | IP | SE/PE/SPE
4 | Construction Activities
4.1 | Formwork Construction & Placement | Each element | Dimensions in plan as per drawings to achieve the desired grout profile. Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks. Where applicable, any cast in componentry (ferrules, conduit etc.) secure. | IFC Drawings | Measure Visual | This ITP | IP | SE/PE/SPE
4.2 | Pre-pour Inspection | Each element | Concrete substrate surface moisture condition as per the Product's TDS, with no ponding of water. Formwork location and RLs comply. Where applicable, any reinforcement is clean and has the required cover. | IFC Drawings Product TDS 610.20 | Measure Visual | This ITP | IP | SE/PE/SPE
4.3 | Weather Conditions | Each element | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Record: Required information on the Grout Pour Record. | 610.17 610.17 (a) & (e) Table 610.171 | Measure Visual | This ITP | IP | Foreman SE/PE/SPE
4.4 | Mixing Product | Each batch | Size of mixer should match the application. Only whole bags to be mixed with potable water. Volume of water matches the required amount for flowable consistency and accurately measured. Product poured into the mixer slowly. Mixing time as per TDS so that a smooth, even consistency is obtained. Enter: Required information on the Grout Pour Record. | Product TDS 610.28 | Measure Visual | This ITP | IP | SE/PE/SPE
4.5 | Product Testing - Compressive Strength Cubes | Each element | Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products. Testing is be in accordance with the following frequencies: First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Enter: Required information on the Grout Pour Record. | 610.28 610.33 | Test | This ITP | IP | Tester Sub-contractor SE/PE/SPE
4.6 | Placement & Compaction | Each element | All batches are traceable. Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water. Product should flow to all areas and self consolidate. Product that stiffens or is showing signs of stiffening shall not be used. Enter: Required information on the Grout Pour Record | Product TDS | Visual | This ITP | IP | Foreman SE/PE/SPE
4.7 | Surface Finishes | Each element | Surface to match the IFC drawings. Where not shown: Pedestals: Surface to be finished flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper. Bearings, base-plates and pockets: Surface to match the the surrounding surfaces using a smooth trowel finish where exposed. | 610.28 | Visual | This ITP | IP | Foreman SE/PE/SPE
4.8 | Curing | Each element | Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS. | Curing Methodology 610.23 Table 610.231 | Visual | This ITP | IP | Foreman SE/PE/SPE
5 | Post-construction Activities
5.1 | Compressive Strength Test Results | Each cube | 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly. 28 day compressive strength per sample comply with the design strength. Attach: Compressive Strength Test Results | IFC Drawings Product TDS 610.28 610.33 | Document Review | This ITP | TP | SE/PE/SPE
5.2 | As-built Survey | Each element | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below: Reduced level ±2.5mm Variation from grade across the width of individual pedestals shall not exceed 1 in 200 Deviation from flat surface ±1mm Attach: Survey As-builts / Survey Report | IFC Drawings 610.47 (a) Table 610.472 | Document Review | This ITP | SCP | Surveyor PE/SE/SPE
5.3 | Non-conformance Report (NCR) Closure | Once, prior to closure of this lot / element / Work area | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | FH Quality Management Plan | Document Review | This ITP | HP* | PE/SE/SPE
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: | Position: |  | Signature: |  |  |  |  | Date:
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent