## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-015-AX-LOT-XXX - Desc | itp |  |  |  |  | ITP 0015 - Structural Grout (Pedestals, Bearings, Base-plates & Pockets)
section | 1 - Preliminaries - Materials
checkpoint | 1.1 - Product Selection
label | Frequency: Once, for each product, prior to placement of product
label | - - - - - - - - -
label | Acceptance Criteria: Product to be selected based on the following criteria:
label | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
label | ii. have the required strength at 28 days as noted on the IFC drawings.
label | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
label | Note: Pedestals 200mm or greater shall be constructed from concrete - use the Structural Concrete ITP instead
textbox | Enter: Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 610.28, 610.33
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Responsibility: Superintendent
checkpoint | 1.2 - Curing Compound
label | Frequency: Once, for each product, prior to placement of product
label | - - - - - - - - -
label | Acceptance Criteria: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | Note: This may be the same product used for the concrete curing
textbox | Enter: Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents: 610.23 (d)
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Responsibility: Superintendent
section | 2 - Preliminaries - Procedures & Documentation
checkpoint | 2.1 - Curing Methodology (for Concrete, Grout and Mortar)
label | Frequency: Once, 4 weeks prior to placement of product
label | - - - - - - - - -
label | Acceptance Criteria: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | Note: This may be the same document used for the concrete curing.
textbox | Enter: Teambinder Correspondence Approval number
label | - - - - - - - - -
label | Reference Documents: 610.23 (a)
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Superintendent
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Pre-construction Activities
checkpoint | 3.1 - IFC Drawings
label | Frequency: Prior to starting Works and at regular intervals
label | - - - - - - - - -
label | Acceptance Criteria: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | - - - - - - - - -
label | Reference Documents: FH Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: All
checkpoint | 3.2 - Survey Set-out
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.472 as applicable to the element.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 610.47 (a) Table 610.472
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Responsibility: Surveyor, SE/PE/SPE
checkpoint | 3.3 - Construction Joint
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Where required, the concrete substrate is to be roughened / scabbled in accordance with the drawings and or Product TDS.
label | ○ Pedestals shall be rebated to 20mm minimum below top of the crosshead / abutment.
label | ○ Where required, any reinforcement shall be adjusted to suit the depth of the pedestal and nominated cover.
label | ○ Concrete substrate surface saturated with water for several hours in accordance with the selected product TDS prior to pouring product.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings, Product TDS 610.20 BTN 024 Note 4
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
section | 4 - Construction Activities
checkpoint | 4.1 - Formwork Construction & Placement
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Dimensions in plan as per drawings to achieve the desired grout profile.
label | ○ Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | ○ Where applicable, any cast in componentry (ferrules, conduit etc.) secure.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.2 - Pre-pour Inspection
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Concrete substrate surface moisture condition as per the Product's TDS, with no ponding of water.
label | ○ Formwork location and RLs comply.
label | ○ Where applicable, any reinforcement is clean and has the required cover.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings, Product TDS 610.20
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.3 - Weather Conditions
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | Record: Required information on the Grout Pour Record.
label | - - - - - - - - -
label | Reference Documents: 610.17, 610.17 (a) & (e) Table 610.171
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Foreman, SE/PE/SPE
checkpoint | 4.4 - Mixing Product
label | Frequency: Each batch
label | - - - - - - - - -
label | Acceptance Criteria: Size of mixer should match the application.
label | ○ Only whole bags to be mixed with potable water.
label | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | ○ Product poured into the mixer slowly.
label | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
label | Enter: Required information on the Grout Pour Record.
label | - - - - - - - - -
label | Reference Documents: Product TDS 610.28
label | - - - - - - - - -
label | Inspection / Test Method: Measure, Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 4.5 - Product Testing - Compressive Strength Cubes
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | ○ Testing is be in accordance with the following frequencies:
label | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | Enter: Required information on the Grout Pour Record.
label | - - - - - - - - -
label | Reference Documents: 610.28, 610.33
label | - - - - - - - - -
label | Inspection / Test Method: Test
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Tester, Sub-contractor, SE/PE/SPE
checkpoint | 4.6 - Placement & Compaction
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: All batches are traceable.
label | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | ○ Product should flow to all areas and self consolidate.
label | ○ Product that stiffens or is showing signs of stiffening shall not be used.
label | Enter: Required information on the Grout Pour Record
label | - - - - - - - - -
label | Reference Documents: Product TDS
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Foreman, SE/PE/SPE
checkpoint | 4.7 - Surface Finishes
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Surface to match the IFC drawings.
label | Where not shown:
label | Pedestals:
label | ○ Surface to be finished flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
label | Bearings, base-plates and pockets:
label | ○ Surface to match the the surrounding surfaces using a smooth trowel finish where exposed.
label | - - - - - - - - -
label | Reference Documents: 610.28
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Foreman, SE/PE/SPE
checkpoint | 4.8 - Curing
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | - - - - - - - - -
label | Reference Documents: Curing Methodology 610.23 Table 610.231
label | - - - - - - - - -
label | Inspection / Test Method: Visual
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Foreman, SE/PE/SPE
section | 5 - Post-construction Activities
checkpoint | 5.1 - Compressive Strength Test Results
label | Frequency: Each cube
label | - - - - - - - - -
label | Acceptance Criteria: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength per sample comply with the design strength.
label | Attach: Compressive Strength Test Results
label | - - - - - - - - -
label | Reference Documents: IFC Drawings, Product TDS 610.28, 610.33
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: SE/PE/SPE
checkpoint | 5.2 - As-built Survey
label | Frequency: Each element
label | - - - - - - - - -
label | Acceptance Criteria: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
label | ○ Reduced level ±2.5mm
label | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | ○ Deviation from flat surface ±1mm
label | Attach: Survey As-builts / Survey Report
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 610.47 (a) Table 610.472
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Responsibility: Surveyor, PE/SE/SPE
checkpoint | 5.3 - Non-conformance Report (NCR) Closure
label | Frequency: Once, prior to closure of this lot / element / Work area
label | - - - - - - - - -
label | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | - - - - - - - - -
label | Reference Documents: FH Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of Conformity: This ITP
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: PE/SE/SPE
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
date | Work Completed On