## Sheet1
| WORK AREA: | DESCRIPTION OF ACTIVITY: Sorrento Street Stormwater Renewal |  | Key: P= PERFORM (Activity) R = REVIEW (Documents & Work) W = WITNESS (Activity) H = HOLD (Point for Acceptance) | Rev | Originator |  | Date | Approved |  | Date
[5 empty] | 0 | Michael Polglase |  | 2024-05-09
| Sorrento Street, Onerahi, Whangarei |  |  |  | 1 | Michael Polglase |  | 2024-05-20 | Vanessa Martinovich |  | 2024-05-21
Earthworks and Stabilization
Item No. | ITEM | ACTIVITY TASK | ACCEPTANCE CRITERIA | CERTIFING DOCUMENTATION AND FREQUENCY |  | Supervisor, Foreman or Subcontractor |  | Project Manager or Delegated Person |  | Principal’s Representative
[6 empty] | Key | Sign / Date | Key | Sign / Date | Key
1.1 | Outlet Slope Stabilization | Material Supply | Enkamat Geofabric (or similar Engineer approved geofabric) | Delivery dockets |  | W |  | P |  | W
1.2 |  | Material Supply | D50-250mm Rock Riprap | Delivery dockets |  | W |  | P |  | W
1.3 |  | Construction | Install as per Drawing No. 3121577-CA-1011 | Visual inspection/photos |  | P |  | W |  | W
2.1 | Surface Reinstatement | Topsoiling | 100mm of clean topsoil | Visual inspection |  | P |  | W |  | W
2.2 |  | Grass Seeding | Over 70% of seed to growth | Visual inspection |  | P |  | W |  | W
Roading
Item No. | ITEM | ACTIVITY TASK | ACCEPTANCE CRITERIA | CERTIFING DOCUMENTATION AND FREQUENCY |  | Supervisor, Foreman or Subcontractor |  | Project Manager or Delegated Person |  | Principal’s Representative
[6 empty] | Key | Sign / Date | Key | Sign / Date | Key
1.1 | Vested Road Subgrade | Subgrade Strength | Subgrade shall be prepared and conditioned as specified in Specification CO209.4 | Visual inspection as excavated |  | P |  | W |  | H
2.1 | Vested Road Sub-base | Material Supply | Shall be constructed of GAP65 | Delivery dockets |  | W |  | P |  | W
2.2 |  | Construction | Shall be compacted in 200mm layers as per WDC EES Sheet 31 | Visual inspection |  | P |  | W |  | W
2.3 |  | Compaction | Clegg hammer test: 0-300mm from surface CIV reading not less than 45; 300mm-1.5m from road surface CIV reading not less than 30; >1.5m from road surface CIVnot less than 25. | QF 022 – Clegg Hammer Test Report. One test every linear 20m of every layer. |  | W |  | P |  | H
3.1 | Vested Road Basecourse | Material Supply | Shall be constructed of lime-stabilized AP40 | Delivery dockets |  | W |  | P |  | W
3.2 |  | Construction | Shall be 300mm thick as per WDC EES Sheet 31 | Visual inspection |  | P |  | W |  | W
3.3 |  | Construction | Shall be constructed in 150mm layers as per WDC EES Sheet 21 | Visual inspection |  | P |  | W |  | W
3.4 |  | Compaction | Clegg hammer test: No reading less than 45 | QF 022 – Clegg Hammer Test Report. One test every linear 20m. |  | W |  | P |  | H
4.1 | Surfacing | Temporary Surfacing | Not less than 30mm thick cold mix asphalt | Visual inspection/photos. Upon reinstatement of road |  | P |  | P |  | W
Stormwater Reticulation
Item No. | ITEM | ACTIVITY TASK | ACCEPTANCE CRITERIA | CERTIFING DOCUMENTATION AND FREQUENCY |  | Supervisor, Foreman or Subcontractor |  | Project Manager or Delegated Person |  | Principal’s Representative
[6 empty] | Key | Sign / Date | Key | Sign / Date | Key
1.1 | Manholes | Material Supply | To be as specified on Drawing No. 3121577-CA-1011 to Drawing No. 3121577-CA-1020 | Delivery dockets |  | W |  | P |  | W
1.2 |  | Location | Survey setout at correct locations as per the Drawings | Visual inspection |  | P |  | W |  | W
1.3 |  | Invert Levels | To be as specified on Drawing No. 3121577-CA-1020 | Visual inspection |  | P |  | W |  | W
1.4 |  | Visual Check Materials Quality and Condition | Material quality in accordance with WDC EES Sheet 37 | QF 036 – Inspection Checklist Manhole Construction. Post construction |  | W |  | P |  | W
1.5 |  | Visual Check Inlets/outlets | To be satisfactorily constructed and free from scour and siltation | Visual inspection/photos |  | P |  | P |  | W
1.6 |  | Concrete Work | In accordance with WDC EES Sheet 37 | Visual inspection/photos |  | P |  | P |  | W
2.1 | Cesspits | Material Supply | To be as specified on Drawing No. 3121577-CA-1011 to Drawing No. 3121577-CA-1020 | Delivery Dockets |  | W |  | P |  | W
2.2 |  | Location | Survey setout at correct locations as per the Drawings | Visual inspection |  | P |  | W |  | W
2.3 |  | Concrete Work | In accordance with WDC EES Sheet 37 | Visual inspection/photos |  | P |  | P |  | W
3.1 | Pipelines | Material Supply | To be as specified on Drawing No. 3121577-CA-1011 to Drawing No. 3121577-CA-1020 | Delivery dockets |  | W |  | P |  | W
3.2 |  | Location | Survey setout at correct locations as per the Drawings | Visual inspection |  | P |  | W |  | W
3.3 |  | Visual Check Materials Quality and Condition | Material quality in accordance with WDC EES Sheet 37 | QF 008 – Inspection Checklist Pipelines. As constructed |  | W |  | P |  | W
3.4 |  | Trenches and Bedding | In accordance with WDC EES Sheet 31 | QF 008 – Inspection Checklist Pipelines. As constructed |  | P |  | W |  | H
3.5 |  | Testing-CCTV Footage | CCTV footage to be reported to council | CCTV footage of pipeline. Post construction |  | W |  | P |  | W
4.1 | Connection to WDC Network | Connection to WDC Network | In accordance with WDC EES - undertaken by Licensed Contractor for Stormwater connections | Visual inspection/photos |  | P |  | P |  | H
Other
Item No. | ITEM | ACTIVITY TASK | ACCEPTANCE CRITERIA | CERTIFING DOCUMENTATION AND FREQUENCY |  | Supervisor, Foreman or Subcontractor |  | Project Manager or Delegated Person |  | Principal’s Representative
[6 empty] | Key | Sign / Date | Key | Sign / Date | Key
1.1 | Final Completion Inspection | Final Completion Inspection | Satisfy Engineer | Visual inspection post construction |  | W |  | P |  | H
2.1 | As-built and Asset Register | As-built Infrastructure | Invert levels to be no more than +30mm than design where grade is >1%, and no more than +3mm where grade is <1% | As-built documentation post construction |  | W |  | P |  | H
2.2 |  | Asset Register | Asset register completed for installed infrastructure | Post-construction |  | W |  | P |  | H
3.1 | Post-completion Certificate | Post-completion Certificate | Post-completion Certificate | Post-construction |  | W |  | P |  | H