## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP001 - Pavement Rehabilitation | itp |  |  |  | Yes | ITP001 - Pavement Rehabilitation | a90ada8e-caa2-4c6a-84d4-9c5330374029
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | 1 - Survey
label | ad10021d-cef8-5eb3-b119-853a193f2985 |  | note | ACTIVITY TASK - Verify latest drawings
label | b0b8b1ff-07d1-5072-8b40-0f07bad85b69 |  | note | ACCEPTANCE CRITERIA - Latest Revision of IFC
label | ce1f339c-04b5-55ff-925d-edd1e3e40d5f |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - Drawing Register
label | 2d60be15-e389-5d6c-a884-316afa413fb0 |  | note | Supervisor, Foreman or Subcontractor - R
label | ec124df2-0fea-5f83-b606-a9e0f06d4bff |  | note | Project Manager or Delegated Person - R
checkpoint-status |  |  | checkpoint | 2 -
label | f754c8a3-dbe3-544d-a78a-cb9e7085e506 |  | note | ACTIVITY TASK - Set out
label | 91e14914-67c8-55a0-9efc-6e14bd960eda |  | note | ACCEPTANCE CRITERIA - Review and Inspection
label | 9599f872-7763-5651-8705-9c05815ebab3 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - Initial, as per engineers’ request
label | 964f6ee8-12ac-52c8-a1fa-eaea9bc04590 |  | note | Supervisor, Foreman or Subcontractor - R
label | c5962d1c-c881-5799-a5f4-a48cfe1527c3 |  | note | Project Manager or Delegated Person - W
label | cf63c9d7-2019-5e2f-9c0b-aeb440bbd353 |  | note | Engineer’s Representative - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 -
label | 39b9bbc7-963e-574e-886d-70a41fccae30 |  | note | ACTIVITY TASK - Trenching/ Potholes
label | bf66097f-ebeb-55b0-868b-9f286648ac93 |  | note | ACCEPTANCE CRITERIA - Location, alignment and level check for existing services
label | e36bba68-9cd0-59e8-bd16-9e0ec4fa044b |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - Checklist
label | efb34c76-e068-5571-be42-c4a59238bc16 |  | note | Supervisor, Foreman or Subcontractor - W
label | 5f94a2d1-009a-5b89-a01b-556f1c4a81e9 |  | note | Project Manager or Delegated Person - R
checkpoint-status |  |  | checkpoint | 4 - Construction – Subsoil Drain
label | e0c31777-ce2e-5ed5-a4f0-327b66e2b031 |  | note | ACTIVITY TASK - Pipe Materials
label | e17da783-18d4-5dfd-89b6-76363ac11049 |  | note | ACCEPTANCE CRITERIA - 100mm dia slotted PVC or Polyethylene subsoil drain pipe
label | 999a485c-2868-592a-8c8e-2d5b4d35e23f |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - Supplier documentation, KDC Engineering Standards
label | 2cadbf0b-bfca-50df-b2d0-2ea0e96b50f8 |  | note | Supervisor, Foreman or Subcontractor - R
label | cedb879a-ae7e-5bb3-824a-502cc148e5d8 |  | note | Project Manager or Delegated Person - R
label | e12be139-5e6a-54b4-ba73-5b13f5dc52ee |  | note | Engineer’s Representative - R
checkpoint-status |  |  | checkpoint | 5 -
label | 86863b86-ce2e-539e-9f6a-02d15e6a8b62 |  | note | ACTIVITY TASK - Drainage materials
label | 7cbac6f1-2f11-50d2-9e92-565c76ea5c3f |  | note | ACCEPTANCE CRITERIA - 20/7 “Pages” metal
label | c65f2638-0075-5348-9398-4ae843f78f8f |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - Supplier documentation, KDC Engineering Standards
label | e7588c29-5391-50ff-b5da-9a4607be6e50 |  | note | Supervisor, Foreman or Subcontractor - R
label | 8c9d743e-8a9a-523f-abb6-0f705605ace6 |  | note | Project Manager or Delegated Person - R
label | 3ae2d96c-24c2-540e-a137-427460e10720 |  | note | Engineer’s Representative - R
checkpoint-status |  |  | checkpoint | 6 - Construction – Dished Channel
label | 63a1ba05-fb67-577c-b532-ae9b3bc137a4 |  | note | ACTIVITY TASK - Concrete Strength
label | fb81cbc6-5c44-52ac-a36a-57fae9c6b8f8 |  | note | ACCEPTANCE CRITERIA - 30MPa at 28 days
label | 5261b07d-4baa-55ab-9ade-ed65c75422f8 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - Supplier documentation, KDC Engineering Standards
label | 1b3eb9d7-f26d-51d8-a621-0535689b36b7 |  | note | Supervisor, Foreman or Subcontractor - R
label | 3869fca2-b1e4-55c0-b2d0-aeaac6fd33bc |  | note | Project Manager or Delegated Person - R
label | 54f3cfe5-a21c-58b6-aef4-301fc24275ed |  | note | Engineer’s Representative - R
checkpoint-status |  |  | checkpoint | 7 - Construction – Pavement
label | 4da9de0c-d0c1-5ae0-a12e-1367ad132270 |  | note | ACTIVITY TASK - Stripped Surface
label | 5918d2df-3f1c-5ec5-b6f9-6c70e87c70b6 |  | note | ACCEPTANCE CRITERIA - Visual Inspection
label | 81e5b31e-f441-5ca7-bae5-cbce6031f317 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - At completion of stripping, prior to further construction
label | 4e93d3aa-d3fc-5f24-bf0f-5ea816fe2342 |  | note | Supervisor, Foreman or Subcontractor - P
label | 2adfff14-4f6c-57b8-b649-72192d237353 |  | note | Project Manager or Delegated Person - W
checkpoint-status |  |  | checkpoint | 8 -
label | 0964abff-3c64-5906-80a5-d1d855096040 |  | note | ACTIVITY TASK - Undercutting
label | 6667a03f-8d5a-5c2c-852f-2b99cf0c3c7f |  | note | ACCEPTANCE CRITERIA - Engineer to confirm
label | cef489ab-f81c-548f-85f1-e9e315e9edb1 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - As required
label | 1858b415-4f04-50a3-8792-d6f593eb4ea4 |  | note | Supervisor, Foreman or Subcontractor - H
label | ab632def-5c15-52ce-b7b5-5ea6627d2760 |  | note | Project Manager or Delegated Person - W
label | 4d776d20-01db-507f-8124-3ae7d691d9a3 |  | note | Engineer’s Representative - W
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 -
label | a4a6c6b4-c912-5b9f-9907-be6e66c51a12 |  | note | ACTIVITY TASK - Subgrade
label | 1ac8263c-a157-5f81-80fe-b3eb6ff9f2a3 |  | note | ACCEPTANCE CRITERIA - 1. CBR > 3%
label | 0601002c-3ec3-5f54-8943-b2c7bdd188c7 |  | note | ○ 2. No visible deflections
label | 0eab6373-053e-579a-871b-50cd821bee3c |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - 1. Scala testing at 10m intervals
label | 17f50f41-5c61-5e43-95f8-bc2c3134438e |  | note | ○ 2. Proof rolling with steel drum roller
label | c76dfe7b-513a-51e4-8f60-b9f7771b2410 |  | note | ○ 3. Checklists
label | 3db7730a-3657-565d-a73e-2ce260fe300c |  | note | Supervisor, Foreman or Subcontractor - P
label | edfdea4c-cb18-58c1-b03a-2a30b4f696fb |  | note | Project Manager or Delegated Person - R
label | 7e5dfc9d-4c9d-50bf-af3e-113bb31463c0 |  | note | Engineer’s Representative - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 -
label | 2b41ab71-617e-5903-9c06-cf15b1ac9bc3 |  | note | ACTIVITY TASK - Sub-basecourse
label | fedb5143-9fd5-554b-b3bb-c635b6314b55 |  | note | ACCEPTANCE CRITERIA - 1. Mean 95% MDD, Min 92% MDD
label | 07d52326-6cb4-554e-9494-438e8bf69470 |  | note | ○ 2. -15mm below 3m straight edge
label | 9f271209-d1df-5caf-b179-140c19a3b66a |  | note | ○ 3. +10mm from design
label | f78f5e55-a842-548c-a2b8-19c1bc5fc0f3 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - 1. Nuclear density as per Waka Kotahi’s Specification B/2 and KDC Engineering Standards 2011 Part 5
label | 94920378-f7af-5952-ac32-b7aa2cd8c2d4 |  | note | ○ 2. Surface Finish – Straight edge
label | 904ee56a-5e57-5d57-b0c2-db1629047b6b |  | note | ○ 3. Level/thickness
label | 994ffecd-8153-5917-9269-c46d6616ccc1 |  | note | ○ 4. Checklist / As-builts
label | 0953058a-5750-5527-8740-517f19f559b9 |  | note | Supervisor, Foreman or Subcontractor - P
label | dc0a8191-4453-57f9-8462-93a6eaf95c6d |  | note | Project Manager or Delegated Person - R
label | d309ff19-88aa-5b39-acc3-2456d0a174c4 |  | note | Engineer’s Representative - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 -
label | 5dff74f8-a82d-5229-82bd-29bca2e516d7 |  | note | ACTIVITY TASK - Basecourse
label | c2084a76-e33a-57e9-898c-e8db48a221eb |  | note | ACCEPTANCE CRITERIA - 1. Mean 98% MDD, Min 95% MDD
label | 4678b274-875e-5095-b275-734f1c11a6ce |  | note | ○ 2. -10mm below 3m straight edge
label | 3148e289-fd31-5ef3-a83c-aa6afc523ca2 |  | note | ○ 3. +5mm;-5mm from design
label | f19d2e50-d685-5cd2-8d51-12a0db12ec64 |  | note | ○ 4. 1.4mm(90%) 1.8mm(max)
label | 8457cd96-868e-5314-8b16-b42df4c27f41 |  | note | ○ 5. Material Approval as per TNZ M/4: 2006
label | 8f8cf5f5-9d8b-51fe-a9ee-0d9ca5aeb299 |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - 1. Nuclear density as per Waka Kotahi’s Specification B/2 and KDC Engineering Standards 2011 Part 5
label | 2608cc8f-ce4b-5fba-8047-7dd729bfe64c |  | note | ○ 2. Surface Finish – Straight edge
label | 647a82f8-3fa8-5f2c-b5a5-224bd64b732b |  | note | ○ 3. Level/thickness
label | 6658415e-6a72-5c37-817e-d2a0a461c09b |  | note | ○ 4. Benkelman Beam Testing – Deflection prior to sealing
label | e7e9f770-179d-5b97-8399-9f7171c1b2ab |  | note | ○ 5. Supplier documentation
label | 189fdfe7-374f-527d-9ad7-a3f355d20bab |  | note | ○ 6. As per technical specification section C0210 and Engineers approval
label | bb8259df-043c-528a-bd3b-bc6c1064220a |  | note | Supervisor, Foreman or Subcontractor - P
label | 2853438d-fd20-5cad-92a4-21434fa1f2c9 |  | note | Project Manager or Delegated Person - R
label | 43c2a180-b62f-5925-9111-7411a134e850 |  | note | Engineer’s Representative - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 -
label | 6d21febe-d67c-50f9-ba26-6b48248fd663 |  | note | ACTIVITY TASK - Chip-seal
label | 62d8f314-68e8-522c-a423-f38944c5deea |  | note | ACCEPTANCE CRITERIA - 1. Check tight stone Mosaic surface
label | c8a2f116-4a6b-55ee-bb71-f56076f5c4e8 |  | note | ○ 2. Aggregate – PSV54-56
label | f0ada437-09b9-502b-8c32-5a6ae7cd30e4 |  | note | ○ 3. Sealing QA
label | 7105b295-75d0-5702-a532-650f8c9c2042 |  | note | ○ 4. Approval of materials before use
label | 99999b9d-4d32-545f-bb8f-5e3fdee1bc8a |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - 1. Visual Inspection
label | 32bf0fb2-176b-5b30-900f-ce02a0023a78 |  | note | ○ 2. Test data sheet
label | d173fa9e-77d8-5ae0-9ab7-735485eccfd2 |  | note | ○ 3. Technical specification section C0213
label | 30a8a8b3-ea42-54df-a3d2-8b5f6096e05d |  | note | ○ 4. Mix design as per technical specification section C0213 and Engineers approval
label | 371f1107-1c97-59cb-be1f-a13114a65660 |  | note | Supervisor, Foreman or Subcontractor - P
label | f9ef6ca6-c0ae-5a86-8da5-c5197bce1970 |  | note | Project Manager or Delegated Person - R
label | 70ea8b70-daa0-5703-bb0e-8691e3339b5b |  | note | Engineer’s Representative - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 -
label | 1006071f-cb53-5139-ade7-fd34d0548bc2 |  | note | ACTIVITY TASK - Line Marking
label | 07809068-9aaa-5b90-bb29-b5c294ef2189 |  | note | ACCEPTANCE CRITERIA - 1. Visual Inspection
label | 5bc5ca41-9049-5874-b495-1ebc4b8a0f5f |  | note | CERTIFING DOCUMENTATION AND FREQUENCY - 1. TNZ Manual of Traffic Signs and Markings
label | 54fba7aa-c1b8-5a90-99b4-2f614526c817 |  | note | Supervisor, Foreman or Subcontractor - P
label | f971dfaa-f9e8-5cb8-b369-b1e4f16510b9 |  | note | Project Manager or Delegated Person - R
label | 98feb73c-92da-5570-beca-6a187cae1db2 |  | note | Engineer’s Representative - R
checkpoint-status |  |  | checkpoint | 14 - As -Builts
label | 3782996a-6962-58d8-b4ec-0d99b0dee6fc |  | note | ACTIVITY TASK - As-builts
label | 38432957-8318-5e26-be0b-8b9771d18cc3 |  | note | ACCEPTANCE CRITERIA - A complete set of as-builts shall be provided on the completion of the project. This will include but not limited to
label | de07b1b5-8fdc-584f-a241-e77f78b35e8b |  | note | ○ 1. Pavement levels
label | 65d5c60e-5eec-5361-a44f-7f8ca38ed293 |  | note | ○ 2. Subsoil drains, dished channel, flushing eyes
label | 64abf517-1233-542c-ae67-8fc7c833e11a |  | note | Supervisor, Foreman or Subcontractor - P
label | 358de67a-8223-5371-8f42-6a64b14bcb30 |  | note | Engineer’s Representative - R