## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 240514 V2 CON24003 Sorrento Street Stormwater Renewal ITP 7036 | itp |  |  |  |  | 240514 V2 CON24003 Sorrento Street Stormwater Renewal ITP 7036
section | Earthworks and Stabilization
checkpoint | 1.1 - Outlet Slope Stabilization
label | ACTIVITY TASK - Material Supply
label | ACCEPTANCE CRITERIA - Enkamat Geofabric (or similar Engineer approved geofabric)
label | CERTIFING DOCUMENTATION AND FREQUENCY - Delivery dockets
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 1.2 -
label | ACTIVITY TASK - Material Supply
label | ACCEPTANCE CRITERIA - D50-250mm Rock Riprap
label | CERTIFING DOCUMENTATION AND FREQUENCY - Delivery dockets
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 1.3 -
label | ACTIVITY TASK - Construction
label | ACCEPTANCE CRITERIA - Install as per Drawing No. 3121577-CA-1011
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection/photos
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
checkpoint | 2.1 - Surface Reinstatement
label | ACTIVITY TASK - Topsoiling
label | ACCEPTANCE CRITERIA - 100mm of clean topsoil
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
checkpoint | 2.2 -
label | ACTIVITY TASK - Grass Seeding
label | ACCEPTANCE CRITERIA - Over 70% of seed to growth
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
section | Roading
checkpoint | 1.1 - Vested Road Subgrade
label | ACTIVITY TASK - Subgrade Strength
label | ACCEPTANCE CRITERIA - Subgrade shall be prepared and conditioned as specified in Specification CO209.4
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection as excavated
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Vested Road Sub-base
label | ACTIVITY TASK - Material Supply
label | ACCEPTANCE CRITERIA - Shall be constructed of GAP65
label | CERTIFING DOCUMENTATION AND FREQUENCY - Delivery dockets
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 2.2 -
label | ACTIVITY TASK - Construction
label | ACCEPTANCE CRITERIA - Shall be compacted in 200mm layers as per WDC EES Sheet 31
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
checkpoint | 2.3 -
label | ACTIVITY TASK - Compaction
label | ACCEPTANCE CRITERIA - Clegg hammer test: 0-300mm from surface CIV reading not less than 45; 300mm-1.5m from road surface CIV reading not less than 30; >1.5m from road surface CIVnot less than 25.
label | CERTIFING DOCUMENTATION AND FREQUENCY - QF 022 – Clegg Hammer Test Report. One test every linear 20m of every layer.
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Vested Road Basecourse
label | ACTIVITY TASK - Material Supply
label | ACCEPTANCE CRITERIA - Shall be constructed of lime-stabilized AP40
label | CERTIFING DOCUMENTATION AND FREQUENCY - Delivery dockets
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 3.2 -
label | ACTIVITY TASK - Construction
label | ACCEPTANCE CRITERIA - Shall be 300mm thick as per WDC EES Sheet 31
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
checkpoint | 3.3 -
label | ACTIVITY TASK - Construction
label | ACCEPTANCE CRITERIA - Shall be constructed in 150mm layers as per WDC EES Sheet 21
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
checkpoint | 3.4 -
label | ACTIVITY TASK - Compaction
label | ACCEPTANCE CRITERIA - Clegg hammer test: No reading less than 45
label | CERTIFING DOCUMENTATION AND FREQUENCY - QF 022 – Clegg Hammer Test Report. One test every linear 20m.
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1 - Surfacing
label | ACTIVITY TASK - Temporary Surfacing
label | ACCEPTANCE CRITERIA - Not less than 30mm thick cold mix asphalt
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection/photos. Upon reinstatement of road
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
section | Stormwater Reticulation
checkpoint | 1.1 - Manholes
label | ACTIVITY TASK - Material Supply
label | ACCEPTANCE CRITERIA - To be as specified on Drawing No. 3121577-CA-1011 to Drawing No. 3121577-CA-1020
label | CERTIFING DOCUMENTATION AND FREQUENCY - Delivery dockets
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 1.2 -
label | ACTIVITY TASK - Location
label | ACCEPTANCE CRITERIA - Survey setout at correct locations as per the Drawings
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
checkpoint | 1.3 -
label | ACTIVITY TASK - Invert Levels
label | ACCEPTANCE CRITERIA - To be as specified on Drawing No. 3121577-CA-1020
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
checkpoint | 1.4 -
label | ACTIVITY TASK - Visual Check Materials Quality and Condition
label | ACCEPTANCE CRITERIA - Material quality in accordance with WDC EES Sheet 37
label | CERTIFING DOCUMENTATION AND FREQUENCY - QF 036 – Inspection Checklist Manhole Construction. Post construction
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 1.5 -
label | ACTIVITY TASK - Visual Check Inlets/outlets
label | ACCEPTANCE CRITERIA - To be satisfactorily constructed and free from scour and siltation
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection/photos
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 1.6 -
label | ACTIVITY TASK - Concrete Work
label | ACCEPTANCE CRITERIA - In accordance with WDC EES Sheet 37
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection/photos
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 2.1 - Cesspits
label | ACTIVITY TASK - Material Supply
label | ACCEPTANCE CRITERIA - To be as specified on Drawing No. 3121577-CA-1011 to Drawing No. 3121577-CA-1020
label | CERTIFING DOCUMENTATION AND FREQUENCY - Delivery Dockets
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 2.2 -
label | ACTIVITY TASK - Location
label | ACCEPTANCE CRITERIA - Survey setout at correct locations as per the Drawings
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
checkpoint | 2.3 -
label | ACTIVITY TASK - Concrete Work
label | ACCEPTANCE CRITERIA - In accordance with WDC EES Sheet 37
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection/photos
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 3.1 - Pipelines
label | ACTIVITY TASK - Material Supply
label | ACCEPTANCE CRITERIA - To be as specified on Drawing No. 3121577-CA-1011 to Drawing No. 3121577-CA-1020
label | CERTIFING DOCUMENTATION AND FREQUENCY - Delivery dockets
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 3.2 -
label | ACTIVITY TASK - Location
label | ACCEPTANCE CRITERIA - Survey setout at correct locations as per the Drawings
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - W
checkpoint | 3.3 -
label | ACTIVITY TASK - Visual Check Materials Quality and Condition
label | ACCEPTANCE CRITERIA - Material quality in accordance with WDC EES Sheet 37
label | CERTIFING DOCUMENTATION AND FREQUENCY - QF 008 – Inspection Checklist Pipelines. As constructed
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 3.4 -
label | ACTIVITY TASK - Trenches and Bedding
label | ACCEPTANCE CRITERIA - In accordance with WDC EES Sheet 31
label | CERTIFING DOCUMENTATION AND FREQUENCY - QF 008 – Inspection Checklist Pipelines. As constructed
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - W
label | Principal’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 -
label | ACTIVITY TASK - Testing-CCTV Footage
label | ACCEPTANCE CRITERIA - CCTV footage to be reported to council
label | CERTIFING DOCUMENTATION AND FREQUENCY - CCTV footage of pipeline. Post construction
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - W
checkpoint | 4.1 - Connection to WDC Network
label | ACTIVITY TASK - Connection to WDC Network
label | ACCEPTANCE CRITERIA - In accordance with WDC EES - undertaken by Licensed Contractor for Stormwater connections
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection/photos
label | Supervisor, Foreman or Subcontractor - P
label | Project Manager or Delegated Person - P
label | Principal’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
section | Other
checkpoint | 1.1 - Final Completion Inspection
label | ACTIVITY TASK - Final Completion Inspection
label | ACCEPTANCE CRITERIA - Satisfy Engineer
label | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection post construction
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - As-built and Asset Register
label | ACTIVITY TASK - As-built Infrastructure
label | ACCEPTANCE CRITERIA - Invert levels to be no more than +30mm than design where grade is >1%, and no more than +3mm where grade is <1%
label | CERTIFING DOCUMENTATION AND FREQUENCY - As-built documentation post construction
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 -
label | ACTIVITY TASK - Asset Register
label | ACCEPTANCE CRITERIA - Asset register completed for installed infrastructure
label | CERTIFING DOCUMENTATION AND FREQUENCY - Post-construction
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Post-completion Certificate
label | ACTIVITY TASK - Post-completion Certificate
label | ACCEPTANCE CRITERIA - Post-completion Certificate
label | CERTIFING DOCUMENTATION AND FREQUENCY - Post-construction
label | Supervisor, Foreman or Subcontractor - W
label | Project Manager or Delegated Person - P
label | Principal’s Representative - H
holdpoint | AUTHORITY HOLDPOINT