## Sheet1
1. Precast concrete drainage pipes | R11.2.1, R11.2.6 | · The manufacturer must implement and maintain a Quality Management System in accordance with AS/NZS ISO 9001 as a means of ensuring that the manufactured precast concrete pipes conform to the requirements of the Specification. · Precast reinforced concrete pipes must comply with AS 4058 and the requirements in R11.2.1 (I to 11) | Submit Certificate of conformity at least 7-day prior works commencement to PV | HP | Project Engineer (PE)/PV | 1. Precast concrete drainage pipes | Reference documents - R11.2.1, R11.2.6 | Criteria/Test Method/Spec - · The manufacturer must implement and maintain a Quality Management System in accordance with AS/NZS ISO 9001 as a means of ensuring that the manufactured precast concrete pipes conform to the requirements of the Specification. · Precast reinforced concrete pipes must comply with AS 4058 and the requirements in R11.2.1 (I to 11) | Record for conformity/Inspected by - Submit Certificate of conformity at least 7-day prior works commencement to PV | Type of Record - HP | Responsible Position - Project Engineer (PE)/PV | 1. Precast concrete drainage pipes
2. Design of “Other Drainage Products | R11.2.4.1, R11.4.7 | · The design must be in accordance with the Standards shown in Table R11.1 for the structure or component · Design and development must also comply with TfNSW Q. · Supply of precast concrete members subject to traffic and/or earth pressure loading, and water retaining structures with capacity greater than 25,000 litres. · For all pits, such as junction box, gully pit, drop structure, etc, which are deeper than 600 mm, install an individual-rung ladder (step irons) in accordance with AS 1657 on one internal wall for the full depth of the structure. | At least 7 days prior to the date of delivery, submit the documents specified in Clause 2.4.1 to the PV. | HP | PV/PE | [6 empty] | Reference documents - R11.2.1, R11.2.6
Criteria/Test Method/Spec - · The manufacturer must implement and maintain a Quality Management System in accordance with AS/NZS ISO 9001 as a means of ensuring that the manufactured precast concrete pipes conform to the requirements of the Specification. · Precast reinforced concrete pipes must comply with AS 4058 and the requirements in R11.2.1 (I to 11)
Record for conformity/Inspected by - Submit Certificate of conformity at least 7-day prior works commencement to PV
Type of Record - HP
Responsible Position - Project Engineer (PE)/PV