## Sheet1
1.1 | Outlet Slope Stabilization | Material Supply | Enkamat Geofabric (or similar Engineer approved geofabric) | Delivery dockets | W | P | W | [7 empty] | 1.1 - Final Completion Inspection
1.2 |  | Material Supply | D50-250mm Rock Riprap | Delivery dockets | W | P | W | [7 empty] | ACTIVITY TASK - Final Completion Inspection
1.3 |  | Construction | Install as per Drawing No. 3121577-CA-1011 | Visual inspection/photos | P | W | W | [7 empty] | ACCEPTANCE CRITERIA - Satisfy Engineer
2.1 | Surface Reinstatement | Topsoiling | 100mm of clean topsoil | Visual inspection | P | W | W | [7 empty] | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection post construction
2.2 |  | Grass Seeding | Over 70% of seed to growth | Visual inspection | P | W | W | [7 empty] | Supervisor, Foreman or Subcontractor - W
Project Manager or Delegated Person - P
1.1 | Vested Road Subgrade | Subgrade Strength | Subgrade shall be prepared and conditioned as specified in Specification CO209.4 | Visual inspection as excavated | P | W | H | [7 empty] | Principal’s Representative - H
2.1 | Vested Road Sub-base | Material Supply | Shall be constructed of GAP65 | Delivery dockets | W | P | W | [7 empty] | 2.1 - As-built and Asset Register
2.2 |  | Construction | Shall be compacted in 200mm layers as per WDC EES Sheet 31 | Visual inspection | P | W | W | [7 empty] | ACTIVITY TASK - As-built Infrastructure
2.3 |  | Compaction | Clegg hammer test: 0-300mm from surface CIV reading not less than 45; 300mm-1.5m from road surface CIV reading not less than 30; >1.5m from road surface CIVnot less than 25. | QF 022 – Clegg Hammer Test Report. One test every linear 20m of every layer. | W | P | H | [7 empty] | ACCEPTANCE CRITERIA - Invert levels to be no more than +30mm than design where grade is CHAR(GREAT)1%, and no more than +3mm where grade is CHAR(LESS)1%
3.1 | Vested Road Basecourse | Material Supply | Shall be constructed of lime-stabilized AP40 | Delivery dockets | W | P | W | [7 empty] | CERTIFING DOCUMENTATION AND FREQUENCY - As-built documentation post construction
3.2 |  | Construction | Shall be 300mm thick as per WDC EES Sheet 31 | Visual inspection | P | W | W | [7 empty] | Supervisor, Foreman or Subcontractor - W
3.3 |  | Construction | Shall be constructed in 150mm layers as per WDC EES Sheet 21 | Visual inspection | P | W | W | [7 empty] | Project Manager or Delegated Person - P
3.4 |  | Compaction | Clegg hammer test: No reading less than 45 | QF 022 – Clegg Hammer Test Report. One test every linear 20m. | W | P | H | [7 empty] | Principal’s Representative - H
4.1 | Surfacing | Temporary Surfacing | Not less than 30mm thick cold mix asphalt | Visual inspection/photos. Upon reinstatement of road | P | P | W | [7 empty] | 2.2 -
ACTIVITY TASK - Asset Register
1.1 | Manholes | Material Supply | To be as specified on Drawing No. 3121577-CA-1011 to Drawing No. 3121577-CA-1020 | Delivery dockets | W | P | W | [7 empty] | ACCEPTANCE CRITERIA - Asset register completed for installed infrastructure
1.2 |  | Location | Survey setout at correct locations as per the Drawings | Visual inspection | P | W | W | [7 empty] | CERTIFING DOCUMENTATION AND FREQUENCY - Post-construction
1.3 |  | Invert Levels | To be as specified on Drawing No. 3121577-CA-1020 | Visual inspection | P | W | W | [7 empty] | Supervisor, Foreman or Subcontractor - W
1.4 |  | Visual Check Materials Quality and Condition | Material quality in accordance with WDC EES Sheet 37 | QF 036 – Inspection Checklist Manhole Construction. Post construction | W | P | W | [7 empty] | Project Manager or Delegated Person - P
1.5 |  | Visual Check Inlets/outlets | To be satisfactorily constructed and free from scour and siltation | Visual inspection/photos | P | P | W | [7 empty] | Principal’s Representative - H
1.6 |  | Concrete Work | In accordance with WDC EES Sheet 37 | Visual inspection/photos | P | P | W | [7 empty] | 3.1 - Post-completion Certificate
2.1 | Cesspits | Material Supply | To be as specified on Drawing No. 3121577-CA-1011 to Drawing No. 3121577-CA-1020 | Delivery Dockets | W | P | W | [7 empty] | ACTIVITY TASK - Post-completion Certificate
2.2 |  | Location | Survey setout at correct locations as per the Drawings | Visual inspection | P | W | W | [7 empty] | ACCEPTANCE CRITERIA - Post-completion Certificate
2.3 |  | Concrete Work | In accordance with WDC EES Sheet 37 | Visual inspection/photos | P | P | W | [7 empty] | CERTIFING DOCUMENTATION AND FREQUENCY - Post-construction
3.1 | Pipelines | Material Supply | To be as specified on Drawing No. 3121577-CA-1011 to Drawing No. 3121577-CA-1020 | Delivery dockets | W | P | W | [7 empty] | Supervisor, Foreman or Subcontractor - W
3.2 |  | Location | Survey setout at correct locations as per the Drawings | Visual inspection | P | W | W | [7 empty] | Project Manager or Delegated Person - P
3.3 |  | Visual Check Materials Quality and Condition | Material quality in accordance with WDC EES Sheet 37 | QF 008 – Inspection Checklist Pipelines. As constructed | W | P | W | [7 empty] | Principal’s Representative - H
3.4 |  | Trenches and Bedding | In accordance with WDC EES Sheet 31 | QF 008 – Inspection Checklist Pipelines. As constructed | P | W | H
3.5 |  | Testing-CCTV Footage | CCTV footage to be reported to council | CCTV footage of pipeline. Post construction | W | P | W
4.1 | Connection to WDC Network | Connection to WDC Network | In accordance with WDC EES - undertaken by Licensed Contractor for Stormwater connections | Visual inspection/photos | P | P | H
1.1 | Final Completion Inspection | Final Completion Inspection | Satisfy Engineer | Visual inspection post construction | W | P | H | 1.1 - Final Completion Inspection | ACTIVITY TASK - Final Completion Inspection | ACCEPTANCE CRITERIA - Satisfy Engineer | CERTIFING DOCUMENTATION AND FREQUENCY - Visual inspection post construction | Supervisor, Foreman or Subcontractor - W | Project Manager or Delegated Person - P | Principal’s Representative - H
2.1 | As-built and Asset Register | As-built Infrastructure | Invert levels to be no more than +30mm than design where grade is CHAR(GREAT)1%, and no more than +3mm where grade is CHAR(LESS)1% | As-built documentation post construction | W | P | H | 2.1 - As-built and Asset Register | ACTIVITY TASK - As-built Infrastructure | ACCEPTANCE CRITERIA - Invert levels to be no more than +30mm than design where grade is CHAR(GREAT)1%, and no more than +3mm where grade is CHAR(LESS)1% | CERTIFING DOCUMENTATION AND FREQUENCY - As-built documentation post construction | Supervisor, Foreman or Subcontractor - W | Project Manager or Delegated Person - P | Principal’s Representative - H
2.2 |  | Asset Register | Asset register completed for installed infrastructure | Post-construction | W | P | H | 2.2 - | ACTIVITY TASK - Asset Register | ACCEPTANCE CRITERIA - Asset register completed for installed infrastructure | CERTIFING DOCUMENTATION AND FREQUENCY - Post-construction | Supervisor, Foreman or Subcontractor - W | Project Manager or Delegated Person - P | Principal’s Representative - H
3.1 | Post-completion Certificate | Post-completion Certificate | Post-completion Certificate | Post-construction | W | P | H | 3.1 - Post-completion Certificate | ACTIVITY TASK - Post-completion Certificate | ACCEPTANCE CRITERIA - Post-completion Certificate | CERTIFING DOCUMENTATION AND FREQUENCY - Post-construction | Supervisor, Foreman or Subcontractor - W | Project Manager or Delegated Person - P | Principal’s Representative - H