## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-076-CIV-CPD-Pit 5.5 Installation Melbourne Water | itp |  |  |  | Yes | ITP-076-CIV-CPD-Pit 5.5 Installation Melbourne Water Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-CIV- CPD - Melbourne Water - Stormwater Pit Suppy & Installation
label | ITP Description: Melbourne Water - Stormwater Pit Suppy & Installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | Revision Number: 0
label | Revision Date: 19/09/2023
label | ITP created by: Ethan Caruana Smith
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 701 (May 2020)
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 705 (June 2021)
checkpoint | 1.3 - Non Dependent
label | Reference - Melbourne Water Standard Drawing 7251/08/416
checkpoint | 1.4 - Non Dependent
label | Reference - Melbourne Water Standard Drawing 7251/08/423
checkpoint | 1.5 - Non Dependent
label | Reference - IFC Drawings - Package 36
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Precast Drainage Pit
label | Reference - IFC drawings - package 36, Gestalt Engineers pit L-4/5 & L-5/5 package
label | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with design drawings marked as IFC.
label | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Drainage Pit - Step Irons
label | Reference - Melbourne Water Standard Drawing 7251/08/416
label | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12 and Melbourne Water - 7251/08/416
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
checkpoint | 2.3 - Drainage Bedding
label | Reference - IFC drawings - package 36
label | Acceptance Criteria - Pit shall be installed on nominal 50mm thick 200 Sq concrete packers. positioned at 1m centres around perimeter of pit. Underside of pit to be flood grouted with Min 25Mpa grout
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Drainage Backfill Material
label | Reference - IFC drawings - package 36, Melbourne Water Backfilling the excavation - Backfilling materials 6.8.2
label | Acceptance Criteria - Approved Backfill as per Mebourne Water requirements
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Survey Set Out - Pits
label | Reference - IFC Drawings
label | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | Method - Survey
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Pits - Excavation
label | Reference - IFC Drawings
label | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
checkpoint | 5.2 - Pits - Placement of Bedding Material
label | Reference - IFC Drawings
label | Acceptance Criteria - Underside of pit to be flood grouted with Min 25Mpa grout - As per Design Drawings
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
checkpoint | 5.3 - Pits - Bedding Testing
label | Reference - IFC Drawings Section 701.20
label | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength per sample comply with the design strength.
label | Method - Document Review
label | Frequency - Each Cube
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Compaction test results
date | Date Completed:
checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
label | Reference - IFC Drawings Section 701.10
label | Acceptance Criteria - Survey pick-up to verify:
label | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm22
label | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
label | Reference - IFC Drawings Section 705.06, Section 610, Section 611
label | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | Method - Survey, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
checkpoint | 5.6 - Pits - Jointing & Drainage Connections
label | Reference - Section 705.11 Package 36
label | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | ○ Joints to be sealed with Hydrophilic seal around pipe as per design package 36.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
checkpoint | 5.7 - Pits - Shaping of Floor
label | Reference - Section 705.13
label | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
checkpoint | 5.8 - Pits - Step Irons
label | Reference - Melbourne Water Standard Drawing 7251/08/416
label | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with Melbourne Water 7251/08/416. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
checkpoint | 5.9 - Pits - Fitting of Covers
label | Reference - IFC Drawings Section 705.17
label | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh shrinkage compensated grout with a minimum of 40MPa.
label | ○ Height shall be within 10mm of the design level.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
checkpoint | 5.10 - Pits - Pit Lids
label | Reference - IFC Drawings
label | Acceptance Criteria - Precast steel reinforced concrete drainage lid shall be manufactured, supplied and installed in accordance with design drawings marked as IFC.
label | ○ Stitch pour concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
textbox | Enter: Teambinder Material Approval number
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
label | Reference - Section 705.18
label | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | Method - Visual inspection, Measure
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - IFC drawings - Package 36
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Flushing & CCTV
label | Reference - Section 701.28, Section 701.30
label | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | Method - Record Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP, CCTV Reports
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - As Built Survey
label | Reference - Section 701.10
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP, As Built Survey Report
date | Date Completed:
checkpoint | 6.3 - Repairs to Damaged Pipes
label | Reference - Section 701.31
label | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | ○ cracks wider than 0.5 mm
label | ○ spalling of concrete
label | ○ exposed reinforcement
label | ○ joints that are not fully engaged.
label | Any pipes with defects greater than the following limits shall be removed and replaced:
label | ○ longitudinal cracks greater than 2 mm
label | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | ○ circumferential cracks around part of the circumference with width greater than 4 mm
label | ○ penetrations with area greater than 400 mm2
label | ○ pipe joints that are separated.
label | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP, Approved Repair Procedure, Post Repair CCTV Report
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP