## Table 1
SECTION 1 – GENERAL DETAILS
Project Name: | [7 empty] | Inspection Key. |  |  |  | Responsibilities
Project Number: | [7 empty] | A |  | Action |  | Role Key |  |  |  | Name |  |  | Signature/ Initial
Client: | [7 empty] | B |  | Report by Breach |  | CR Client Representative
Contract Number: | [7 empty] | C |  | Check |  | PE Project Engineer
Lot Number / ID | [7 empty] | D |  | Dimension Inspection |  | IP Inspection Personnel
SP Supervisor
[8 empty] | E |  | Examine
ITP Number: |  |  |  |  | Version: |  | 0
[8 empty] | H |  | Hold Point
ITP Description: |  | Install Concrete Column | [5 empty] | I |  | Inspection
Prepared By: | [7 empty] | M |  | Monitor on Random Basis
Revision Date
[8 empty] | O |  | Operation
Comments: | [7 empty] | R |  | Review
[8 empty] | S |  | Subcontractor
[8 empty] | V |  | Visual Verification
[8 empty] | W |  | Witness Point
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Vic Civil |  |  | Name: |  |  |  |  | Signature: | [6 empty] | Date:
Client Close Out (If Req) |  |  | Name: |  |  |  |  | Signature: | [6 empty] | Date:
SECTION 3 – RECEIVING INSPECTIONS
Item No. | Activity/ Task Description |  |  | Inspection Point: Quality Control Activity |  | Acceptance Criteria |  |  | Verifying Document |  | Inspection/ Test |  |  | Inspection Point/ Signature & Date
[11 empty] | Key |  | By | Vic Civil Signature |  |  | Client Signature | Date |  | Comments
3.1 | Survey / Set out |  |  | Levels confirmed on site |  | Set out in accordance with design drawings or site conditions |  |  | Visual Inspection / On Site Verification |  | I |  | IP
SECTION 4 – IN-PROCESS INSPECTIONS
Item No. | Activity/ Task Description |  |  | Inspection Point: Quality Control Activity |  | Acceptance Criteria |  |  | Verifying Document |  | Inspection/ Test |  |  | Inspection Point/ Signature & Date
[11 empty] | Key |  | By | Vic Civil Signature |  |  | Client Signature | Date |  | Document Reference
4.1 | Reinforcement Installation |  |  | Structural Reinforcement as per Structural Design documentation / additional SDA |  | Steel bar installed as required, with starter bars if needed |  |  | Client Engineering Inspection |  | HP |  | IP
4.2 | Formworks |  |  | Formworks to comply with the final shape/size of the column |  | Formworks match designs and will enable concrete finishes as desired |  |  | Visual Inspection |  | WP |  | IP
4.3 | Finish |  |  | Finish surface of column or off-form finish |  | Finished as required |  |  | Visual Inspection |  | WP |  | IP
SECTION 3 – RECEIVING INSPECTIONS
Item No. | Activity/ Task Description |  |  | Inspection Point: Quality Control Activity |  | Acceptance Criteria |  |  | Verifying Document |  | Inspection/ Test |  |  | Inspection Point/ Signature & Date
[11 empty] | Key |  | By | Vic Civil Signature |  |  | Client Signature | Date |  | Comments
4.4 | Pre-Pour Concrete Check |  |  | Inspection of reo and formworks |  | Steel reinforcement in accordance with design documentation |  |  | Client Inspection |  | HP |  | IP
4.5 | Concrete Pour |  |  | Concrete is poured to required levels and strength |  | Strength and finish requirement met Finished level within tolerances |  |  | Visual inspection Strength Test Supplier: |  | HP |  | IP
SECTION 5 – FINAL INSPECTION AND HANDOVER
Item No. | Activity/ Task Description |  |  | Inspection Point: Quality Control Activity |  | Acceptance Criteria |  |  | Verifying Document |  | Inspection/ Test |  |  | Inspection Point/ Signature & Date
[11 empty] | Key |  | By | Vic Civil Signature |  |  | Client Signature | Date |  | Comments
5.1 | Completions |  |  | Inspection of works |  | Works completed to the client requirements |  |  | This document |  | H |  | PE
SECTION 6 – COMMENTS