## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP007 - Concrete - Column Installation | itp |  |  |  |  | ITP007 - Concrete - Column Installation
section | SECTION 1 – GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
textbox | Project Name:
textbox | Project Number:
label | Client:
label | Contract Number:
label | Lot Number / ID
textbox | ITP Number:
textbox | Version:
label | ITP Description: Install Concrete Column
textbox | Prepared By:
date | Revision Date
section | SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
checkpoint-no-status | ITP Close-Out by Vic Civil
textbox | Name:
date | Date:
checkpoint-no-status | Client Close Out (If Req)
textbox | Name:
date | Date:
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Survey / Set out
label | Inspection Point: Quality Control Activity - Levels confirmed on site
label | Acceptance Criteria - Set out in accordance with design drawings or site conditions
label | Verifying Document - Visual Inspection / On Site Verification
label | Key - I
label | By - IP
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Reinforcement Installation
label | Inspection Point: Quality Control Activity - Structural Reinforcement as per Structural Design documentation / additional SDA
label | Acceptance Criteria - Steel bar installed as required, with starter bars if needed
label | Verifying Document - Client Engineering Inspection
label | Key - HP
label | By - IP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Formworks
label | Inspection Point: Quality Control Activity - Formworks to comply with the final shape/size of the column
label | Acceptance Criteria - Formworks match designs and will enable concrete finishes as desired
label | Verifying Document - Visual Inspection
label | Key - WP
label | By - IP
checkpoint | 4.3 - Finish
label | Inspection Point: Quality Control Activity - Finish surface of column or off-form finish
label | Acceptance Criteria - Finished as required
label | Verifying Document - Visual Inspection
label | Key - WP
label | By - IP
checkpoint | 4.4 - Pre-Pour Concrete Check
label | Inspection Point: Quality Control Activity - Inspection of reo and formworks
label | Acceptance Criteria - Steel reinforcement in accordance with design documentation
label | Verifying Document - Client Inspection
label | Key - HP
label | By - IP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Concrete Pour
label | Inspection Point: Quality Control Activity - Concrete is poured to required levels and strength
label | Acceptance Criteria - Strength and finish requirement met, Finished level within tolerances
label | Verifying Document - Visual inspection Strength Test Supplier:
label | Key - HP
label | By - IP
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Completions
label | Inspection Point: Quality Control Activity - Inspection of works
label | Acceptance Criteria - Works completed to the client requirements
label | Verifying Document - This document
label | Key - H
label | By - PE
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – COMMENTS
checkpoint-no-status | Comments