## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP105 - Civil - Concrete Stairs | itp |  |  |  |  | ITP105 - Civil - Concrete Stairs
section | SECTION 1 – GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
textbox | Project Name:
textbox | Project Number:
label | Client:
label | Contract Number:
label | Lot Number / ID
textbox | ITP Number:
textbox | Version:
label | ITP Description: Concrete Stair Installation
textbox | Prepared By:
date | Revision Date
section | SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
checkpoint-no-status | ITP Close-Out by Vic Civil
textbox | Name:
date | Date:
checkpoint-no-status | Client Close Out (If Req)
textbox | Name:
date | Date:
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Survey / Set out
label | Inspection Point: Quality Control Activity - Levels confirmed on site
label | Acceptance Criteria - Set out in accordance with design drawings or site conditions
label | Verifying Document - Visual Inspection / On Site Verification
label | Key - I
label | By - IP
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 3.1 - Preparation of Subgrade/Rock Preparation
label | Inspection Point: Quality Control Activity - Subgrade meets design requirements. FCR placed to specified thickness and compacted
label | Acceptance Criteria - No soft spots. Rock layer conforms to required thickness.
label | Verifying Document - Visual Inspection. Geotech test if required.
label | Key - W
label | By - IP
checkpoint | 3.2 - Formwork
label | Inspection Point: Quality Control Activity - Installation of formwork to support stairs
label | Acceptance Criteria - As per temp design
label | Verifying Document - Visual Inspection
label | Key - H
label | By - PE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Steel Reinforcement
label | Inspection Point: Quality Control Activity - Installation of steel mesh and or steel bar reinforcement as per drawings
label | Acceptance Criteria - Reinforcement installed as required
label | Verifying Document - Visual Inspection
label | Key - H
label | By - IP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Concrete Pour
label | Inspection Point: Quality Control Activity - Concrete is poured to required levels and strength
label | Acceptance Criteria - Strength and finish requirement met
label | Verifying Document - Visual inspection only Strength Test
label | Key - I
label | By - IP
checkpoint | 3.5 - Stair edging or surface treatments
label | Inspection Point: Quality Control Activity - Stair treatments installed as required. (stair nosing’s, edge treatments, etc.)
label | Acceptance Criteria - As per drawings
label | Verifying Document - Visual inspection
label | Key - I
label | By - IP
section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Completions
label | Inspection Point: Quality Control Activity - Inspection of works
label | Acceptance Criteria - Works completed to the client requirements
label | Verifying Document - This document
label | Key - H
label | By - PE
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – COMMENTS
checkpoint-no-status | Comments