## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S104 - Piling Overarching - Rev 1 | itp |  |  |  |  | DS2672-ITP-S104 - Piling Overarching - Rev 1
section | 3.01 Site Requirements
checkpoint | 3.01.01 - Construction Pack
note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
note | Standard / Specification - Downer
note | Verifying Document - Construction Pack
note | Frequency - Submit Prior to commencement of works
note | Activity - H
note | By - PE
checkpoint | 3.01.02 - Survey Setout
note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
note | Standard / Specification - Downer
note | Verifying Document - Survey Records
note | Frequency - Prior to Works
note | Activity - H
note | By - SV
checkpoint | 3.01.03 - Service Location
note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
note | Standard / Specification - Downer
note | Verifying Document - Excavation Permit
note | Frequency - Prior to Excavation
note | Activity - H
note | By - SE
checkpoint | 3.01.04 - Internal Permits
note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
note | Standard / Specification - Downer
note | Verifying Document - Internal Permits
note | Frequency - Prior to Excavation
note | Activity - H
note | By - SE
checkpoint | 3.01.05 - External Permits
note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
note | Standard / Specification - Downer
note | Verifying Document - External Permits
note | Frequency - Prior to Excavation
note | Activity - H
note | By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
note | Standard / Specification - Downer
note | Verifying Document - IFC Drawings
note | Frequency - Prior to works start
note | Activity - H
note | By - PE
section | 7.01 Piling General
checkpoint | 7.01.01 - Method Statements
note | Acceptance / Conformance Criteria - A detailed method statement shall be prepared by the Constructor for the Designer’s review for each piling operation undertaken on the site.
note | Standard / Specification - 51/33669 - 3.2, 4
note | Verifying Document - Method Statement
note | Frequency - 3 weeks prior to the commencement of each piling operation
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.01.02 - Piling Change
note | Acceptance / Conformance Criteria - When a change is made to the piling crew, excavation method or other change (e.g. variations in ground conditions) that could influence the quality of the works, the Designer may adjust the inspection requirement and frequency to suit the revised risk profile of the works.
note | Standard / Specification - 51/33669 - 6.3.2
note | Verifying Document - Notice
note | Frequency - When a change is made
note | Activity - W
note | By - ENG
checkpoint | 7.01.03 - Jointing of permanent casing Inspection
note | Acceptance / Conformance Criteria - Designer inspection of jointing of permanent casings for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure)
note | Standard / Specification - 51/33669 - 9.4
note | Verifying Document - Hold Point Release
note | Frequency - First pile at every structure
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 10.01 Site Post Construction Activities
checkpoint | 10.01.01 - Construction Record Compilation
note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
note | Standard / Specification - Downer
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - SE
checkpoint | 10.01.02 - Survey Records
note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
note | Standard / Specification - Downer P&G 20.1
note | Verifying Document - Records
note | Frequency - Post construction
note | Activity - H
note | By - PE
checkpoint | 10.01.03 - Redline Drawings
note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red-pen mark-up copies of the Drawings and Specifications and other design documentation showing any deviations from the specified details and requirements produced in accordance with industry good practice.
note | Standard / Specification - Downer P&G 20.1
note | Verifying Document - Redlines
note | Frequency - Post construction
note | Activity - H
note | By - PE
checkpoint | 10.01.04 - Defect, Snag and Punch List
note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
note | Standard / Specification - Downer
note | Verifying Document - Register
note | Frequency - Post construction
note | Activity - H
note | By - PE