## res_1630-P200-SYM-QAC-ITP-0021.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-0024 - STORMWATER DRAINAGE PITS AND PIPES | itp |  |  |  |  | ITP-0024 - STORMWATER DRAINAGE PITS AND PIPES
section | NA HOLD POINTS
checkpoint | 1.4 Trench Shields
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.5 Material Conformance Mortar
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.9 Acceptance of precast reinforced Concrete Pipes & Pits
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.10 Supply Precast Covers, Grates, Box Culverts, Lids and Pits
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.1 Set Out
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.11 Precast Fibre Reinforced Concrete Drainage Pit (if applicable)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.13 Step Iron Fitting
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.17 Backfill with Cement Stabilised Sand
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.22 Inspection of Drainage Lines
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.23 Repairs to Damaged Pipes
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.5 NCR Close out (if applicable)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | MATERIAL DELIVERY DOCKETS
checkpoint | PHOTOS
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint | SURVEY CONFORMANCE REPORT
checklist | ITP-0027 - TYPE A FILL PLACEMENT | itp |  |  |  |  | ITP-0027 - TYPE A FILL PLACEMENT
section | NA HOLD POINTS
checkpoint | 2.1 PRE-CONDITION
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.4 FILL AT STRUCTURES
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.5 TEST ROLL
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint | OTHER
checklist | ITP-0029 - UNBOUND FLEXIBLE PAVEMENTS | itp |  |  |  |  | ITP-0029 - UNBOUND FLEXIBLE PAVEMENTS
section | NA HOLD POINTS
checkpoint | 2.4 Material of Nominal Size Greater than 40mm (if required)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.6 Testing – Stability (Proof Roll)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint | AS-BUILT SURVEY REPORT
checklist | ITP-0042 - CONDUITS (TRENCHING & INSTALL) | itp |  |  |  |  | ITP-0042 - CONDUITS (TRENCHING & INSTALL)
section | NA HOLD POINTS
checkpoint | 2.5 EXCAVATION AND BORING
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.1 CERTIFICATION OF INSTALLATION
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | DELIVERY DOCKETS
checkpoint | AS-BUILT SURVEY REPORT
checklist | ITP-0059 - HOT MIX ASPHALT PLACEMENT | itp |  |  |  |  | ITP-0059 - HOT MIX ASPHALT PLACEMENT
section | NA HOLD POINTS
checkpoint | 1.6 ASPHALT MIX DESIGN
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 1.8 BITUMINOUS MATERIALS
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.1 RAP MAMNAGEMENT
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.6 APPROVAL FOR COMMENCEMENT OF PLACING
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.9 AMBIENT CONDITIONS FOR PLACING
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.10 COMMENCEMENT OF PLACEMENT
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.13 TRAFFICKING PAVEMENT AFTER PLACEMENT
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 2.17 SURFACE RECTIFICATION (IF REQUIRED)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
checkpoint | 3.3 NCR CLOSE OUT (IF APPLICABLE)
textbox | Holdpoint number
holdpoint | Authority Holdpoint
section | ATTACHMENTS
checkpoint | LOT MAP
checkpoint | GEOTECHNICAL REPORT - COMPACTION
checkpoint | GEOTECHNICAL REPORT - MATERIAL PROPERTIES
checkpoint | PHOTOS