## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Cesspit |  |  |  |  | Yes | Cesspit | f65fd03c-5b4e-48e0-8c43-bc5372110c85
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | 34df29de-8bbe-5d24-b3fd-7ee97088c3ec |  | textbox | Drawing Ref No.
checkpoint-status |  |  | checkpoint | Tank sizing checked to match plans
checkpoint-status |  |  | checkpoint | Setout checked and run through with operator
checkpoint-status |  |  | checkpoint | Prep Height Determined
text | 4278928f-9c27-5ce4-a633-307f7a0c9e7a |  | textbox | IL Outlet
boolean | 91adea48-45dc-5fd5-a3d1-3f69ccb4d2bd |  | tickbox | IL Outlet = Prep height
boolean | 1822fd82-7fdc-5971-9e6c-960aa231e83f |  | tickbox | Ensure lid level is lower than future works
checkpoint-status |  |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status |  |  | checkpoint | Benching/shield required if depth is >1.5m
checkpoint-status |  |  | checkpoint | Bedding depth and material correct and compacted (Photo Required)
boolean | b5d2d37f-ecd8-53cb-929d-327981b83733 |  | tickbox | Ensure Sump is dug out
checkpoint-status |  |  | checkpoint | Backfill material correct and compacted in 300mm layers (Photos required)
boolean | 314d7ce0-1600-5c20-865e-279097a6a63e |  | tickbox | Anchors required for tanks not under future concrete works
checkpoint-status |  |  | checkpoint | Pipes connected according to plan with suitable bedding and haunching (Photo Required)
checklist-flat |  |  | checklist | Private Sewer Pumps Station |  |  |  |  | Yes | Private Sewer Pumps Station | 23031ec4-35ee-4509-a280-6f0754ca4772
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | dcf6a728-9321-5247-8579-2b2059c1e15f |  | textbox | Drawing Ref No.
checkpoint-status |  |  | checkpoint | Tank sizing checked to match plans
checkpoint-status |  |  | checkpoint | Setout checked and run through with operator
checkpoint-status |  |  | checkpoint | Prep Height Determined
text | ce4302ea-b237-54af-9c65-5196f3efac60 |  | textbox | IL Outlet
boolean | 84d44108-85a8-59ea-b5bd-296c393fc853 |  | tickbox | IL Outlet = Prep height
boolean | 24035053-41cc-590e-b886-06f228e737df |  | tickbox | Ensure lid level is lower than future works
checkpoint-status |  |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status |  |  | checkpoint | Benching/shield required if depth is >1.5m
checkpoint-status |  |  | checkpoint | Bedding depth and material correct and compacted (Photo Required)
boolean | e50d7f84-b442-5aaf-a541-43b79ba4d371 |  | tickbox | Ensure Sump is dug out
checkpoint-status |  |  | checkpoint | Backfill material correct and compacted in 300mm layers (Photos required)
boolean | 91303d07-38b9-5d44-b9f9-65db580c3b4a |  | tickbox | Anchors required for tanks not under future concrete works
checkpoint-status |  |  | checkpoint | Pipes connected according to plan with suitable bedding and haunching (Photo Required)
checkpoint-status |  |  | checkpoint | Pumps tested and commissioned
checklist-sectioned |  |  | checklist | Sewer Junction |  |  |  |  | Yes | Sewer Junction | aea87d05-a34b-445f-8681-f9f0489f52fd
checkpoint-group |  |  | section | Sewer Junction
checkpoint-status |  |  | checkpoint | Correct Junction SN16 Y Junction or SN16 Z Junction
checkpoint-status |  |  | checkpoint | Target Checked on Junction
checkpoint-status |  |  | checkpoint | Fall Checked with level
checkpoint-status |  |  | checkpoint | Angle of Junction between 30 and 60 degrees (Photo Required)
checkpoint-status |  |  | checkpoint | Junction Pegged and Sprayed Red
checkpoint-status |  |  | checkpoint | Inspection straight if connecting to private drainage (Photo Required)
checklist-sectioned |  |  | checklist | Stormwater Concrete Junction |  |  |  |  | Yes | Stormwater Concrete Junction | 58f98b1c-cc14-4d57-b858-24e7985363da
checkpoint-group |  |  | section | Stormwater Concrete Junction
checkpoint-status |  |  | checkpoint | Correct sized junction
checkpoint-status |  |  | checkpoint | Angle of Junction Between Spring level and 60 degrees (Photo Required)
checkpoint-status |  |  | checkpoint | Expoxy inside and out
checkpoint-status |  |  | checkpoint | Shear band connection (Photo required)
checkpoint-status |  |  | checkpoint | Junction Pegged and Sprayed Blue
checkpoint-status |  |  | checkpoint | Inspection straight if connecting to private drainage (Photo Required)
checklist-sectioned |  |  | checklist | Pipeline Installation |  |  |  |  | Yes | Pipeline Installation | f43188d1-4007-4f63-9d52-0521ae7c787c
checkpoint-group |  |  | section | Pipe Laying
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | 0f3218ef-44f1-559f-9603-006e97d2d0dd |  | textbox | Drawing Ref No.
checkpoint-status |  |  | checkpoint | Setout completed checked and accurate
checkpoint-status |  |  | checkpoint | Services Located and before you dig plans checked
checkpoint-status |  |  | checkpoint | All junctions marked out and run through with operator
checkpoint-status |  |  | checkpoint | Laser grade checked. Correct +/-. Benching required if >1.5m
text | cfec04f4-2027-5596-bd0a-667604377011 |  | textbox | Design Grade %
text | 54f593b5-f038-42b0-a497-4df2079aff2d |  | textbox | Actual Grade %
checkpoint-status |  |  | checkpoint | Laser checked for line with string line
checkpoint-status |  |  | checkpoint | Correct trench width for pipe size
checkpoint-status |  |  | checkpoint | Starter checked for fall. Starter epoxyed to seal from water.
checkpoint-status |  |  | checkpoint | Corbel installed with suitable bedding around pipe (Photo Required)
checkpoint-status |  |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status |  |  | checkpoint | General photos during pipe laying
checkpoint-status |  |  | checkpoint | Pipe Laying Completed
text | 692d00a8-4a4f-570b-8ce2-46c8a690e16a |  | textbox | Laid by
boolean | 1daa0841-49b0-5bf6-812c-c1f81a30f62e |  | tickbox | Trench Compacted
boolean | 30bcebf3-f612-51bc-970d-b5c6b89179a3 |  | tickbox | Vehicle Areas or Road Reserve Hard Filled
checkpoint-status |  |  | checkpoint | CCTV Completed
checklist-sectioned |  |  | checklist | Concrete Surface - Ashphalt ETC |  |  |  |  | Yes | Concrete Surface - Ashphalt ETC | b71a7634-ece7-42d9-80b6-95e0d125aa0c
checkpoint-group |  |  | section | Concrete Right of Way
checkpoint-status |  |  | checkpoint | Setout complete and checked
checkpoint-status |  |  | checkpoint | Services Located and before you dig plans checked
checkpoint-status |  |  | checkpoint | Stringline set out
boolean | 37468f06-047e-5b16-9ea9-daa05c5f08fe |  | tickbox | String checked for fall
boolean | 5a551fc1-c8c1-527e-a74c-720392aa69dd |  | tickbox | Driveway checked for correct width
checkpoint-status |  |  | checkpoint | Excavation correct depth
checkpoint-status |  |  | checkpoint | Metal correct depth (Photos required)
checkpoint-status |  |  | checkpoint | Metal compacted
checkpoint-status |  |  | checkpoint | Lids set
checkpoint-status |  |  | checkpoint | Steel placed
checkpoint-status |  |  | checkpoint | Engineer Inspection
checkpoint-status |  |  | checkpoint | Boxing stripped
checkpoint-status |  |  | checkpoint | Topsoil placed (if required)
checklist-flat |  |  | checklist | Services |  |  |  |  | Yes | Services | 819297ce-8304-4fb7-988a-bb7321a03c62
checkpoint-status |  |  | checkpoint | Latest consented drawings
checkpoint-status |  |  | checkpoint | Trench width to allow for separation between services
checkpoint-status |  |  | checkpoint | All laterals marked out
checkpoint-status |  |  | checkpoint | General photos
checkpoint-status |  |  | checkpoint | Surveyor as-built completed
checkpoint-status |  |  | checkpoint | Warning tape and magslab installed
checklist-flat |  |  | checklist | Detailed Excavation |  |  |  |  | Yes | Detailed Excavation | a64c4621-c456-43ea-9e57-ed1c701bd495
checkpoint-status |  |  | checkpoint | Services Located
checkpoint-status |  |  | checkpoint | Location accurate
checkpoint-status |  |  | checkpoint | Topsoil stripped completely
checkpoint-status |  |  | checkpoint | Building pads set out correctly with RLs as required for cut/fill
checkpoint-status |  |  | checkpoint | Correct cut back for walls/foundations
checkpoint-status |  |  | checkpoint | Geotech Engineer Inspection
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
checklist-flat |  |  | checklist | End Cap |  |  |  |  | Yes | End Cap | 45060cf7-64e7-4544-b272-1a31bf8cbb8d
checkpoint-status |  |  | checkpoint | Photo and location of capped connection
checklist-sectioned |  |  | checklist | Stormwater PVC Junction |  |  |  |  | Yes | Stormwater PVC Junction | 00013314-907e-4386-8b32-5b6ee63d9105
checkpoint-group |  |  | section | Stormwater PVC Junction
checkpoint-status |  |  | checkpoint | Correct Junction SN16 London Junction or SN16 Y Junction
checkpoint-status |  |  | checkpoint | Target Checked on Junction
checkpoint-status |  |  | checkpoint | Fall Checked with level
checkpoint-status |  |  | checkpoint | Angle of Junction Between Spring level and 60 degrees (Photo Required)
checkpoint-status |  |  | checkpoint | Junction Pegged and Sprayed Blue
checkpoint-status |  |  | checkpoint | Inspection straight if connecting to private drainage (Photo Required)
checklist-flat |  |  | checklist | Civil - Retaining walls |  |  |  |  | Yes | Civil - Retaining walls | cd4c5a73-deb4-4eb5-867b-a5d9bc2bd24e
checkpoint-status |  |  | checkpoint | Retaining wall(s) setout/heights confirmed
checkpoint-status |  |  | checkpoint | Services Located
checkpoint-status |  |  | checkpoint | Profiles set out level and rigid. Ensure boundary is encompassed within profile.
checkpoint-status |  |  | checkpoint | Finished heights are set hole spacing and pole sizes depending on retained height
boolean | 5e8766dd-d0e5-53e5-8b84-dd14ece6842d |  | tickbox | Excavation correct
boolean | 79431808-7782-5f08-a1c8-cdc214cdeba9 |  | tickbox | correct hole size
boolean | ccf17069-8d13-59fa-8fa6-351caec56119 |  | tickbox | correct pole size
boolean | e6cc3298-647d-517b-a3e0-39bb24df5004 |  | tickbox | correct depth
boolean | a8fcdb21-a2e6-55c8-85a4-289e0daba76f |  | tickbox | All pile holes are inside boundary
checkpoint-status |  |  | checkpoint | General install photos and observations attached
checkpoint-status |  |  | checkpoint | Geotech Pre-pour Inspection
checkpoint-status |  |  | checkpoint | Structural Engineer Inspection
checkpoint-status |  |  | checkpoint | Lagging to be arissed on visible side.
checkpoint-status |  |  | checkpoint | Correct screws/nails used, galvanised/stainless steel etc
checkpoint-status |  |  | checkpoint | Backfill completed - correct materials and compaction methodology used
checklist-sectioned |  |  | checklist | Manhole Installation |  |  |  |  | Yes | Manhole Installation | 5fcf2626-a57f-41fe-aafb-6b56f3372ece
checkpoint-group |  |  | section | Manhole Install
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | d7b3ae31-6175-5520-b6e6-efcf66108ac4 |  | textbox | Drawing Ref No.
checkpoint-status |  |  | checkpoint | Setout an manhole sizing checked
checkpoint-status |  |  | checkpoint | Services Located and before you dig plans checked
checkpoint-status |  |  | checkpoint | MHS measured onsite. Prep height determined from Lid Level.
text | 1d6be5d5-068f-5452-b16d-2fc7540f7825 |  | textbox | Lid Level RL
boolean | f8f6bb6f-e473-514a-beb0-726d15ce22dd |  | tickbox | Lid level confirmed as correct
text | 6fd47e60-4b65-557b-a9ed-6cd0dffe13e2 |  | textbox | Manhole System allow 50mm play
text | 100f95c5-36b6-5dc1-a60d-260e5b2610b5 |  | textbox | Prep height RL
text | b57fbda4-a15a-5062-9af3-84b25717cb3a |  | textbox | Outlet RL
boolean | 98149633-3ef1-544c-91f5-b02ac425148a |  | tickbox | Outlet RL is 200mm greater than Prep height RL
boolean | 909467dc-9d1a-579f-b555-f34e77bb48c7 |  | tickbox | Throat height checked to be less than 450mm
boolean | 3d08c737-0664-5179-b51b-2710c82d6469 |  | tickbox | Concrete lid will be underneath future works
checkpoint-status |  |  | checkpoint | Benching/shield required if >1.5m
checkpoint-status |  |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status |  |  | checkpoint | Bedding depth and material correct & compacted (Photo Required)
checkpoint-status |  |  | checkpoint | Cut in Manhole Shearbands ( Photos required)
checkpoint-status |  |  | checkpoint | Manhole Risers epoxyed (if applicable Photo required)
checkpoint-status |  |  | checkpoint | Inside of starters epoxyed all the way around
checkpoint-status |  |  | checkpoint | Manhole benching completed and acceptable (Photo required)
checkpoint-status |  |  | checkpoint | Concrete Lid Installed, Correct orientation and sealed
checkpoint-status |  |  | checkpoint | Cast Iron Lid Raised and Installed at 90 degrees to steps
checkpoint-status |  |  | checkpoint | Epoxy completed inside lid and
checkpoint-status |  |  | checkpoint | Stormwater lids to be spray painted blue
checkpoint-status |  |  | checkpoint | Sewer manhole safety grille installed
checklist-flat |  |  | checklist | Retaining Wall |  |  |  |  | Yes | Retaining Wall | 43ca8ec5-99e8-41ca-84cb-7351bf277060
checkpoint-status |  |  | checkpoint | Latest consented drawings
boolean | 2c5b60df-2c50-5944-b64c-9b19d35acdad |  | tickbox | Finished levels confirmed
checkpoint-status |  |  | checkpoint | Minimum clearance of 1m between edge of pile hole and edge of pipe if applicable
checkpoint-status |  |  | checkpoint | Pipe bridging detail required
checkpoint-status |  |  | checkpoint | Clay wall has been excavated to allow for installation of lagging and backfill post pour (approx. 300mm from back of post). Varies between types
checkpoint-status |  |  | checkpoint | Profiles set up with a nail for the external boundaries
checkpoint-status |  |  | checkpoint | Retaining set out is correct
boolean | 53632ab4-dec4-5942-b7d1-8f6e8aac3d64 |  | tickbox | String line set up showing finished levels
boolean | 656d11a9-d1df-5e7d-9966-73637ae2c756 |  | tickbox | Pile holes are within boundary
boolean | ce0e2ee1-bb16-536a-8445-3f2d4b1cb464 |  | tickbox | Pole spacings correct
boolean | f467bd49-1459-542b-9086-89632e30f741 |  | tickbox | Pole sizes correct
boolean | 4678bdae-d794-5624-a53b-1c4b494e1566 |  | tickbox | Hole depths correct
checkpoint-status |  |  | checkpoint | Geotech Inspection
checkpoint-status |  |  | checkpoint | Structural Inspection
checkpoint-status |  |  | checkpoint | Council Inspection
checkpoint-status |  |  | checkpoint | General pre pour photos: Hole depths, spacings, pole sizes
checkpoint-status |  |  | checkpoint | Backfill
boolean | 232d4eb6-2c5a-517f-8c13-0bf9c63796f6 |  | tickbox | Bidim cloth required or N/A
boolean | 9f7075b3-3e13-5b22-bff7-bbe000d82454 |  | tickbox | Correct drainage metal used for backfill
checklist-flat |  |  | checklist | APD Tank Installation |  |  |  |  | Yes | APD Tank Installation | 104e3c89-6a5a-4c7e-88fc-6204c370e4e3
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | 963eec1b-fd38-50a5-b2aa-a8bcd39f787e |  | textbox | Drawing Ref No.
checkpoint-status |  |  | checkpoint | Tank sizing checked to match plans
checkpoint-status |  |  | checkpoint | Setout checked and run through with operator
checkpoint-status |  |  | checkpoint | Prep Height Determined
text | 3fed289d-0294-5ff5-be9e-d19db7abec63 |  | textbox | IL Outlet
boolean | d894f8e9-0a27-5fb2-b90b-26a396bc803e |  | tickbox | IL Outlet = Prep height
boolean | e78f8284-bdcd-5cb0-bede-96d92d13b14c |  | tickbox | Ensure lid level is lower than future works
checkpoint-status |  |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status |  |  | checkpoint | Benching/shield required if depth is >1.5m
checkpoint-status |  |  | checkpoint | Bedding depth and material correct and compacted (Photo Required)
boolean | 9e15e77b-3b84-5fb8-994a-3c0040813aae |  | tickbox | Ensure Sump is dug out
checkpoint-status |  |  | checkpoint | Backfill material correct and compacted in 300mm layers (Photos required)
boolean | 6afc8771-7313-5f81-aa62-e09e4721e135 |  | tickbox | Anchors required for tanks not under future concrete works
checkpoint-status |  |  | checkpoint | Pipes connected according to plan with suitable bedding and haunching (Photo Required)