## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Multiplex Column Concrete Pour ITP (V.132121) | [5 empty] | Multiplex Column Concrete Pour ITP (V.132121)
section | Pre-Pour
checkpoint | Subcontractor Column Prepour Completed
note | ITP Completed by Form700 and all documents uploaded to CONQA
checkpoint | Reinforcement installation - inspected by MPX
note | MANDATORY - Attach photos below of inspected elements
checkpoint | Services penetrations - Inspected for all slabs/walls and "CONQA-Service Penetrations Matrix" verified as passed off by each of the services subcontractors
note | Markup attached as applicable
checkpoint | Cast in items and holding down bolts - Confirmation of Form700 completed ITP
checkpoint | Cast in items and holding down bolts - MPX Inspection of all elements
note | MANDATORY - Attach photos below of inspected elements
checkpoint | Area clean - All debris removed from the area prior to pouring concrete
checkpoint | Reinforcement installation - Inspected by structural engineer and corrective actions completed and signed-off
note | Structural Engineer Inspection report attached below (If applicable)
tickbox | Corrective actions completed and signed-off - Attach corrective action photos below
signoff | Request Structural Engineer Sign-Off
section | During Pour
checkpoint | Placement of concrete checked
note | Monitored by Multiplex and subcontractor supervision to ensure adequate compaction/vibration of concrete is achieved
checkpoint | Concrete Testing - Compressive testing and slump tests samples completed by supplier
checkpoint | Concrete Traceability - Mud map established to indicate date and location of pour
note | Mudmap attached below
section | Post-Pour
checkpoint | Curing – Application rate of approved curing compound being applied in accordance with manufacturers recommendations
checkpoint | Concrete test results - Compressive strength results for initial and final stress submitted and compliant
note | Report attached below
checkpoint | Concrete test results - 28 day compressive strength results submitted and compliant
note | Report attached below