## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV-Camms- Hot Mix Asphalt
ITP Description: |  | Camms- Hot Mix Asphalt
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2023-08-31
ITP created by: |  | Victor Mira
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | Camms Road
Inspection & Test Plan - Hot Mix Asphalt
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2023-08-31
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VR 407 - July 2022 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VR 173 - Oct 2008 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Mix Design | VR 407.09 | All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport. The registration for all mixes incorporated into the works shall be current at the time of their use. Enter: Teambinder Approval number [free text box] | Document Review | Each Mix | HP | PE/Nominated authority | This ITP TeamBinder Approval
2.2 | Bituminous Materials-Tack Coat | VR 407.08 (d) | Tack coat shall consist of a bituminous based binder. only trackless tack coat or a tack coat application system that prevents pickup of the tack coat must be used. The Contractor shall submit the details of the trackless tack coat proposed to be used in the works. Enter: Teambinder Approval number [free text box] | Document Review | Each Material | HP | PE/Nominated authority | This ITP TeamBinder Approval
3 | Preliminaries - Procedures & Documentation
3.1 | Asphalt Quality Plan | VR 407.04 VR 407.11 | the Contractor shall provide an asphalt quality plan that addresses the following requirements: •RAP Management plan (Approved by DTP) •asphalt loading and transportation to minimise segregation and achieve adequate mix temperature on delivery to site •measuring and recording of pavement temperature, wind speed and weather conditions •achieving a uniform application of tack coat •achieving uniform asphalt placement including determination of paving speed and paving plans •determination of appropriate compaction equipment, number of rollers and rolling patterns required to achieve density •procedures to maximise density at joints. Production, storage, discharge and compaction temperature ranges for warm mix asphalt shall be included in the Contractor’s asphalt quality plan. Enter: Teambinder Approval number [free text box] | Document Review | Each Lot | HP | PE/Nominated authority | This ITP TeamBinder Approval
3.2 | RAP Management Plan | VR 407.13 (f) | No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent. Enter: Teambinder Approval number [free text box] | Document Review | Each Lot | HP | PE/Nominated authority | This ITP TeamBinder Approval
3.3 | Cold weather placement | VR 407.17 (b) | Where approved by the Superintendent placement of dense graded asphalt in layers 35 mm or greater may take place at pavement temperatures up to 5ºC below the minimum temperatures specified in Table 407.171. Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review. Enter: Teambinder Approval number [free text box] | Document Review | Each Lot | HP | PE/Nominated authority | This ITP TeamBinder Approval
4 | Pre-construction Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | PE/SE | This ITP
4.2 | Lot Map-and Lot size | VR 407.21 (a) VR 407.27 (b) (i) | A lot presented for testing shall consist of an asphalt layer which is placed in one shift under uniform conditions and is essentially homogeneous in respect to placement methods, materials and appearance. The location of all joints shall be planned prior commencement to achieve the specified offsets between layers and the position of joints in the wearing course. ATTACH: Lot Map with planned location of Joints | Document review | Each Lot | HP* | PE/SE | attached Lot Map
5 | Construction Activities
5.1 | Ambient Conditions-Surface conditions | VR 407.17 (a) VR 407.18 | The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent. the Contractor shall remove all loose and deleterious material and sweep clean the area upon which asphalt is to be placed. | Visual | Each Lot | IP | PE/SE | This ITP
5.2 | Ambient Conditions-Surface Temperature | VR 407.17 (a) | Asphalt shall not be placed when the majority of the area to be paved has a surface temperature less than that detailed in Table 407.171 and as below: - Specified binder class of C170 or C320: Wearing course: 10°C Other courses: 5°C - Specified binder class of C600 or containing a PMB: Wearing Course 15°C Other courses 10°C | Measure | Each Lot | IP | PE/SE | This ITP
5.3 | Joints and Junctions-Layer by Layer-Transverse Joints | VR 407.21 (b) | Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course. - All transverse joints shall be offset from layer to layer by not less than 2 m. | Visual Measure | Each Lot | IP | PE/SE | This ITP
5.4 | Joints and Junctions-Layer by Layer-Longitudinal Joints | VR 407.21 (c ) | Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course. - Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines. - Longitudinal joints shall be parallel to the traffic lanes. - Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane. | Visual Measure | Each Lot | IP | PE/SE | This ITP
5.5 | Joints and Junctions-Abutting existing pavement | VR 407.21 (c ) | - Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm. - At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied. | Visual Measure | Where applicable | IP | PE/SE | This ITP
5.6 | Joints and Junctions-Junctions at limits of works | VR 407.21 (d ) VR 402 | At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402. The chase shall be cut by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times the nominal size of the asphalt from the existing pavement to the minimum length as follows: (i) at side streets and median openings – 600 mm (ii) on through carriageways with a speed limit of 80 km/h or less – 3 m (iii) on through carriageways with a speed limit of more than 80 km/h – 6 m. | Visual Measure | Where applicable | IP | PE/SE | This ITP
5.7 | Application of Tack Coat | VR 407.19 | A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed. The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen for joints and chases rates shall be doubled. the Contractor may omit the tack coat where asphalt is to be spread over - A clean, un-trafficked, freshly laid asphalt, or - A clean primed surface, or - Granular material where the overall asphalt depth is 150mm or greater. PHOTOGRAPHIC EVIDENCEshall be supplied to show that tack has been applied. ATTACH: Photographic Evidence | Visual | Where applicable | SP | PE/SE | This ITP
5.8 | Joints and Junctions | VR 407.21 (a) | - All joints shall be well bonded and sealed - All cold joints and abutting concrete edges shall be tack coated | Visual | Where applicable | SP | PE/SE | This ITP
5.9 | Delivery Dockets | VR 407.20 | Asphalt delivered to the site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site. Maximum Asphalt temperature at discharge from the plant is 175°C ATTACH: Mix Delivery Docket | Document review | Each Lot | IP | PE/SE | This ITP
5.10 | Commencement of Placement | VR 407.23 | The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent. | Visual | Each Lot | HP | SE/Nominated authority | This ITP
5.11 | Paving of Asphalt | VR 407.25 | Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings. All asphalt shall be spread with paving machine (or by hand if not accessible by Paver) to form a smooth asphalt mat without segregation, tearing or gouging. | Visual | Each Lot | SP | SE/PE | This ITP
5.12 | Paving of Asphalt | VR 407.25 | If the paver is required to stop and asphalt in front of the screed cools to below 120°C, a transverse joint shall be constructed. | Measure | Where applicable | IP | SE | This ITP
5.13 | Compaction | VR 407.26 | Asphalt shall be uniformly . Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement. Vibratory rolling shall not be used to compact asphalt on bridge decks. | Visual | Each Lot | SP | SE | This ITP
6 | Post-construction Activities
6.1 | Compaction test-Lots larger than 500 sqm | VR 407.27 (b) (i) | The work (excluding longitudinal edge strips) represented by a lot of six tests shall be assessed as shown in Table 407.271. For lots exceeding 500 m2 density testing of the longitudinal edge strips (200 mm from the longitudinal joint) for the wearing course shall be undertaken and results reported as a separate lot. The Characteristic Value of the Density Ratio determined for the longitudinal edge strips within the lot shall be submitted for report only ATTACH: Compaction test report ATTACH: Wearing course joint strip compaction test results | Document Review | Each Lot Where Applicable | HP | Nominated authority | This ITP
6.2 | Compaction test frequency-Lots smaller than 500 sqm | VR 407.27 (b) (ii) VR 173.04 (d) | acceptance of the lot shall be based on the mean values of 3 individual tests. The lot will be accepted if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests. ATTACH: Compaction test results | Document Review | Each Lot Where Applicable | HP | Nominated authority | This ITP
6.3 | Surface finish and conformity with drawings-Surface Finish and shape | VR 407.29 (a) (i) VR 407.29 (a) (ii) VR 407.29 (a) (iii) | The finished surface of any asphalt course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks. No point on the finished surface of the wearing course: shall lie more than 4 mm below a 3 m straight edge For intermediate and base course layers: the distance below the straight edge shall not exceed 6 mm and 10 mm respectively. Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel | Measure | Each Lot Where Applicable | IP | SE/PE | This ITP
6.4 | Surface finish and conformity with drawings-Alignment and width | VR 407.29 (a) (iv) VR 407.29 (a) (v) | Where asphalt pavement is not placed against a concrete edging: the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside,from design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m. the width of asphalt layers shall not be less than the design more than 50 mm or greater than the design by more than 100 mm. The average width over any 300 m shall not be less than the design. | Measure | Each Lot Where Applicable | IP | Surveyor/SE/PE | This ITP
6.5 | Conformity with drawings-Scale A and Scale B | VR 407.29 (b) (i) VR 407.292 VR 407.293 VR 173.05 | the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.05 Number of measurements and acceptable tolerances are to be as per tables VR 407.292 and VR 407.293 | Measure | Each Lot Where Applicable | IP | Surveyor/SE/PE | This ITP
6.6 | Conformity with drawings-Scale C | VR 407.29 (b) (ii) VR 173.06 (c ) VR 173.06 (d) | the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.06 The level of the top of each asphalt course shall not differ from the specified level by more than 15 mm for intermediate and base courses and 10 mm for wearing course. For the purpose of this clause, the maximum lot size shall not be more than 4,000 m2 of pavement area. | Measure | Each Lot Where Applicable | IP | Surveyor/SE/PE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /