## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | bc3fee4f-78b5-4c73-b828-2e76f71adce9 |  | checklist | ITP-000 - Client Pre-Construction Checklist Rev1 | itp |  |  |  | Yes | ITP-000 - Client Pre-Construction Checklist Rev1 | 013df901-ba88-462b-a4ce-96b6beca5845
checkpoint-group | b6492295-6ed4-495a-bd21-df35abca0427 |  | section | Pre - Construction Works
checkpoint-status | d529dae4-6377-4d70-b519-375c6ec7635e |  | checkpoint | 1.1 Asphalt - submission of asphalt mix design
label | 6403505f-9421-5397-90b6-d633de760a07 |  | note | FREQUENCY: Prior to commencing asphalt
label | bd6b24c2-35c5-5382-ba9c-63a901207278 |  | note | ACCEPTANCE CRITERIA: Ensure the mix design/s have been registered and are approved by Superintendent prior to laying mix.
label | 250ee8c9-bcd4-5a5c-9348-5b817f679ea4 |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09. RAP DoT letter from production plant
label | 8a4f799f-4445-5900-8a18-39bf807a63af |  | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from the RAP DoT Letter.
label | 6d5f9939-30c8-5770-825c-f182f6dca3fc |  | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
label | ff8f73ff-650a-5ebb-bab0-c40db2c4eb17 |  | note | HP
label | ad2123b4-b412-5bca-8837-255087d448ab |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
text | 0ee839db-a922-56e3-9f15-0ced25e7bd8e |  | textbox | Date Completed:
holdpoint | 726cd246-a045-4012-aa01-ddbbb47df83b |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 8e4e382c-07ba-4615-9961-f58e03430d93 |  | checkpoint | 1.2 Concrete - submission & approval of concrete mix design prior to commencement of project
label | 23872242-d199-5a15-a9df-7dc9af723a49 |  | note | FREQUENCY: Prior to first concrete pour
label | d273ab31-e359-5638-9c04-60df69d3eaa3 |  | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
label | 490ea516-a436-53bd-85ff-40ca3a536e28 |  | note | ○ Mix shall contain minimum 460 kg/m3 cement content. Special 50 mPa mix is to be VS502B25MET1 with a suitably flowable design slump agreed prior to construction.
label | ce263cc8-5d79-5b62-baad-6c2deae4f9a1 |  | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 VicRoads Spec. Cl. 503.04
label | 36de6669-62bd-55d7-b959-2a291699bcb5 |  | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from supplier
label | 501c1abc-6064-5a9e-971d-b647b47d661c |  | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
label | 5a7b6fe3-1db9-5f56-9928-5d39976b9ec4 |  | note | HP
label | fd12675a-fc04-5e39-a0b2-2dcc47ea41d5 |  | note | RESPONSIBILITY: FH Engineer / Superintendent
text | 75a7f02d-ae64-52bf-8786-c540541da93f |  | textbox | Date Completed:
holdpoint | 62ce3754-f752-4f9f-84b8-4cd2aa90e8a9 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | eb939875-8c5a-4b03-92ab-eb05b48ff476 |  | checkpoint | 1.3 Welders qualifications, competencies & work methodology
label | ded92e7b-27db-5b38-ab23-f1d09f381c4e |  | note | FREQUENCY: Prior to commencing works
label | db6349e8-1bcb-5e38-804d-b776a0fed7ac |  | note | ACCEPTANCE CRITERIA: Weld methodology to be submitted prior to commencement of works.
label | c3e9a841-ebd7-58d8-828e-9a78c8fd4afc |  | note | Welders shall be trained and compliant in Australian aluminothermic welding competencies as outlined below;
label | 879ceacf-3751-516b-9bda-35fc30e43600 |  | note | ○ TLIW2012 Grind Rails
label | 513d25f4-2056-5ac7-9201-163768d73c7d |  | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
label | a90c514c-1242-5dfc-b57f-bdb85b776b94 |  | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
label | a240d510-a72a-54e5-bb99-5ddf48a5244d |  | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 Appendix C
label | f5202224-e935-5d2a-a431-4cddf31dddd4 |  | note | INSPECTION/TEST METHOD: Welding methodology
label | 3ad9c94e-bf14-5ae6-82b6-2610baa19ea5 |  | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
label | b68b56cf-eaa0-57e0-891f-5f785e8c79ba |  | note | HP
label | 0a8376e9-be3e-5f5a-8749-30761bb6bcad |  | note | RESPONSIBILITY: FH Engineer / Superintendent
text | 11052ade-feaa-5350-9892-61d75ff226f3 |  | textbox | Date Completed:
holdpoint | 899c0f79-5b72-481b-897f-97f43439ee49 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 72614640-4a73-401d-8792-97fb8044fbd6 |  | checkpoint | Final Inspection
label | 83cdff67-1bfe-5cce-b4c6-4a528886baec |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 2112aa52-4d1b-5b72-9706-2eae6e504f73 |  | textbox | Print Name:
text | eab52b7b-96ff-5757-a712-e0b2b5c3711c |  | textbox | Position:
text | 193fdd69-fb33-54fc-9286-03fcf6fb4ea7 |  | textbox | Date:
checklist-sectioned | ff5881f1-ce85-4723-8bd8-15bde7e3fee2 |  | checklist | ITP-019 - Line Marking Rev3 | itp |  |  |  | Yes | ITP-019 - Line Marking Rev3 | 0e607bae-efa3-4156-b48c-424de7182ec9
checkpoint-group | 28837b38-6de8-40c4-b7b6-d4fa601f12b7 |  | section | Preliminary Works
checkpoint-status | 3e0340ad-ba8d-49af-85b9-85961e9960da |  | checkpoint | 1.1 Check for correct documentation
label | 8da3f127-4e8e-52b4-a2b6-e7c1923e5f0c |  | note | FREQUENCY: Prior to commencing any activity
label | 0b38a5fd-ff8f-51b3-b18d-828a26204b42 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 531b499a-f298-5cb1-82e6-5825bb9eb44c |  | note | – using the correct and complete set of drawings
label | a64bcbce-814a-530d-aa3c-0df1ee4138d4 |  | note | – all drawings are the latest revision
label | 90ef870a-8b3f-5669-a350-18f25dff3a1a |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | a83f05ae-a39a-5cec-812e-20f5bb660cea |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 3bce68e4-f19c-59f5-a409-8761c7c20492 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 83e6547a-b1e0-59d0-b480-8b38473a9517 |  | note | WP
label | e072d5d3-734b-5069-8d2c-9b13acb37203 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1ad1a24a-0d9a-566a-804b-962541b0e4c2 |  | textbox | Date Completed:
checkpoint-status | 1deeaf3a-38d2-4247-aaaf-72bea456e958 |  | checkpoint | 1.2 Implementation of all measures and controls
label | eaba2dbc-4a77-5895-a7ef-d24206173f19 |  | note | FREQUENCY: Prior to commencing any activity
label | d19d9079-988e-511c-962c-512ac1224bab |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 848b838f-627e-55d7-95a1-7a95ad247903 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 5046df8d-eb04-594d-8d32-76b31c449a2d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7c94ec5f-3755-50a7-8169-ed9046754289 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 170e979e-5aad-5d14-bd7a-029af48399e8 |  | note | WP
label | a3d5fb8c-b7bb-5339-97c6-1eea1ad0ece9 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e6467bd1-2e4a-5842-a597-8c20e51f229e |  | textbox | Date Completed:
checkpoint-group | 936c9991-cb68-45ff-8701-de05ff3c90ac |  | section | Construction Works
checkpoint-status | be612767-80a2-4d68-9a0d-cebb86669b5f |  | checkpoint | 2.1 Setting Out
label | 2c709100-0a38-57c5-ab91-2610e0c5ef5b |  | note | FREQUENCY: Prior to start
label | 647b5997-c190-539b-a2e0-9e7b42b906c2 |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | 2f44313c-7a67-5fb9-8e91-943d59f11bf3 |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | eceeffe0-8a34-545c-a251-31a5c0f412f7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7e34c88c-c9c7-5ac5-9738-54900d0c491f |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 836f3c7c-90ea-50ea-abea-db19992ca39f |  | note | IP
label | 8e9bde68-ef6a-546f-aaab-ed52e0f8fd12 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 208b991b-527f-5b1f-9737-6f99321ab1b2 |  | textbox | Date Completed:
checkpoint-status | c85eb8ac-2b36-4c9f-8ebc-b83ae32eec0e |  | checkpoint | 2.2 Position of Markings
label | 54a22f7e-c4d9-509b-9d71-750b975d8a94 |  | note | FREQUENCY: Prior to application
label | 01f5b900-8e7f-5b68-ad56-a211f10b54a2 |  | note | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
label | c894dd33-5b2c-54a7-ab59-80aceb44a8e5 |  | note | ○ Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2.
label | 260f626e-22cc-5e66-a904-6bf0e53bb49f |  | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010,
label | 8525d927-6a72-53b4-85bd-686fc064dd1a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 7835fcb2-a752-5b39-a660-c7fc412a7ca9 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 6958322d-9c13-556f-8531-47ec5b438227 |  | note | HP
label | b7928d76-673b-52ef-b1d0-a236d64e1b10 |  | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
text | 3fb4084b-3be4-529a-89cf-4c1ed18fc4e1 |  | textbox | Date Completed:
holdpoint | 06d7e21c-57e0-479c-8529-08e6448f4b65 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 5f94ea83-01e7-498f-8a98-7e4fc2b51260 |  | checkpoint | 2.3 Tolerance of Pavement Markings
label | 65233e29-a2e9-5ae2-9ceb-def146b762cf |  | note | FREQUENCY: Each lot
label | 70fae0b3-005c-58c3-b4ab-8e450eb0e0e8 |  | note | ACCEPTANCE CRITERIA: The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings. The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
label | 00f15db6-1d0e-54c8-a892-56637e551084 |  | note | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
label | 32c07c61-26b9-5463-b55c-c2fb88a27f2f |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 5c8f4457-e7b0-5bcb-a060-34804302aee5 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 8916dfc6-8afa-5067-a8f6-44b284c24b7e |  | note | IP
label | 9ffc999c-53ff-532c-bd0a-447d41a54e2b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 02428ef3-d3de-52c5-9d23-7bd0c9c4036c |  | textbox | Date Completed:
checkpoint-status | ad401a23-7ed9-4365-9d17-ae607bcb47df |  | checkpoint | 2.4 Raised Pavement Markings
label | b2986c1c-b22b-5ade-97a6-8b3e8d674438 |  | note | FREQUENCY: Each lot
label | cd3a800c-31f7-5109-a8c4-9dd78f877cde |  | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
label | 4a210796-a415-5392-b834-2df1a6149707 |  | note | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
label | a99e62d2-bd76-53e4-a6d3-803b8447717b |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 8785ce5e-6ebf-5dba-bac7-c65aa5b26575 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0912629d-2343-5e38-b4bf-1aa4d43e8546 |  | note | IP
label | d7535ecc-243a-5bfd-a556-7e448bbc7429 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 92921fa0-2868-5e4d-93d8-fccf293277f3 |  | textbox | Date Completed:
checkpoint-status | e3032390-a45f-4c8e-b56c-d08959d27bc5 |  | checkpoint | Final Inspection
label | 3dca893b-bea7-5c5b-aab6-3535ddb2212a |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 61578cb2-3d91-52fd-a3ba-79bc465df419 |  | textbox | Print Name:
text | acbd2008-1364-541d-9131-5dd673955b05 |  | textbox | Position:
text | 53bdff53-593d-5f3b-9b1a-4ebf4b2e42e2 |  | textbox | Date:
checklist-sectioned | a741be33-0281-4739-b29b-8a9fa1dce8e4 |  | checklist | ITP-004b - Cement Treated Crush Rock Sub Base | itp |  |  |  | Yes | ITP-004b - Cement Treated Crush Rock Sub Base | 1c23921c-5c57-4532-9c97-08ab60fcf6e3
checkpoint-group | 901236b1-1d9c-4789-a1d4-767d626745f6 |  | section | Preliminary Works
checkpoint-status | 0ff4f73b-c535-42f5-bb71-97168f417d04 |  | checkpoint | 1.1 Check for correct documentation
label | d12096e1-8c76-5401-b475-985b54534cda |  | note | FREQUENCY: Prior to commencing any activity
label | 4b2368e0-84e9-5195-8ac4-40eae1210a0e |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and complete design drawing.
label | 7b612dd7-c96f-5778-b918-7b7940896924 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 401e67f6-205f-5089-9ebb-6c4f56e4d88d |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 1c8a8d4b-6fd6-5692-bb07-ca583c1c93e1 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4af501b5-9f75-5e92-a95d-473fcf181e81 |  | note | HP*
label | 4aef224d-dd5d-5577-9f57-24d15c557690 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e17a24b3-5fe0-5f01-815f-6f9f948d4bbb |  | textbox | Date Completed:
checkpoint-status | f104f13c-1eae-4cc7-86f7-d3427a854dde |  | checkpoint | 1.2 Implementation of all measures and controls
label | 9c79ec9d-86d5-51b1-89c6-67a2c6730e12 |  | note | FREQUENCY: Prior to commencing any activity
label | 58783c6f-ec62-5c9e-9d4a-724c0475d703 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | c379dfa6-6151-50b9-b9ef-1b6f0baf82d5 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | e009796c-41d3-5d17-b741-39b244e42d2c |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f1faef36-261a-52d5-9451-24322f9a074d |  | note | RECORD OF CONFORMITY: This ITP signed
label | 8a4073b4-c833-50b8-bf95-684eed43f552 |  | note | HP*
label | 6d87a948-b77b-5f65-b72e-7f4d270301c1 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c451660e-c0fb-557f-82a5-16130518f6e8 |  | textbox | Date Completed:
checkpoint-status | fde2450f-80e3-4492-823d-0c95673f03c7 |  | checkpoint | 1.3 Confirm CTCR is appropriate mix
label | 3ac19b09-a26b-5df3-891d-44193330279e |  | note | FREQUENCY: Prior to commencing any activity
label | 7fa92823-d1ef-52b1-ae9e-4d3db2ca6153 |  | note | ACCEPTANCE CRITERIA: Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
label | 852a5d46-759a-514d-8ff4-b2fd45b1f580 |  | note | ○ CTCR shall be tested in accordance with 815.141 by supplier
label | 503a77a5-a248-5ca9-9717-65bc9a1b2118 |  | note | REFERENCE DOCUMENTS: Design mix specifications
label | dd83abad-56f8-5e6a-bce6-e00f2f029795 |  | note | INSPECTION/TEST METHOD: Inspection
label | ff896bdf-a73a-5dc5-8165-f35447371b0f |  | note | RECORD OF CONFORMITY: This ITP signed
label | 64a57bfa-2cc6-5bf2-9e47-7993359ca42e |  | note | HP*
label | 2ac3fc4c-ee68-5c1c-9fe0-447ed859fc1e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 35d02a4e-ffdf-5c10-aa18-dbd4ab360463 |  | textbox | Date Completed:
checkpoint-group | d0f2d44b-ebc1-4691-a138-ec4cbdea8834 |  | section | Construction Works
checkpoint-status | 3fb69fae-a9f3-4706-8bd0-0fcbc8413e02 |  | checkpoint | 2.1 Sub base
label | 9bf06c5d-b70e-545f-b7cf-7b1e167dd7d7 |  | note | FREQUENCY: Each lot
label | 868285ad-d84f-53b0-91f5-862c9d4e55d1 |  | note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
label | da792e97-c83f-51bd-91be-a49601bade83 |  | note | ○ ITP-001 HP for subgrade inspection signed off.
label | 17c38e5d-d60e-5545-bce8-4dac83041c83 |  | note | REFERENCE DOCUMENTS: VicRoads 173.03
label | 53af0cfc-1cc6-5ef8-9873-504160c2c8bb |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | 4b71e28f-db23-5fe6-9f77-86f48a191c93 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 75dad20a-3f68-5156-92b4-c734eda72969 |  | note | HP*
label | ffb2db82-f8f1-5a57-abb4-922872b14b02 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 06aa9470-defe-5888-a62c-acab368486fc |  | textbox | Date Completed:
checkpoint-status | d7feae02-1467-482a-b5b0-b6f287b92a33 |  | checkpoint | 2.2 Moisture content
label | ae0fcd12-699f-53b0-8ef8-5a05448ebdb7 |  | note | FREQUENCY: Each lot
label | d8ad8efd-6e10-5cf5-b32c-ce9589d069c0 |  | note | ACCEPTANCE CRITERIA: Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
label | 3a5aeb7e-16e7-5bd7-8a87-72fce7997485 |  | note | REFERENCE DOCUMENTS: VicRoads 306.05
label | a6a4d263-115a-5bb8-96af-a418963a6de0 |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | 4d0c9b7f-022d-5db8-a93e-a0e8c86428a2 |  | note | RECORD OF CONFORMITY: Record of conformity
label | d15ba290-7d25-542a-8751-473a38cae847 |  | note | IP
label | 510889c1-01fe-5856-b12a-95dfec230eaf |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 955906a2-ed61-52ed-bb21-221882ec0b2e |  | textbox | Date Completed:
checkpoint-status | a431498d-2c67-4a76-901d-09ff56563848 |  | checkpoint | 2.3 Jointing
label | e95e3394-0184-55c1-81c8-1d8947631683 |  | note | FREQUENCY: Each lot
label | 5379fd23-c7bd-5a64-bade-945d687f7674 |  | note | ACCEPTANCE CRITERIA: Material shall be spread to minimise number of joins.
label | 4abb320e-fa70-5b82-b775-a6ec9848993e |  | note | ○ Transverse joints in adjoining paver runs shall be offsset by >2m
label | ab47456c-c1b1-5aeb-9655-e3cce36e244d |  | note | ○ Longitudinal joints shall be offset from each layer >150mm
label | 6488f076-163f-54ca-b8bb-08dc2f626bbe |  | note | ○ Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
label | 027f067d-72b6-5d10-9eb3-07a3d7e20047 |  | note | REFERENCE DOCUMENTS: VicRoads 306.08
label | ab14441a-62c2-5162-a52c-3f95164c252c |  | note | INSPECTION/TEST METHOD: Visual inspection
label | c0d3a1f6-69c5-5698-acef-fff02c1c6aab |  | note | RECORD OF CONFORMITY: This ITP signed
label | b7cd156d-b7ab-5376-8bef-7773c48d7cee |  | note | HP*
label | 550c8d0f-f236-5401-919a-91bd094e418b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8ee962ee-0baf-5e62-b442-5ce2c65f7f59 |  | textbox | Date Completed:
checkpoint-status | dd46f684-e364-4480-b93a-9770042abaa9 |  | checkpoint | 2.4 Conformity with drawings
label | f36f2830-b017-5347-bdda-bd09025a8a17 |  | note | FREQUENCY: Each lot
label | f8aeb92f-a17e-5016-9e03-7a611fe8b296 |  | note | ACCEPTANCE CRITERIA: Pavement sub base shall be finished to smooth and uniform surface
label | 7aa01246-a2db-5e2b-a30c-56fd29c5c6c6 |  | note | ○ Surface of sub grade shall not lie more than 12mm below a 3m straightedge
label | 2f229985-2097-578a-94ec-012451da6e10 |  | note | ○ Subgrade height shall lie within +15 to -25mm
label | cf59a02b-f0bb-5694-bce2-589d3da12b17 |  | note | ○ Sub base height shall lie within +10 to -25mm
label | 649c53dc-9176-5ce8-9dfc-30f351d48019 |  | note | REFERENCE DOCUMENTS: VicRoads 306.03, 306.11
label | f8ababf5-10ee-53d4-8227-5395b2740492 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 49bf5a8a-d437-5657-b0ff-7a15bfe83c52 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 3af332a5-595f-53b5-8a0e-00912abd9752 |  | note | WP
label | 54d24a85-47d6-5a6f-aef7-dfc1dfdc0232 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8b9229a6-4dc0-5a92-8122-99364c273870 |  | textbox | Date Completed:
checkpoint-status | 631d3288-8ee1-469c-8911-81dac82254a7 |  | checkpoint | 2.5 Curing
label | 6e420d8a-d715-5d93-a0e9-a116855414a9 |  | note | FREQUENCY: Each lot
label | 128ed410-4b64-5fff-a8ed-b05b7d718e02 |  | note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
label | b0c6ba44-ae47-5ae4-87f8-8c1e551d520b |  | note | ○ As per VicRoads, 4000m2 shall be maximum lot size
label | 8dcbe61c-6dae-5d41-90ac-bed858e3462c |  | note | ○ No trafficking before 24hrs unless approved by superintendent
label | d8ee0fcd-a881-5615-9940-71d5fbff6d5d |  | note | REFERENCE DOCUMENTS: VicRoads 306.11
label | 9b2e42e8-baa8-5abd-9f7a-546da416c92f |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 53505388-2dcb-5ffb-8e63-fb095a2a06f5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | e3d033b2-b820-5e10-8406-6ef9f2925f52 |  | note | IP
label | ba72616c-5439-58fe-a532-0c6500bee013 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 91f93bcf-c0f7-55a8-9a91-dbba61b867dc |  | textbox | Date Completed:
checkpoint-status | a4753fd2-d929-4ec0-bae0-a442c80794b1 |  | checkpoint | 2.6 Compaction testing
label | b3762a77-99f0-585e-8e6a-f7b4523cb3a0 |  | note | FREQUENCY: Each lot
label | 970f3388-2d6e-5c0f-9ca1-9138d569efea |  | note | ACCEPTANCE CRITERIA: • CT material shall be placed, trimmed to level and compacted within allowable working time (306.091)
label | 752a1e20-47ac-5854-888a-97dc6640eace |  | note | ○ At completion of compaction, any segregation shall be rectified
label | b32f0191-ade5-5de1-a6c4-3362efd050f4 |  | note | ○ >500m2 96% modified compaction 6 tests
label | 73ffd139-71ad-50f7-9ed2-0d39bbef771a |  | note | ○ <500m2 98% modified compaction 3 tests
label | 3c7830aa-8264-5799-91f8-1e6bfdeb2e8a |  | note | REFERENCE DOCUMENTS: VicRoads 306.09, 306.11
label | d2546005-9a43-5c72-a105-e100b775df49 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 34475396-50ed-556e-8a20-ac7003e43ea2 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 988959cf-f459-5adf-873a-4d6f9405f9fb |  | note | TP
label | 1d90fdde-1935-5a41-89f4-ea7d108f2fd3 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 489d506b-404f-54f4-9066-78e319927d31 |  | textbox | Date Completed:
checkpoint-status | 9bf94d4b-9744-41d6-ab3d-bce986c87efa |  | checkpoint | Final Inspection
label | fa24602a-eff4-5060-903a-59194273ce52 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | c6cd211f-3c4c-5877-b2aa-0cc5fc84290d |  | textbox | Print Name:
text | 8f23da70-406f-5d5e-a3f2-2237beda419f |  | textbox | Position:
text | d3926930-8516-5dc1-916e-9e361cab3f23 |  | textbox | Date:
checklist-sectioned | 055196b9-dfbc-4ebd-a694-3c24dc8fdd6d |  | checklist | ITP-002 - Feeder Conduits and Pits Rev2 | itp |  |  |  | Yes | ITP-002 - Feeder Conduits and Pits Rev2 | 3d1dec57-43c1-419e-87f9-75d7049c2256
checkpoint-group | 12d946bc-842b-41a6-85a7-0c2ddd21f39a |  | section | Preliminary Works
checkpoint-status | 614dd828-9b7a-42ac-baf7-4ce0df50bee4 |  | checkpoint | 1.1 Check for correct documentation
label | d6181e93-b181-56c8-b340-89dc6e16db11 |  | note | FREQUENCY: Prior to commencing any activity
label | 0b09676d-e770-5b5c-b07d-0fbe91d8727f |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 0c5c3522-23be-5367-bf27-7ea321a53009 |  | note | – using the correct and complete set of drawings
label | 77598745-e705-5e56-8311-bbf4cef87fa6 |  | note | – all drawings are the latest revision
label | 0da2105d-33c3-5f2e-8f57-f9118ccd05ed |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 8aa40b2f-44fb-5713-9388-aab23fece5ac |  | note | INSPECTION/TEST METHOD: Visual inspection
label | a8239e5c-3826-52da-9a27-83f66faa6664 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 8a5444f4-0900-5580-ab2f-f2f8c30e9bd0 |  | note | HP*
label | 5b8c2047-7da6-5bc5-bd94-f41e9c2e033d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 08ff088f-6275-510e-b100-25e438c40601 |  | textbox | Date Completed:
checkpoint-status | 0e26d356-87c6-4168-9162-55d16a66dc7f |  | checkpoint | 1.2 Implementation of all measures and controls
label | b5c608bc-0e0b-5615-8e60-92786a55edc6 |  | note | FREQUENCY: Prior to commencing any activity
label | 8f7f6a82-dab1-55a9-9e97-33195757431e |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 37da78b1-e395-5c36-9425-6bef8875cc1b |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | b0c92033-6aa4-5554-9bba-67d2fa6d827d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 87a37078-d318-57a7-91b1-fe448fb9a94d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c17d1c67-4b21-5ef1-b026-8c2fc9d6980c |  | note | HP*
label | c90b7dda-6ffc-54ab-b18c-e10e5e93c230 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 3e778fbb-ea2f-58c5-904d-0fe6e6a25f59 |  | textbox | Date Completed:
checkpoint-status | 2d1186f4-b5f3-4c73-9c12-197b14037eaf |  | checkpoint | 1.3 Materials
label | 084f61e9-8a32-5591-aea9-ad1114369326 |  | note | FREQUENCY: Per batch
label | d2d4b3e8-47d7-55b3-8385-050fb99909a9 |  | note | ACCEPTANCE CRITERIA: • Electrical supply conduit to be orange. (Heavy duty 100mm diameter UPVC)
label | 4de65465-3944-5a19-a71e-9e30c224515b |  | note | ○ Modula Stakka pits to be used for feeder pit, entries for conduits to be cut with hole saw.
label | 9899e7d6-24ca-508e-9619-16407ddfb05f |  | note | ○ All pit covers to be class D or greater and installed in accordance with manufacturer requirements.
label | 970b0a7e-8f04-5de3-9671-30a180705cd7 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4 AS 2053
label | 05ef29c7-118b-5ccb-a987-1380e40b873b |  | note | INSPECTION/TEST METHOD: Verify
label | 22db3705-fcf8-5bd0-8b74-e4eb98c9b474 |  | note | RECORD OF CONFORMITY: This ITP signed
label | e9426c0f-5909-5698-9878-28b14595bc27 |  | note | HP*
label | 209067df-0d5d-512a-8a46-df6754629147 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | d9c7033f-9e6f-5f15-8bd8-07ae71c76998 |  | textbox | Date Completed:
checkpoint-group | f901e7f3-746c-4b9a-8f40-2cc8dea8b09c |  | section | Construction Works
checkpoint-status | 3c310fce-e2aa-401a-9647-89ec304cf784 |  | checkpoint | 2.1 Survey set-out
label | aba8a7c5-f24a-54cf-aaa3-9973b8a02286 |  | note | FREQUENCY: As required
label | 5b94d276-6ba1-5de4-9076-1ba666b03d6a |  | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
label | 0ea7012c-c600-5400-9c7b-d56b9e230e2b |  | note | ○ Ensure that pits are placed as shown on drawings and shall align with overhead poles which are suitable for connection with infrastructure from pits
label | efacd21c-1eac-5d64-8a19-e9c5e3108c5d |  | note | REFERENCE DOCUMENTS: Work procedure
label | 3f00230d-8f61-51ed-a194-eff80c48d341 |  | note | INSPECTION/TEST METHOD: Verify
label | 8c5b01da-ec6f-5a05-9313-48c8a063f958 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ce0fc213-ab74-5fad-a7fe-98abb5a28d3b |  | note | HP*
label | 45003f71-ed5e-5cba-8746-1911231a9283 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c1c95336-1713-5a7b-b675-72f4cf5f96be |  | textbox | Date Completed:
checkpoint-status | d98d8973-2158-454d-9b18-712bab58e35b |  | checkpoint | 2.2 Excavation and trenching
label | bcff69db-df3e-5608-a44f-44453a3d4129 |  | note | FREQUENCY: Prior to installation
label | 93a453a1-182d-50dc-8a4b-38455b53b978 |  | note | ACCEPTANCE CRITERIA: Minimum cover for underground conduits shall be 600mm
label | edae2ed5-f6ad-5960-b8ad-db695c9097e5 |  | note | ○ Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
label | 00bd9ddf-eb9b-55d9-9dfc-751c7aef5fcc |  | note | ○ Trench shall maintain a minimum clearance of 300mm from all existing services where possible
label | a90e7228-0dcb-5850-a407-9d2bff216a1a |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
label | 113d0b70-61e3-5732-9f30-18bc5b444225 |  | note | INSPECTION/TEST METHOD: Verify
label | 2a081e03-6a88-5c6d-86f2-a88b69479177 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 58b97eb8-f265-59c5-afd3-cd2f67aff3d4 |  | note | WP
label | b7d299ad-8dc9-5523-a160-36447a18792e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b268fbaa-10a1-514f-b172-8d6827a241e3 |  | textbox | Date Completed:
checkpoint-status | eb5c9a2d-56d8-42f9-9e10-556416645cb5 |  | checkpoint | 2.3 Installation of conduits and pits
label | a8f514f7-bb95-540e-8dee-d737cf9371e8 |  | note | FREQUENCY: Each lot
label | ed864ac0-7951-5c97-9182-a5b3a1a17c3b |  | note | ACCEPTANCE CRITERIA: Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
label | 6784d4fc-3c0d-5df6-a565-55a7c68ad739 |  | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm sand
label | 7247cda3-a1e5-522a-88fc-7cfd710b3b91 |  | note | ○ Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
label | d68a57bf-f29b-58c8-adf8-4790d594298e |  | note | ○ Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
label | fd81c851-6b49-524a-8dec-f765abeae319 |  | note | ○ Conduits shall not be subject to construction loadings
label | 56e38c26-9fdd-5255-92c5-9f7a4ffb2063 |  | note | ○ Pits shall be constructed as to allow for class D rated covers
label | c0955d76-443d-556f-910a-714cc4939935 |  | note | ○ Conduits shall be placed a minimum of 100mm above pit floor.
label | 3502e70d-f5a9-53ee-90c0-902d0c3e5dbc |  | note | ○ A 50mm gap between conduits shall be maintained as they enter pit face.
label | e6423fab-6b41-50c6-ade5-1738637b4846 |  | note | ○ Conduits exiting the pit as 'stub ends' shall extend a minimum of 50mm beyond the pit face and shall be fitted with a spigot end and capped with UPVC electrical caps to prevent contamination to internal surface.
label | 212137c3-f559-5ab5-a5e8-c13780e80766 |  | note | ○ Conduits installed for future connections shall be installed to the track margin
label | f348ea8e-bdac-5702-ad41-b0cf1e26af07 |  | note | ○ 100mm of concrete around and under pit lid to be installed for structural integrity
label | 17803227-e37c-50a9-83d5-a5ba3c065405 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
label | e943a0f7-9997-58b2-97ce-ce37c9c0feb0 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 785fe686-0a62-5f34-b016-5140a64e20a3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | a6ae879d-4451-5d65-aa2f-3417ac9b2e7a |  | note | WP
label | 77ac8ec7-da0e-503b-b852-d3f8ff6e3fe2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
text | 9b161e7b-28c4-5df5-98ca-317f38cecafc |  | textbox | Date Completed:
checkpoint-status | e19c2e84-057d-4cf4-9565-a971d579db95 |  | checkpoint | 2.4 Inspection of conduit installation
label | 018bb72e-be33-5191-98af-b36f072656df |  | note | FREQUENCY: Each lot
label | 49566cb3-43a5-5045-9304-598dbf1bc441 |  | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspected by superintendent and conform to design drawings before any backfilling is to commence.
label | 6f1dbb3a-7a2c-5d87-99a4-50ee09a5abcf |  | note | REFERENCE DOCUMENTS: Work procedure
label | 5200da55-fac8-5eeb-97e0-e0fff58c6800 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9ad7bf84-dcd5-563a-a77a-4c083d0d3bf7 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | a4e9eb40-46fb-55c5-aab5-40f9614d3aa2 |  | note | HP
label | ce97e41c-5e44-5bc7-8187-d97d1ac67845 |  | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
text | 958eb464-afdc-516c-a257-2bc2315fb9d3 |  | textbox | Date Completed:
holdpoint | eb37834e-4e35-4470-a802-13f3f1cb8122 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 5c8c1afd-a345-4a65-a8ef-3d1b4db37aaf |  | checkpoint | 2.5 Back fill of trenches
label | 7bcd64d2-6c7b-5718-9dc5-0b9aab4d79aa |  | note | FREQUENCY: Each lot
label | 279841a6-dbf0-5118-932b-32fb8093e27d |  | note | ACCEPTANCE CRITERIA: Backfilling (only to be used for road crossing trenches)
label | 62c85111-58ec-5cb2-989b-4f7c9eb89035 |  | note | ○ Conduit trench shall be backfilled above marker tape with crushed rock or suitable material and compacted to 90% standard compaction 150mm- 200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction
label | 8d5b4f19-fb73-55d4-a260-ed93188ca64d |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
label | 89f7ddfb-6106-5df3-95b6-e60fa97e858f |  | note | INSPECTION/TEST METHOD: Verify
label | 1561d260-67d3-5c98-8510-f22e55a74a2b |  | note | RECORD OF CONFORMITY: This ITP signed
label | 9b63e10b-09a7-5aad-8045-40b1ac1cf317 |  | note | WP
label | 2092d0e9-eb73-5aa0-8bc4-8cb6241a661a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 00f2b12e-0f15-5ea2-97ba-8b37c086593e |  | textbox | Date Completed:
checkpoint-status | c506b850-e744-4837-88fa-0cbeb52adce8 |  | checkpoint | 2.6 Installation of draw cords
label | 8a7ebad6-ee54-5709-b8c2-fea952bd5002 |  | note | FREQUENCY: Each lot
label | c331f7c4-5037-588b-92a9-f3527d1b23e5 |  | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit. Material shall be 6mm 'telstra rope'.
label | d1aaf589-664d-5ff1-918b-e710921d9a72 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
label | d97e46b2-a545-5944-b659-3d3401dc5de2 |  | note | INSPECTION/TEST METHOD: Verify
label | fc4be3cc-f5de-509a-ab4e-cea8ead06489 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 950b4078-9bc2-5f98-9986-a02924084b77 |  | note | WP
label | d1368411-b442-5240-ab30-a4ef506441e2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a814ef66-bb03-529d-a175-6d57ec9a30e6 |  | textbox | Date Completed:
checkpoint-status | b84038f1-e933-45b4-8dd0-fdb6d933cd7d |  | checkpoint | 2.7 Compaction
label | 8c3928af-ad63-5e8f-9740-53333a166090 |  | note | FREQUENCY: Each lot
label | 89489a74-83b7-58cc-b9fe-799a7ad4a003 |  | note | ACCEPTANCE CRITERIA: Bedding and backfill material to be compacted using mechanical plant During compaction optimum moisture content of bedding and select fill is within 85% to 115%
label | 1d6bd3d6-cd9c-541e-a295-c681cdcd096c |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
label | 479418a7-d08a-54b5-93f1-a17b21f3143d |  | note | INSPECTION/TEST METHOD: Verify
label | e4de42f3-b69a-56be-a35d-8999ba989962 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 14c6b332-c6db-545a-b9f4-54cd3b55a104 |  | note | IP
label | ff17e45c-bd08-557b-b81d-284515eb9a32 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 9aaf092f-a5ae-5246-982b-abf4c16fceec |  | textbox | Date Completed:
checkpoint-status | 2a339321-a6e8-4f03-b268-11103eba552f |  | checkpoint | 2.8 Feeder pits & pit lids
label | b9439572-4410-5e84-a9a9-f95e92d3f1c6 |  | note | FREQUENCY: Each lot
label | dffd12ae-3ac7-5ae9-bb36-51ad181c9aa8 |  | note | ACCEPTANCE CRITERIA: Feeder pits to be constructed and installed as per drawings
label | 5f5e9d39-c9b9-50a2-a303-b70f3822bb53 |  | note | ○ All conduit connections to cable pits shall be neatly made and ends of conduit trimmed off and the area between the conduit and pit wall stopped with cement mortar.
label | 62075198-40ec-5047-b3fc-f824541b9ab5 |  | note | ○ Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
label | 47fc9658-ceaa-573f-b87f-f604745264ba |  | note | ○ Gatic pit lids shall be filled with structural grade concrete.
label | b5260a49-7918-524a-a36d-ccb668bbee23 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.7
label | 439f2908-f70d-50d6-9d6b-f95f3d9c391b |  | note | INSPECTION/TEST METHOD: Verify
label | d2c9184c-23e1-5e7e-98ce-0f66e82d8ed0 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1815a698-870f-5209-9282-55dc49f9a8bc |  | note | WP
label | ce7f2845-db7e-5e17-a654-35f6d703499e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | dd3d3511-40d1-5941-8a30-b414fdfb81a9 |  | textbox | Date Completed:
checkpoint-status | 8b4cdf82-472d-4ee6-922e-6e20c35e6ba0 |  | checkpoint | Final Inspection
label | 9ec470d0-7dc7-578b-bfb8-f317013ae868 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 705304a8-e641-5935-bd1f-8c98f44bb8db |  | textbox | Print Name:
text | dc6e6b3d-863d-5f25-be75-39f6b50f3546 |  | textbox | Position:
text | a780e70d-70fa-5146-bae9-a011e9cef394 |  | textbox | Date:
checklist-sectioned | 54c0101e-d37e-4ea4-a307-b1f69e19a813 |  | checklist | ITP-007 - Concrete Track Slab Pour Rev2 | itp |  |  |  | Yes | ITP-007 - Concrete Track Slab Pour Rev2 | 5cce70ce-7b52-425a-8bf3-3691c4e166dc
checkpoint-group | 4d10432b-420d-4008-81ee-55cbb9bea153 |  | section | Preliminary Works
checkpoint-status | 99ad0882-1e94-4f97-8267-1ba28149aac5 |  | checkpoint | 1.1 Check for correct documentation
label | be57b85e-07cd-5324-b9b4-38d3f84f3ce7 |  | note | FREQUENCY: Prior to commencing any activity
label | 1ed56570-7852-5c40-8aef-f69074edcac2 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 52264034-d7f4-5859-a157-7aa0af8b41f2 |  | note | – using the correct and complete set of drawings
label | 1de04f5e-5b2a-5897-b0a8-043aa8d2e029 |  | note | – all drawings are the latest revision
label | 19b46163-8ea0-580d-a643-3eaba8365b25 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 44e7c93e-036f-5329-a8f2-b62ef6512720 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 46778201-7931-5b16-bf65-b5e017cf89d7 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | dfe520f2-e11a-5525-bbe6-caeca3884456 |  | note | HP*
label | c13e8a5b-7ad7-5342-8f00-22b8b6c10ede |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 0d1a3646-e9c2-59fd-a067-03d863e3fcc4 |  | textbox | Date Completed:
checkpoint-status | d08e9635-323e-4f41-95e6-8469f680d5ce |  | checkpoint | 1.2 Submission & approval of concrete mix design prior to commencement of project
label | 97d8aa35-cafc-570e-9ba6-e62451524917 |  | note | FREQUENCY: Prior to first concrete pour
label | 2b61859f-e766-5541-9d37-0bbfc5bd3829 |  | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
label | 4dd8acc4-831f-52dc-a06d-80a754e179b9 |  | note | ○ Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
label | 4b1aa988-2197-5f61-a4f1-29ec162ee266 |  | note | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 and AS 1379
label | 5287c6a5-ddb9-5f2f-b225-408303e61c22 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | 890dd6f1-3858-5519-9a8c-27098c9dfc3c |  | note | INSPECTION/TEST METHOD: Verify
label | 8cd20c41-85d3-5e1a-8b0d-e5edd810b585 |  | note | RECORD OF CONFORMITY: Mix Design ITP
label | fa2f21f2-084e-508a-90ee-e6f4bc2c0330 |  | note | HP*
label | 8ab23562-6621-51c4-b026-99cfc2ca9783 |  | note | RESPONSIBILITY: FH Engineer / Superintendent
text | a2836b95-d5f9-519c-bd3b-22a59fe6a28c |  | textbox | Date Completed:
checkpoint-group | a341568c-5668-4096-b955-55273f11dab2 |  | section | Construction Works
checkpoint-status | 099d611a-bec0-401c-b88f-4cde6d91062e |  | checkpoint | 2.1 Weather monitoring
label | 0bdc6273-4fee-5666-9b2e-4975ee81397c |  | note | FREQUENCY: Prior to start
label | 09aeb4fc-39fe-5e4a-b2cc-46ec4004df8c |  | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
label | e9c65360-13d8-5b1e-8bdc-d1e00cf85fa8 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
label | 39667d7e-cb53-5c8a-ae30-e74a51d052d0 |  | note | INSPECTION/TEST METHOD: Verify
label | 107c0a39-e787-59bc-b9f8-32fd17016b01 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | dc50fbe6-e27e-5f8d-882d-af6723a3d454 |  | note | HP
label | 9a6188a2-db2a-582a-b06d-55fd050aea3e |  | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
text | b5d8d0c9-588d-5da3-9dbc-7965cf70a5bf |  | textbox | Date Completed:
holdpoint | f5043892-02b2-46cc-bde3-c3f193f7d042 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | fe312294-a4c0-42d4-85cf-a9164f410f16 |  | checkpoint | 2.2 Surface preperation
label | ff9a3064-e80b-52eb-9a7e-23a5708490bb |  | note | FREQUENCY: Prior to start
label | 93140c4e-5afa-512b-b395-af949803d52c |  | note | ACCEPTANCE CRITERIA: Crushed rock surfaces shall be moist and thoroughly cleaned of all foreign and loose matter prior to pour
label | f0ac1ee1-8566-542b-bc65-130b25c6e848 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | ff931bba-fea2-5393-81b9-f7546e4bc882 |  | note | INSPECTION/TEST METHOD: Verify
label | 30fec05f-2358-55d5-9d72-a372ec383e05 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 5a51cfc3-d7af-5fa1-acf2-b3ba0da2ba0f |  | note | HP*
label | 3adbfa92-b2da-5611-acd4-43f9bebf1541 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
text | 036e6302-67f1-5a64-bb72-36903122552e |  | textbox | Date Completed:
checkpoint-status | 30014955-9f78-4fec-81e7-bad3c26f6e20 |  | checkpoint | 2.3 Setting out
label | 9762b71f-7606-5d17-8021-efecef536d7d |  | note | FREQUENCY: Prior to start
label | 991a1879-dc2f-5d68-9af2-2d960e070acc |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications.
label | cfc40e49-89f4-5cf5-9b21-8ef0decee7ae |  | note | ○ No survey/level pegs to be removed by any persons until completion of works.
label | 0ec1afcc-266e-58e7-ad77-34d1977e02a5 |  | note | ○ Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
label | 65843e54-15cd-5e7a-9fd1-7f26c50abb94 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | eabe821f-3d1f-5908-933b-6bac673aa0ba |  | note | INSPECTION/TEST METHOD: Verify
label | fdd9443a-e5c0-5c76-a9f6-0450507766f6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | f9454d44-3cd0-5dea-a3ff-0c688ffd5ece |  | note | IP
label | b0c14e94-d235-5bbd-89c1-b26c7c9272dd |  | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
text | 928db1d2-62ad-5a2f-89a7-f8d85afa70ff |  | textbox | Date Completed:
checkpoint-status | 5d563f7a-ae13-47bd-816a-cf113a940f79 |  | checkpoint | 2.4 Formwork
label | 348d83eb-a3ad-5ec5-ab83-47db4e8c0fa6 |  | note | FREQUENCY: Prior to start
label | 5891e126-d586-559a-b2d1-2b7ce2f84e0d |  | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
label | d8909aef-c57d-5fd3-b528-f1a689cdb335 |  | note | ○ The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
label | 6299f933-a6f6-5519-a760-9b344c6dd734 |  | note | ○ Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
label | 818330ba-c2a2-5063-bfae-0e94c1a614e1 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
label | d7da653f-2d9d-5fec-825c-fc20ed6e50f1 |  | note | INSPECTION/TEST METHOD: Verify
label | 6528cc26-d6ae-5b58-b0fe-1585e46f68a4 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 78a25aaa-4566-5fbb-a85f-804b4e595029 |  | note | WP
label | 3324c1f8-99a5-5d2f-8cf5-eebeb048c29d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 218d1dea-e978-55e5-bb96-d324e501d233 |  | textbox | Date Completed:
checkpoint-status | 59b44e30-bec8-46fd-a489-0104cc6ccc51 |  | checkpoint | 2.5 Reinforcement
label | 3d626ad0-9012-50f0-be5c-4c94df51cfa8 |  | note | FREQUENCY: Where Required
label | 5f443d97-d91f-51d5-a22d-719b10872c2f |  | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
label | 211e436f-4e9b-5d1c-8cd7-5fe4f8941a67 |  | note | ○ All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
label | c5bb4869-ead9-53f7-a6da-d31d06a6f15b |  | note | ○ Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
label | ed87f936-6910-5a3e-ba46-a70cce7d7847 |  | note | ○ Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints. Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
label | a73c0c35-29fa-5100-87ee-620da7b10bdd |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
label | aa4a7588-b890-5ecb-8c5c-31d1e27c48ee |  | note | INSPECTION/TEST METHOD: Verify
label | 7f293e8d-4074-536a-a88e-fb2698edf40b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 01310bf2-8611-5c42-8c63-6fbc81fe2b6c |  | note | IP
label | 2bb8c132-10ca-50ab-9efe-52485071d580 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | bd07a06e-807b-5cfd-8558-436a933aa9b8 |  | textbox | Date Completed:
checkpoint-status | eed7952a-76f9-4967-a719-cb03ac16edfe |  | checkpoint | 2.6 Dowels
label | 480af2ec-240c-59bd-8a58-5507254db535 |  | note | FREQUENCY: Where Required
label | 56d71ccc-fb74-56d4-a76c-7eec4434932f |  | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
label | f1701ee6-9c5e-5c4c-978b-0830bc9d3667 |  | note | ○ All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
label | 1a7d0f74-056d-593d-8d81-306655742144 |  | note | ○ Dowels shall be clean and free from mill scale, loose rust or oil.
label | 1d58aa87-e29f-5aad-bc35-14d88eab4190 |  | note | ○ Ensure that all dowels are securely held in their correct position until the concrete has set.
label | 2971733b-be01-5ebd-a405-f1993901c397 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
label | ff33ccf8-0acb-5ab2-b720-a7bd1912b601 |  | note | INSPECTION/TEST METHOD: Verify
label | 0ded8f1e-1638-5a3e-824a-2392189e9ce8 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 2ca6a1ad-b3d8-5ac2-a8ff-be806776703b |  | note | IP
label | 988956b8-e88f-571c-bf65-9ee7491b9c29 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ce52aff9-e4a5-5c92-9288-10ab7ca24c2c |  | textbox | Date Completed:
checkpoint-status | 5764187f-e98a-49bb-a750-4c56047cef24 |  | checkpoint | 2.7 Pre pour inspection
label | 9b53340b-f6b1-533d-ab92-4f3d2946e29a |  | note | FREQUENCY: Prior to start
label | a8119398-eefe-500f-ab81-d7070fd238c8 |  | note | ACCEPTANCE CRITERIA: Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
label | 5de3a1d9-aa0d-57a5-a6a0-e1b5a7dc82e7 |  | note | ○ Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
label | 339535f0-08ca-57ce-85de-a3c1ac544424 |  | note | ○ Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
label | 45181c2b-ca98-56cd-8d31-c762fc79726d |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | a22e65ca-08e9-57ae-b152-52bbb5349832 |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | 847608aa-7da6-5218-8cd3-c43d70fd6a6c |  | note | RECORD OF CONFORMITY: FH Track Inspection
label | 27b55393-a075-5e11-bbd3-842adb3b0798 |  | note | HP
label | 4ef0c3f6-635b-5397-9760-98d8f2af6210 |  | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
text | ea9e049a-cdb3-564f-ab17-ee7f76748dc7 |  | textbox | Date Completed:
holdpoint | b365255a-cd91-4d2d-b5b8-2b2b16fd7e76 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | f984d063-2aba-44b1-9c85-2827e8d16819 |  | checkpoint | 2.8 Carry out sampling of concrete
label | 7573d2a6-bd8e-5300-90f6-7d2fffbb4038 |  | note | FREQUENCY: Each concrete pour
label | a43777e9-6e60-51ad-bb9d-ae5683f93be5 |  | note | ACCEPTANCE CRITERIA: Slump:
label | dae3c41e-688b-5651-b4d5-c4c4d6fb8175 |  | note | ○ Concrete Slump shall be 100mm +/-20
label | 5f2778cd-f29d-54c1-8f11-33581f6c060a |  | note | Compressive Strength:
label | 88f5e201-e234-5722-9eaf-70d6b5fa3fb6 |  | note | ○ Shall be measured in accordance with CE-019-ST- 0033
label | 5bc9093e-b3fe-5aba-a881-3c958555140d |  | note | ○ Testing frquency =
label | c684d4f2-0d4d-5054-9a22-2675cfd76234 |  | note | 0-50m3, 1 sample
label | 3ac002b8-cf79-5177-a28a-120163756cef |  | note | 50-100m3, 2 samples
label | 092c13e3-bbd1-5f0b-b100-a10b91921b18 |  | note | 100m3+, 3 samples
label | 6208978a-413b-5762-9834-63c5bfaa02b9 |  | note | ○ Each sample shall consist of 4 cylinders
label | a03236ee-c184-5ed6-902b-24a859a9428f |  | note | ○ Test Results will be provided to the Superintendent
label | f728e86a-dc4e-5bf7-a6de-6fc543c9e06a |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 and 4.7.18.4
label | 13cc6f71-6ac6-5bf4-9514-1bb8c83b7948 |  | note | INSPECTION/TEST METHOD: Verify
label | 334ac0ef-b482-5029-bf47-b2a78bae8177 |  | note | RECORD OF CONFORMITY: Concrete supplier test sheet
label | 9ce7dc71-7e39-5dfd-944c-367aa0c5fae4 |  | note | TP
label | 30183e9e-b655-5beb-9162-53167176131a |  | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
text | eddafe42-a84c-5e2f-843a-796f855d7536 |  | textbox | Date Completed:
checkpoint-status | 2ed0c948-fb0c-4f01-a67a-0eaf20d2801c |  | checkpoint | 2.9 Concrete placement
label | 7e439bf1-63fd-55a7-8220-350df80ebcc4 |  | note | FREQUENCY: Each Lot
label | 7e4c55f1-5ffb-50e4-aee4-1674546a2386 |  | note | ACCEPTANCE CRITERIA: Ensure formwork is clean
label | f6fe3199-fe99-506b-b611-702b6e2fa1f3 |  | note | ○ Concrete shall be entirely discharged 60 minutes after batching,
label | 30e05be1-3668-5561-ac2e-a28ef3aa37d3 |  | note | ○ Ensure that pouring does not occur from a height greater than 1200mm
label | 9978df4a-72ca-569b-87d8-8afe188c4bc1 |  | note | ○ Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
label | e11974de-7d94-5b46-9897-85c5d62ee04c |  | note | ○ The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
label | af9e8af0-a97e-5806-8366-e108f0dcc5fe |  | note | ○ There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
label | 67242f24-2572-5f28-a594-d30b1ea4b6ec |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
label | 34857fbe-0b70-5705-ad5d-0b667a414136 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9df2aa3c-b61c-513e-97e7-e113d04e4c7c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 0362c722-0148-5798-9962-c6a592e583bc |  | note | WP
label | 59266f34-b235-533e-9a4a-eeff1b574a7f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e841b855-86d1-5ab2-9219-d2ffac9dfdf4 |  | textbox | Date Completed:
checkpoint-status | 4b18dbb5-8116-48c3-bc20-5550dcb71078 |  | checkpoint | 2.10 Compaction
label | 9027161c-0cde-5d4c-8e37-f4f5a76be7d4 |  | note | FREQUENCY: Each Lot
label | 58c30cc5-4099-58fb-942c-8a9c72cec781 |  | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
label | fe71b8dc-fcea-5053-aa5d-f1129e752561 |  | note | ○ Vibration shall take place until exposed concrete surface is free from air voids
label | 4e6b4699-6653-56eb-aa25-43f2fc0f40e0 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
label | c7373958-5551-5817-ab09-7f97db5ef2b5 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | df912d01-68e1-5ce8-aba6-cd53a3ef4e61 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 3f5648d8-b3ee-54ff-ac72-e8426f4f989f |  | note | IP
label | 2dabc8de-6d1e-5e76-8da3-9f4918a8ad0c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 5a10843e-744b-5398-b316-c15939b836fc |  | textbox | Date Completed:
checkpoint-status | e8f1981d-bf3f-4956-b3ce-aa256883dd7a |  | checkpoint | 2.11 Record location of each batch
label | bde88345-c6f9-594c-982f-4a839395c783 |  | note | FREQUENCY: Each concrete pour
label | 2068d813-b264-56a5-b38e-bfcf4752261a |  | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
label | 1835b7b0-e6ee-58c3-9e43-6cdc4fd7d0c8 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | 75c78586-3700-52d6-8d59-878143f40416 |  | note | INSPECTION/TEST METHOD: Checklist
label | ba22f7f3-b1c1-5757-a41f-194144bf56d9 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 7648739c-4179-5b58-9e94-f37ae4d9365c |  | note | IP
label | 4e3ce116-06c5-5ea7-be9e-1d087b90df4b |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 6db32102-6ffa-58a8-85ee-4efef8f460b2 |  | textbox | Date Completed:
checkpoint-status | 38d2d068-48e6-44e2-aa9c-60a31dd280c1 |  | checkpoint | 2.12 Curing
label | a3476e29-cb49-546c-bd43-7663a2db0ce7 |  | note | FREQUENCY: Each concrete pour
label | d8d19c6f-44f5-50dd-be2f-c2e4a68d3783 |  | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
label | 6568baf1-5ee1-5887-9306-c451e8cf6ea0 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
label | c51c3db2-0023-59e1-a7b5-79e74f089249 |  | note | INSPECTION/TEST METHOD: Checklist
label | 8156a8ba-ba5a-5f38-bef0-863e8c4e8955 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 506bebde-bc3b-53c2-9ea4-9e92e3fd0196 |  | note | IP
label | 24c22fbe-1e51-5060-b762-feb439669a78 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 31d6297a-f9f5-5723-bb2c-8ef89dea998c |  | textbox | Date Completed:
checkpoint-status | 98302658-6677-44d5-a690-9d6fd3180189 |  | checkpoint | 2.13 Tolerances
label | 47257178-5cf6-53af-89d5-e1fefaba8d17 |  | note | FREQUENCY: Each concrete pour
label | a373f0e5-6279-5405-8828-5d2ff3384cda |  | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
label | 752ea9d5-469a-5738-9fe6-a45a0449e05c |  | note | ○ Plan dimension of slab +10,-10mm
label | 2fa0917e-549b-5cb0-ab91-4a9593e0a41f |  | note | ○ Thickness of slab +10,-10mm
label | 62debc58-b679-57fc-8ebb-04a583cd3681 |  | note | ○ Cover to reinforcement +5,-3mm
label | 49f024a6-0bb9-5222-b895-9deeef1b65ea |  | note | ○ Finished level of slab +3,-3mm
label | 0139beae-79d8-5995-b8b8-a601cf3df6ed |  | note | ○ Foundation level of slab +0,-20mm
label | 3ea098ac-21bb-5b7f-884f-9af3d100b0e3 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
label | b82c4649-e624-5bac-a092-743d7336753c |  | note | INSPECTION/TEST METHOD: Checklist
label | f1449a08-cc91-53f4-bb1a-a3a36d54acd6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | e5df1433-d45d-56b7-bf58-fab64dc93bf0 |  | note | IP
label | 766adc74-0dd8-5815-a893-a859504ff028 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 13ca8f16-fd14-52ee-99af-e1bafe856e3a |  | textbox | Date Completed:
checkpoint-status | 483f6f0f-e413-45c6-a54f-86d3e2e38243 |  | checkpoint | 2.14 Slab finish
label | bf2f787f-8a08-5cce-8eb9-c0634e963126 |  | note | FREQUENCY: Where appilcable - if track is Type 1 structure
label | 4d63485b-3031-5d68-9651-41a36c9ddad0 |  | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities.
label | 2835f402-13d6-5d2b-94de-5e5062345626 |  | note | ○ All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
label | bcd94fd5-c6f4-5033-a1fd-4a0cc208486c |  | note | ○ A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
label | 2ea634b4-1b9e-5568-8e7e-e0c997f1c5b9 |  | note | ○ The slab surfaces shall be broomed to provide a non-slip finish.
label | 2bde4e60-1524-5251-872d-8a4ec100e790 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
label | 11645b9b-aa46-52cf-9e5c-181fa1dddf3c |  | note | INSPECTION/TEST METHOD: Checklist
label | cffdf13a-f8ff-55aa-ad2c-332858c9a122 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 352feb6b-e0e4-5bfd-9c2b-edcd0dbe44fa |  | note | IP
label | 92ee2fcc-b7fe-5888-91e5-5a804a5851ce |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | dd9603b6-e8ce-5009-a5bb-b7de9ae90736 |  | textbox | Date Completed:
checkpoint-status | 72493c98-1012-4bd1-80ed-ac30d861dd3c |  | checkpoint | 2.15 Post pour inspection
label | b0e5df4c-10b9-5534-a2de-837ac6f74af3 |  | note | FREQUENCY: Each Lot
label | ed30d8f2-a063-53f3-b47b-a0668c77b9c8 |  | note | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
label | 440cb4b2-ed6a-5cf2-befb-77d58830de52 |  | note | ○ Ensure no defects are present in slab
label | 4777a00c-24b3-5706-b71d-daf9ef7969a4 |  | note | ○ Complete Fulton Hogan Post Pour Checklist
label | 1e2ca9b0-cda0-5327-99b3-06e951d138b2 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | b140faaa-c03d-524f-8d83-fca3ec78b9f2 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d39778aa-bb2f-5f7f-9619-5416b56190d9 |  | note | RECORD OF CONFORMITY: Post pour checklist
label | 59d754f8-87be-5d12-84aa-84d9123353ce |  | note | IP
label | 4ac7df1c-78ec-5791-83db-0aefb2332735 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a48c3f8d-9537-5f38-889d-4c11e0269e58 |  | textbox | Date Completed:
checkpoint-status | e7276fc6-1256-4fa6-9d84-d23f5dfbc3c1 |  | checkpoint | Final Inspection
label | 60f13e90-8bdc-5233-ae41-c35a531f485d |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 69916127-1ab3-5817-910f-7d05923f4aca |  | textbox | Print Name:
text | a2970c3d-18df-5acb-a492-ed66acf0c16e |  | textbox | Position:
text | a70521fd-0352-5bf3-9e60-ae2442b1a130 |  | textbox | Date:
checklist-sectioned | 61f4bff3-2af7-456c-975b-28e48f708fa0 |  | checklist | ITP-005 -Track Drains | itp |  |  |  | Yes | ITP-005 -Track Drains | 74fd916a-a6f5-4387-9dac-6e84c2f9cb5d
checkpoint-group | 393270ed-6cca-40d9-8b7d-32c6c4fdd52d |  | section | Preliminary Works
checkpoint-status | 361738d8-f2a9-421b-a7dd-75019153335f |  | checkpoint | 1.1 Check for correct documentation
label | 4e45af8c-ecbf-5eb0-b8e4-82cd0ffdc21d |  | note | FREQUENCY: Prior to commencing any activity
label | 729ede4e-b349-5e7e-9dc8-2050e3e0b46d |  | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwarded to the superintendent
label | ccb75a00-8601-56f3-8761-3cabf6cc9228 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 0e9aa4eb-cfc7-57c6-b203-fac79aefb494 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 11c89326-9c2e-556e-88a2-c572c1145ca1 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 38edb628-c050-5521-84e5-000e2778b5a6 |  | note | HP*
label | 504adf52-7e62-55f2-8cd5-267fa656e547 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 82b44a2e-9bc2-5807-8893-79ce18f9c003 |  | textbox | Date Completed:
checkpoint-status | ea5e3c64-eee6-4259-a8a8-fd3456b25b35 |  | checkpoint | 1.2 Materials Check
label | 62f68889-f467-575d-a80a-401d2bf334de |  | note | FREQUENCY: Prior to commencing any activity
label | 6a33e886-57d5-57a6-8771-8a9e75d05051 |  | note | ACCEPTANCE CRITERIA: Ensure drainage pipes are of correct classification and are without damage
label | 511c4397-c35c-5a24-b6ca-6e123cfb436d |  | note | ○ Check triangle drains are of adequate quality, and are design according Ri57A rail profile
label | 978cd21c-ff9f-5465-b3c4-5f6b99ec9521 |  | note | ○ Ensure lid and j-bolts being used are in accordance with STD T9022
label | c99aeac5-e40d-5be8-b9d1-24a0a5fa6e22 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1 STD T9021A STD T9020 STD T9022
label | 72c3b0c6-a529-589d-8e54-5c308b9c45b3 |  | note | INSPECTION/TEST METHOD: Visual inspection, Inspection Checklist
label | 763ed6fd-3fb5-57e1-9434-22a43851cbd6 |  | note | RECORD OF CONFORMITY: This ITP signed off, Recievable Inspection Checklist
label | 893902b3-35ef-50ac-8935-167872d5e4c0 |  | note | HP*
label | 7af34985-5337-5b74-8465-d10f3ff8565a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 3615fa5d-5cb4-5609-b1c0-efd415ecaa4b |  | textbox | Date Completed:
checkpoint-status | 2e8ab428-231e-4aeb-be05-d7856a9948c1 |  | checkpoint | 1.3 Bedding Sand
label | 75139fa8-fa80-5b44-925c-c04871ed66aa |  | note | FREQUENCY: Prior to commencing any activity
label | 633af56e-ae8d-59b6-a500-114a3e232cb2 |  | note | ACCEPTANCE CRITERIA: The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following: Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities,Consisting of hard durable particles, and well graded.
label | 64694d28-9664-5cc6-aa5e-52a54b94cbbe |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3
label | 6460ce5b-810a-508a-9879-6fbf1ac460af |  | note | INSPECTION/TEST METHOD: Visual inspection
label | fe0ecd19-a0e2-5a81-b2d2-e85f121b091f |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 5184d55d-5b2c-527e-9104-d072462b50d5 |  | note | HP*
label | 010a7b76-3427-5c6f-b99b-46eeafd93dcb |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | d05110e0-2b18-5259-bdbc-a3931703eb93 |  | textbox | Date Completed:
checkpoint-group | 25956f10-bbfd-4c47-8887-083232bbb51d |  | section | Construction Works
checkpoint-status | 832a9173-469a-4278-9224-6240caeebae6 |  | checkpoint | 2.1 Set out drainage
label | b8e52546-669d-5cde-80c0-502e47981103 |  | note | FREQUENCY: Prior to commencing any activity
label | 7399091e-1f5f-5ece-8c31-2a19ac6533ce |  | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | 069f8295-f946-5f4c-ae69-8cf9191dbedb |  | note | ○ Track drain locations are to be identified and based off IFC drawings and sections.
label | 205b3516-f994-59f3-899a-b5f5200a2da6 |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | a7f7ac05-d220-567c-a67c-eb3827f308da |  | note | INSPECTION/TEST METHOD: Visual inspection
label | e0fc48a2-e4b1-5e59-b884-2879899d4f23 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | bb2ef332-9b58-5f14-9f76-aeb7d1f6681c |  | note | HP*
label | 7a072354-dc9a-5c34-a980-2e56a30090e7 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1dd47440-d2bc-507a-b090-76bba0b1c74f |  | textbox | Date Completed:
checkpoint-status | 6e8c0284-23b6-46df-9f19-a1eb88c6f643 |  | checkpoint | 2.2 Excavation (pipes)
label | 8aeb63d8-9b02-564f-8d1c-6bce4ec6f345 |  | note | FREQUENCY: Each Trench
label | 975afffb-a2c0-5259-9200-8cdee32b74f7 |  | note | ACCEPTANCE CRITERIA: Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe
label | 77830d12-36bb-599a-8ff3-ecb8d96c0e30 |  | note | ○ Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
label | 05048e54-7cf8-5d2a-8515-4082911ed946 |  | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044 cl 4.3
label | e5c3c2fa-e50e-50cb-9814-07e1d7b95c5d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | bf69c74a-62fc-5eae-b7d6-39ee6d7c1e4c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | be0dec9b-7c09-5f8a-b94c-5e9f345f21d6 |  | note | IP
label | 47a27a8e-3eae-57d8-9491-569d357ed44e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2f5651ad-1b8e-53d9-a2a3-f930faddfcb4 |  | textbox | Date Completed:
checkpoint-status | 6b726219-4278-4fd7-9835-024c60ad3411 |  | checkpoint | 2.3 Bedding
label | 11991987-be2b-526a-9865-0bbd4d898161 |  | note | FREQUENCY: Each lot
label | 0c520c19-5b9c-5869-9c15-80145a6cb0ce |  | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
label | 8ced1656-1d2c-546a-ac93-a5734de88b24 |  | note | REFERENCE DOCUMENTS: STD T9021A
label | 7d24a35b-abe4-569a-91c4-c2d17fd988e7 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 928ea025-835c-533a-9f5b-72632aecdae9 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 190fa441-1804-5a05-92fe-3c2509b5823c |  | note | IP
label | 8d3bdc4f-57e6-58aa-9fb3-f2c30273b29d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f8de45bb-21ea-5cec-9c15-0636e68eeb55 |  | textbox | Date Completed:
checkpoint-status | dc0a8cee-4505-46cf-bd33-4ef4240595f2 |  | checkpoint | 2.4 Joining
label | 8793cf1a-e208-558a-b9b1-b53e2c3c994c |  | note | FREQUENCY: Eaach lot
label | 912e8bbf-b600-5b3f-a86c-812348bada87 |  | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends.UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
label | c22bb49e-c0b2-512d-a272-609a5ea89645 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
label | a381b7cb-28a0-5528-b99c-16f0002a555a |  | note | INSPECTION/TEST METHOD: Verify
label | 91f21c50-264a-56b1-a9e4-a45740eca08e |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 06f22989-6069-57a8-acd4-0d0d1d02188c |  | note | IP
label | 899c820a-9410-5ebd-b48b-f0fbf800e99d |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c65f9969-81d8-5787-ae1c-af4013166bde |  | textbox | Date Completed:
checkpoint-status | b8bd4edb-aa16-4e99-ae78-d8ff9396c2b9 |  | checkpoint | 2.5 Track Drain Installation
label | d5d8c323-e08b-5bd8-a978-01a0c13cb5c2 |  | note | FREQUENCY: Each Lot
label | 8f457e83-da47-54d4-bdca-1d5a2180576a |  | note | ACCEPTANCE CRITERIA: Track drains shall be welded to designated positions, and cleaned of all weld splatter.
label | b0efea61-76a4-5444-871d-527d0fbd0cf2 |  | note | ○ Weld shall be sealed after installation
label | d842ce27-b437-54a4-a1de-3094b2a9f2d4 |  | note | ○ Rectangular 300 x 450mm junction pit and lid shall be used with 4 x j-bolts secured as per STD T9022
label | e889e8fe-23dc-5fc3-98e6-8139aa9f8d0c |  | note | REFERENCE DOCUMENTS: STD T9021A, STD T9022
label | b9bf538a-0cc6-57ed-87bd-305bb213d365 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | e5ad637d-8fb2-5cf5-8158-7ceae06ff9dd |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 289ac792-0cc2-5150-9195-ed257885e500 |  | note | IP
label | 8423d1e3-03fd-5a73-9906-07e4bbc47773 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2e6805a7-4318-5399-bec4-d1eec5ba2882 |  | textbox | Date Completed:
checkpoint-status | 92b5cf11-a944-4f24-af8d-49052d0095c4 |  | checkpoint | 2.6 Points Drainage
label | 9dede1a9-ef20-534d-ba6d-26b6f8e4a022 |  | note | FREQUENCY: Where required
label | 86e3ead3-6a83-5459-b0d0-e853a96b2947 |  | note | ACCEPTANCE CRITERIA: The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit.
label | 1d7f43e1-73ba-5f27-baaf-176b522bc378 |  | note | ○ Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
label | 0cee07d1-0b1c-5b8e-ba71-1f2d9ba2b5c8 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3 STD T0304 STD T0305
label | 44748afa-d4d9-5967-ac58-e02f8cbd1f2a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | eca212ea-02af-5abf-9ef8-9702cc431739 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 898a277d-722a-51a7-90ca-24d090b8c12c |  | note | IP
label | b6d07478-3b26-5300-a884-a53d9c24fbb6 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 3dd2cfa9-887f-51d1-90d3-760fbacc0081 |  | textbox | Date Completed:
checkpoint-status | 87eadf40-f593-4e41-a004-8a6e17c327d9 |  | checkpoint | 2.7 Concrete Pour
label | 00dcf223-ae2e-5f0d-ae23-8ef1e0638e89 |  | note | FREQUENCY: Each Lot
label | 28e903a6-4dd5-5203-b5ab-256b669dc97a |  | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
label | 615dc44f-05c8-56c0-a2b2-019d84ec1132 |  | note | REFERENCE DOCUMENTS: STD T9021A
label | 158b59c8-e1f5-5464-878e-7b6d0b9f8b73 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | d3a2f775-5b37-55e3-be15-fa39dc39e428 |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 85b4bfe5-7f87-5f84-bffd-27727b891a03 |  | note | IP
label | 64c1d386-c777-5cfb-aca1-0a4703c263ce |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2a802548-7a86-516c-ba4f-329204cdfd5d |  | textbox | Date Completed:
checkpoint-status | 3497970b-6cbb-49df-8ac7-4a1aeffe9255 |  | checkpoint | 2.8 Connection to local drainage
label | 56fa65bc-ed60-535d-be31-c5a6a76da10a |  | note | FREQUENCY: Each Lot
label | ee21e0a0-ad10-57ae-9773-6eddea8e5f4e |  | note | ACCEPTANCE CRITERIA: Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority. The minimum pipe size shall be 150 mm.
label | 0664a6db-61cb-587c-b537-74a975de2085 |  | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
label | e55bb5b1-2e55-5641-aae9-f60c034c012d |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 42166255-1e02-54a6-8a60-b7db7a18f46f |  | note | RECORD OF CONFORMITY: This ITP Signed off
label | 4730c049-f19e-5fd1-afb1-03e5ed3cbecd |  | note | IP
label | 8c8fc447-34c8-59bc-aa29-18953e348e48 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 7ad8d43d-b404-5f23-8bf9-b7216d6d1534 |  | textbox | Date Completed:
checkpoint-status | b673e6b3-f7e4-44e9-8df5-f0a41004f1ca |  | checkpoint | Final Inspection
label | dc4a425f-c597-561a-bd86-1d6a96704703 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | f5f996a9-c3cb-5f74-9a35-3802ba070589 |  | textbox | Print Name:
text | 0df5d9a4-8d7b-5ffe-a129-6b843b23d1a2 |  | textbox | Position:
text | 551ed2cc-58b1-5411-9b5d-fa72520556db |  | textbox | Date:
checklist-sectioned | de985e5c-3411-40d9-a7bd-3320ec632707 |  | checklist | ITP-001 - Subgrade Preparation Rev2 | itp |  |  |  | Yes | ITP-001 - Subgrade Preparation Rev2 | 778285b2-812d-4ed5-b00a-d97e4df21a17
checkpoint-group | e64bb743-4437-45e8-af14-67876dd03ad4 |  | section | Preliminary Works
checkpoint-status | ecd9e2eb-82e9-4862-bcf0-c58b4e52ab1b |  | checkpoint | 1.1 Check for correct documentation
label | f9c22416-adad-5c3a-b5da-b2b672b56d6d |  | note | FREQUENCY: Prior to commencing any activity
label | dc31da29-cf94-54cb-a943-62a978304e50 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | b1ccfefa-b4d4-5e17-b2b3-e8b88ceea31c |  | note | – using the correct and complete set of drawings
label | 25811e2a-8083-51d6-8c94-54db9a519931 |  | note | – all drawings are the latest revision
label | 3920fe06-1e45-5812-9ff4-2dc517fa5c0c |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 65618ecf-54d6-5dbe-b323-041a3a2b0e5f |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 68489806-07a6-576a-aa79-6f089e375a35 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 6dfddd64-f664-544a-a9ec-de7982d921f3 |  | note | WP
label | 9cc0aeb1-4a8a-5dcd-87d0-d495d4a00fa0 |  | note | RESPONSIBILITY: Fulton Hogan
text | 64f99948-c636-555c-9063-facc206f1f15 |  | textbox | Date Completed:
checkpoint-status | c14175ef-b6b0-4a1e-ba2e-6d60b508f4ce |  | checkpoint | 1.2 Implementation of all measures and controls
label | 0a4b9840-15cb-5e4a-9794-2536729b8000 |  | note | FREQUENCY: Prior to commencing any activity
label | 258b18f0-bea3-5930-8865-dd0e2e46422d |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 31895126-b3ab-52a5-882f-1c63f3a80830 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 1846b26b-5e13-571e-8d89-c3a553e1ddd6 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 46fd3b63-a5bf-52c3-923f-554274a9db0e |  | note | RECORD OF CONFORMITY: This ITP signed off
label | acc9bd44-769e-5a2d-820a-6f9ffad18ba0 |  | note | WP
label | 02e9ba95-0ac8-5cf9-b5e9-37d619070910 |  | note | RESPONSIBILITY: Fulton Hogan
text | 46cfd7b3-a817-591a-98bf-2592fbd7c430 |  | textbox | Date Completed:
checkpoint-status | 4f4001a7-3140-462f-8cca-b6d6f430ac93 |  | checkpoint | 1.3 Selection and approval of disposal site
label | 08bedc12-d023-5a23-86ab-4ad1f6ad9ede |  | note | FREQUENCY: Prior to commencing any activity
label | 69eac4e4-78c9-5b41-a394-d7609c5d2076 |  | note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements and in accorance with Yarra Trams site classification report.
label | 563493b5-ebd5-5429-956e-bf5ad446e73f |  | note | ○ It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the authorities controlling disposal of material at that location.
label | 10142392-8113-5c29-a58c-f6ec00fc33b9 |  | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019- ST-0033 CL. 4.2.1.5.
label | 6fb8709d-325c-528b-b9cc-0c10926d557f |  | note | INSPECTION/TEST METHOD: Verify
label | 3e49ceb2-4da5-508b-91f4-72c38aa49473 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 003969ef-ee58-53fc-8358-5f9e0570856b |  | note | WP
label | 28b23d52-5690-572f-a106-e54ea3e2df7f |  | note | RESPONSIBILITY: Fulton Hogan
text | 275d6709-ac13-5949-ab7c-eafd474fadc0 |  | textbox | Date Completed:
checkpoint-group | 8e2d534b-fb0e-4f2b-938f-ae4d7efdf211 |  | section | Construction Works
checkpoint-status | edbb8a00-c1aa-4833-9a83-78937da7f4bf |  | checkpoint | 2.1 Excavation
label | 44e774db-7f1f-5c6b-92c9-c6d243454245 |  | note | FREQUENCY: Each lot
label | 773c46f8-dbc4-5046-a5e9-d9eff7b3b0c1 |  | note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of works.
label | 31b62af9-f71d-52f6-8f58-92b15c06977a |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
label | 7604f338-7bb0-5c98-b7b0-8265ed3c0be7 |  | note | INSPECTION/TEST METHOD: Verify
label | 5bcedd1f-86d7-546c-a1f2-4dcb0af0c819 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | b930933d-df7f-5877-a3fc-fd8869b04b59 |  | note | IP
label | 33faad4b-b1e8-59d8-aa38-797d695c137b |  | note | RESPONSIBILITY: Fulton Hogan
text | 79380ca7-6e38-5da7-b2fe-f19277b66279 |  | textbox | Date Completed:
checkpoint-status | ce2ca4f8-9ade-458b-b68e-eb275965dc18 |  | checkpoint | 2.2 Reinstatement of bonds
label | ccaa24e7-d87a-5aaa-a68b-7b827c98c399 |  | note | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
label | 99d9c45f-b33a-5262-9f95-693bc7254fb6 |  | note | ○ All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
label | 2139d3d5-4d3e-5db2-a3a7-695b1820171e |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
label | 6dd9c525-3d30-5286-a902-67e562a242a4 |  | note | INSPECTION/TEST METHOD: Verify
label | 5836c98a-8f3e-5d1b-bed5-64a3c15b7f43 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 0768c6cd-e4a9-5b3c-977e-eca30be30fdb |  | note | IP
label | 84b9115f-0100-528f-8303-c5dbde1fcc63 |  | note | RESPONSIBILITY: Fulton Hogan
text | 8a8be112-5380-504a-9f36-ae496a259a47 |  | textbox | Date Completed:
checkpoint-status | 4410f3a8-663e-41ee-94ad-794d91f0b05d |  | checkpoint | 2.3 Inspection of subgrade material
label | 0586e95a-0ac5-565d-95e3-8e71c30372b1 |  | note | FREQUENCY: Each lot
label | b30d7713-afb3-5ad5-aef3-1d899c5ca729 |  | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the standard.
label | c295a9e7-b25f-5c72-bb3f-bf7e5143b0dd |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
label | 136d08ea-c049-5c74-a9cf-a524d6b166d5 |  | note | INSPECTION/TEST METHOD: Verify
label | 332b27c7-70e1-5fda-89bd-9ae2b398ba8a |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 562f7694-fbc0-5999-ae86-7583ba271cd2 |  | note | HP
label | ce6c9bfc-083e-5808-bc5f-ee67a9327a40 |  | note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams, Superintendent
text | 61330ee3-9407-504f-ba27-b0f0396e7b91 |  | textbox | Date Completed:
holdpoint | da8188bc-b89d-40df-8274-55e9a05b8d11 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 7749a138-fa79-4393-9144-33205fb69fe6 |  | checkpoint | 2.4 Width and level conformity
label | ae452c4d-352c-507a-90a7-a2843e7e27f4 |  | note | FREQUENCY: Each lot
label | b12079f8-2017-59c0-ae5a-e8273b763130 |  | note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings.
label | 84aede2a-6259-5c5b-a9b2-cefec61f537f |  | note | ○ No point in the general surface shall vary more than 12mm from a 3m straight edge.
label | c0908866-9909-598e-b21a-99951210c6a6 |  | note | ○ Finished formation widths shall not vary more than -0 mm, +50mm from dimensions shown on the drawings
label | b612f489-105f-55f0-9132-209f75af2d9d |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
label | d6758c11-fcf8-5326-8c89-c87115f1b143 |  | note | INSPECTION/TEST METHOD: Survey Report
label | ab6bee9c-396e-53c3-aa10-e0a80d9bc8a4 |  | note | RECORD OF CONFORMITY: Survey Record
label | 645f7308-bce4-57c6-a4ba-ea3eedb4c803 |  | note | IP
label | af87218b-d37c-50ef-8854-0e70c9811e07 |  | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
text | 9c3aa7b1-2c65-53d6-aa3f-85a17aa09b2d |  | textbox | Date Completed:
checkpoint-status | 99c91f76-b475-4878-b291-d638e808437e |  | checkpoint | Final Inspection
label | d795803d-1fb9-53a3-97c9-8d3827ee69b0 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | d9b6e478-085c-5532-9aa2-140e32d646d0 |  | textbox | Print Name:
text | a840e408-3fab-5131-a0ae-b7c0b280eee4 |  | textbox | Position:
text | d6b7f003-bd1b-5df6-9b1f-7fc274d52d0a |  | textbox | Date:
checklist-sectioned | 6e36808b-879e-4030-9d99-ca6c88f1c834 |  | checklist | ITP-003 - Electrical and Communication Conduit Rev2 | itp |  |  |  | Yes | ITP-003 - Electrical and Communication Conduit Rev2 | 8b1fafa4-cec0-4389-94e8-b2a65a5a0b37
checkpoint-group | 82f36df4-b959-4116-bdc8-388178188ec9 |  | section | Preliminary Works
checkpoint-status | 6a8261cf-c891-4af2-a42b-4f6db16c7f88 |  | checkpoint | 1.1 Check for correct documentation
label | 2b9f812a-c50e-5e82-a8b8-0387b4ae3772 |  | note | FREQUENCY: Prior to commencing any activity
label | c0858687-8926-56ea-a1a5-962e8382c972 |  | note | ACCEPTANCE CRITERIA: Employees and sub contractors shall be issued with the most current and complete construction drawings
label | b6d4fb5e-5c64-599b-a38c-a36acfaa5457 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 8df7c2b1-d971-559b-bd46-23f99bdff262 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | ada2c8c7-c98e-5de1-a340-3347be248431 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | aa61e371-59a6-5e4b-8fad-3e93d9eefd07 |  | note | HP*
label | b4d56f38-7a79-5e82-b3e4-bd64255d9c4f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | df0b9859-9ad0-55ed-b10f-ae457da85ea8 |  | textbox | Date Completed:
checkpoint-status | 0bbc5408-b370-4a22-958a-dbb11292cde6 |  | checkpoint | 1.2 Implementation of all measures and controls
label | ba1a6551-4170-5c6b-9fd9-395766a630d1 |  | note | FREQUENCY: Prior to commencing any activity
label | 954bbd15-52e4-5a44-8f4b-99d07a25e99f |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | eee35e62-7bc0-5e79-b252-82e5e0bdd892 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 271f7e17-6770-5302-8a1c-8aebf1df24c4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6473db8b-2471-5946-8c09-f3f108a6ea02 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | f694ef0c-28d4-554e-9dcb-47f20498e18a |  | note | HP*
label | 697574bf-e908-53e5-9bac-cb38681d5e40 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 83fe34c9-b86d-5f78-83c6-9e087941592f |  | textbox | Date Completed:
checkpoint-status | 667c06d6-0fbd-476d-a7be-fef727f881cc |  | checkpoint | 1.3 Materials
label | 825255ff-b30d-59ff-893a-70ca0258a947 |  | note | FREQUENCY: Per Batch
label | 283255c2-ebce-5df7-af0c-e23738b85e6a |  | note | ACCEPTANCE CRITERIA: Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required.
label | 04af5549-63c5-5cac-ba11-60b6346edd0c |  | note | ○ Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required.
label | da0bf4fa-4a93-5460-ab11-69068fa16b07 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.1 AS 2053
label | aa73ee0b-673e-55dd-9936-723793b2b418 |  | note | INSPECTION/TEST METHOD: Verify
label | 9a17bc06-4813-5e16-8c17-a4b9dfbb16fc |  | note | RECORD OF CONFORMITY: This ITP signed
label | 7eee002d-ebb8-5c95-b7e8-282bbee6a7b7 |  | note | HP*
label | 9c873074-b290-5251-a779-afcf87064d60 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b7991ade-0b44-557b-b060-6cc2e6ed4fc1 |  | textbox | Date Completed:
checkpoint-group | 7a6233a9-b132-4a87-a0e2-d40c52fc0f7b |  | section | Construction Works
checkpoint-status | 3e2801c1-54e8-4251-a779-63bad2e7a3d1 |  | checkpoint | 2.1 Survey set-out
label | 2de5c1d6-c189-573e-90ab-305d3156b8d2 |  | note | FREQUENCY: As required
label | feecc3f6-f6b3-5fa3-b751-7692bf81c6bc |  | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
label | a6541ccc-b9ce-5e29-93ac-7e54b3aee956 |  | note | REFERENCE DOCUMENTS: Work procedure
label | 2100ba1f-d263-5b9c-a6cd-72dde25f0672 |  | note | INSPECTION/TEST METHOD: Verify
label | 7594e246-fc4a-5c4a-95c6-05911f1b8c27 |  | note | RECORD OF CONFORMITY: This ITP signed
label | e475af43-0b48-58fa-acee-956f5bd0cc24 |  | note | HP*
label | f5fa1948-ec14-5880-969f-6e0c0fb0160e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2446bd7a-035b-5bd6-8379-23fe5e9aaa4e |  | textbox | Date Completed:
checkpoint-status | 568216c1-bea2-414d-bb31-04f553720538 |  | checkpoint | 2.2 Excavation and Trenching
label | 716dd301-49e9-59db-b5e0-ee410f8d9711 |  | note | FREQUENCY: Prior to Installation
label | 3befc770-f61e-5e72-8a7c-f6fa49e602cc |  | note | ACCEPTANCE CRITERIA: Minimum cover for underground conduits shall be 600mm
label | 5bb0cd1a-768f-587e-8bef-25afb373b29a |  | note | ○ Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
label | 13dd7ed9-1e07-589c-b660-b9aa99327a29 |  | note | ○ Trench shall maintain a minimum clearance of 300mm from all existing services where possible
label | fe1acdcc-7481-5505-a639-6920d35b51e0 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
label | 0f4434e3-95b3-5633-a535-d2a4944c891e |  | note | INSPECTION/TEST METHOD: Verify
label | a6773e3d-5781-509e-ba2e-47a1d7e7577d |  | note | RECORD OF CONFORMITY: This ITP signed
label | 00423b96-3c30-57c7-9b4f-5910c3a8b341 |  | note | WP
label | 2818080a-5540-51d1-bd3e-928fda16e47a |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 14ede8f1-9832-5110-ac38-b8b72e9711f1 |  | textbox | Date Completed:
checkpoint-status | 1f0f5a28-4666-4378-8a34-09ec26f01e3c |  | checkpoint | 2.3 Installation of Conduits and pits
label | ecf58d06-9729-5a2f-9d6d-fc585e9a0f29 |  | note | FREQUENCY: Each Lot
label | 9ad97981-2f13-56c6-908a-3d226555c3d6 |  | note | ACCEPTANCE CRITERIA: Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
label | ba3315cb-ddf8-5f50-a720-9b32f42d25e9 |  | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
label | 5383d87f-5e69-5dd1-8c25-fc79d7385883 |  | note | ○ Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
label | 25656eab-c7f4-584d-b9d1-e4f2d6b69654 |  | note | ○ Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
label | cc2d9066-19f2-5c6b-8496-51fd31c5c3c3 |  | note | ○ Conduits shall not be subject to construction loadings
label | f966e556-7b1c-59a9-aade-6ab361f89afe |  | note | ○ Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
label | 2431e1b8-af01-5a42-b3ed-5c855811c73c |  | note | ○ Conduits shall be capped with UPVC electrical caps
label | f9b67270-bdd8-5496-9fe7-5fff76e30808 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
label | 0d36d79c-20f0-51f1-9e9e-b42c23e5c717 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 5a54b821-d84c-5e69-963c-989a4d683537 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 497bdea4-21d4-5cf9-8dea-c9a5b1629398 |  | note | WP
label | efc8b93e-e0cd-512f-acc7-f3e6530386a8 |  | note | RESPONSIBILITY: Fulton Hogan Engineer/ YT
text | 01b899c3-d16b-59b0-96a7-ee747a6c44b4 |  | textbox | Date Completed:
checkpoint-status | d944c36d-baee-420f-a8d4-89b867207b73 |  | checkpoint | 2.4 Inspection of conduit installation
label | 34f8200c-000b-561c-b337-279937f053ff |  | note | FREQUENCY: Each Lot
label | 4425393b-f2da-5ef5-88b4-1de111f3a486 |  | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
label | 11431eb1-3af1-516c-8090-970ef6b52097 |  | note | REFERENCE DOCUMENTS: Work procedure
label | b6f75094-0c45-5f34-addd-0dfb33e1989b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f232f2bc-b915-50d6-8b8b-3b49dd9ab834 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | bc4b1639-ab9c-582b-aaa5-067252973457 |  | note | *HP
label | b3186681-55b6-547c-8c5e-3f9897a6c044 |  | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
text | 65e999ec-f223-5b8c-8640-e540b539308f |  | textbox | Date Completed:
checkpoint-status | 225b1c76-ad60-40f9-aae7-02acd388596c |  | checkpoint | 2.5 Back Fill of Trenches
label | 45405efd-d81e-512a-b044-3aa1d55cded6 |  | note | FREQUENCY: Each Lot
label | 12f030e9-0569-5dc4-a9a2-3aa9289387e4 |  | note | ACCEPTANCE CRITERIA: Backfilling (for trenching or road crossings)
label | 0d6e0b2f-a037-535e-98f5-07445eca21e5 |  | note | ○ Conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
label | ae702fd5-a226-5aad-9c31-d8eb95a0204d |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
label | 0e112cca-8045-543b-915c-c603c40f4b2b |  | note | INSPECTION/TEST METHOD: Verify
label | 8004e3df-997b-5ea5-8c69-b16f2e5c736f |  | note | RECORD OF CONFORMITY: This ITP signed
label | 0f8f65b6-32ea-5173-85a6-352a5dac9cff |  | note | IP
label | ae31d010-e35e-56a9-8763-3951f8abfa82 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1f03a4a8-7cdd-520b-83bc-7ada53588954 |  | textbox | Date Completed:
checkpoint-status | d1230295-f720-40f8-b9ba-0eaeb1498c44 |  | checkpoint | 2.6 Installation of Draw Cords
label | 9a4eea9b-80bd-50c4-806e-5aabea07806b |  | note | FREQUENCY: Each Lot
label | 87194db5-1107-5d7d-b10c-daeda4354786 |  | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit, material to be used shall be 6mm 'telstra rope'
label | a99d03c3-c641-5af6-ab88-82d116724355 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
label | 860eb4d6-23b8-5bde-b2e4-165eece3587d |  | note | INSPECTION/TEST METHOD: Verify
label | f74b1289-24bb-57ac-8251-0da0eddc1146 |  | note | RECORD OF CONFORMITY: This ITP signed
label | dc2722d3-fc1a-5e4a-98ce-1529386578f5 |  | note | IP
label | a05fa70a-fd3f-5a31-a99d-9924d89936f2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 795b7b1f-0db4-5b02-b989-927305727f0e |  | textbox | Date Completed:
checkpoint-status | 1c7fb2fd-8d4e-4c4a-9050-675225bafac7 |  | checkpoint | 2.7 Compaction
label | 268c3b97-3ab0-56d6-896e-57c72feb6c5c |  | note | FREQUENCY: Each Lot
label | 64380eaf-d002-50aa-82c7-b0ef2b5247b1 |  | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115% as provided by suppliers
label | 6f0ab5a0-2258-5c6a-903f-274ace6d9311 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
label | ee155669-d555-526d-9bbe-fcdc2d1a08ec |  | note | INSPECTION/TEST METHOD: Verify
label | f851e0f3-d1e9-5bd6-8045-c7f6d0e25ab8 |  | note | RECORD OF CONFORMITY: This ITP signed
label | a7c941df-b54a-56b2-a5ec-cc8d6bb63906 |  | note | HP*
label | d39e51d9-ea17-540c-b9ed-36578a02453e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 2627fe93-7bcf-5067-82cc-32da3382c89c |  | textbox | Date Completed:
checkpoint-status | f307752d-5c70-4ad0-89e2-3372e3247f8c |  | checkpoint | Final Inspection
label | f481c64c-f0de-5314-a066-91d145d110ee |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 209f04c7-5f7e-5648-a4ad-f4a523e6c5d1 |  | textbox | Print Name:
text | 937a1cf4-0d08-5934-9169-a3d2adf40651 |  | textbox | Position:
text | 35815286-9830-5586-9379-5480433c7788 |  | textbox | Date:
checklist-sectioned | 13c5a465-7b40-4701-895d-2062c9225151 |  | checklist | ITP-020 - Exothermic Welding | itp |  |  |  | Yes | ITP-020 - Exothermic Welding | 904e9f04-718e-44ac-8f63-e58047cd0a6d
checkpoint-group | 86a994c4-bd46-4246-822f-f828e388c862 |  | section | Preliminary Works
checkpoint-status | 26100171-f24a-4144-a8f2-69be870070e3 |  | checkpoint | 1.1 Check for correct documentation
label | abb97789-caaa-557c-939d-88cb6be7deae |  | note | FREQUENCY: Prior to commencing any activity
label | 17f04002-8f3e-5fd1-9a0c-0431d0ad61a2 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
label | 1e4af1e1-8240-529b-9cb2-7f87b4cf35ae |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 265239be-df74-5c6f-be67-f38e83727920 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 034cd047-155c-55b4-bdf1-95314b5451d6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a66694cd-5bcb-5364-8173-849d2fa1cbaf |  | note | HP*
label | 5551ce8e-96ef-57dd-a111-881ed260bd33 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 1e46a6d5-a9d2-586f-a840-bd1a94f18053 |  | textbox | Date Completed:
checkpoint-status | 027bd78c-329a-417b-814f-1999e41c9c51 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 82170ea5-3e15-50f8-8bb2-f3c3cf863c09 |  | note | FREQUENCY: Prior to commencing any activity
label | 3c79df05-cd0a-50dd-b540-7c7c9e5c8e4f |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | 0c93e225-8cc0-521b-890b-d8231a3a86ff |  | note | ○ Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
label | f972dabb-7c67-5b36-87e7-2d9cd158aa11 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 3fcee982-80b6-59fc-a29a-1f4c470dbbd5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | fb898adb-3d0f-5981-8951-3e39db8c9d1c |  | note | RECORD OF CONFORMITY: This ITP signed off
label | e476d8e4-98bd-580b-a85a-3b36e5aa96a9 |  | note | IP
label | 0a232a39-9bd7-5a7b-8bee-cc08bc34f576 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 9799fe37-1334-5c47-8381-385e90285ade |  | textbox | Date Completed:
checkpoint-status | 8b77bcab-f0f9-4814-a4f8-da9d407bf168 |  | checkpoint | 1.5 Materials Check
label | be6e667a-970f-57f1-8aa4-d9ced7782a3b |  | note | FREQUENCY: Prior to commencing any activity
label | 558d8534-ce40-540f-b8cf-106e6c363d5a |  | note | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type of connection being made.
label | c8011992-4e0b-519a-afe1-089fca334cbd |  | note | Inspect the mould ID tag to ensure that it corresponds to the application, indicated by the following parameters:
label | 83a5be43-8f68-502c-b08f-d2819087b006 |  | note | 1. Mould part number:
label | a0797ed4-ee47-550f-afbc-66a5d1873fe2 |  | note | 2. Conductor size:
label | 3e6cd3a8-cdbf-5910-9b10-0824fcac66e4 |  | note | 3. Welding material required
label | 51d07e87-e8a2-531e-b793-16bec71c897b |  | note | ○ Check to ensure the graphite mould is not worn or broken, which could cause leakage of molten weld metal during the reaction.
label | 85add4a1-e15e-5f53-90e6-8c764fa671d1 |  | note | ○ Ensure a working fire extinguisher is available within 10 metres of the working area.
label | b1aadaf9-f158-5ea9-9826-65b66f249500 |  | note | REFERENCE DOCUMENTS: Eritech CADWELD, Exothermic Welding Manual Fig. 2, 3, 4
label | aeea1815-13fc-5477-8221-452e89a52e01 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 2653f111-43a0-5c79-a04d-f6d4ef939c9a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 79a4e7e2-0ac8-5345-8fdb-82740f5a510e |  | note | HP*
label | e91243c3-00ec-5f22-9e6a-d0f1f0530ac0 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | fc3776c2-e5da-5247-8be7-6b54927bc1f5 |  | textbox | Date Completed:
checkpoint-group | b77f7845-363c-4263-ac49-ee5f37ea5cf4 |  | section | Construction Works
checkpoint-status | 64c59132-7281-4aaf-94f9-f4dbef52664c |  | checkpoint | 2.1 Preparation
label | 8166ddbf-4e19-517d-9507-4fab1b15ea9e |  | note | FREQUENCY: Each Weld
label | 7e7422ef-2adb-52dd-86ac-238d9eab6e62 |  | note | ACCEPTANCE CRITERIA: Ensure the position of the conductors being welded is correct.
label | 45d6398d-1141-555e-9dba-037f6f42095b |  | note | ○ Heat mould to ensure it is dry.
label | 9cb0ff47-6919-5498-aa34-1c180c46da0f |  | note | ○ Strip and clean conductors, ensure they are dry & clean.
label | eac190a3-95ff-5792-ba95-7e211c318daf |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | 3524b210-e541-5a86-9d10-23c958b3948b |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 9589aa2e-d14d-588a-9a0c-2ee477777821 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 1b4bb8f8-8e83-567f-9803-c01cbd086894 |  | note | IP
label | a18806f1-4e6e-537e-9202-7a1f75470669 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 11729288-f1e2-500a-8649-951f6e373ee7 |  | textbox | Date Completed:
checkpoint-status | 57dec254-c672-4f29-ab7d-1c938ba9af65 |  | checkpoint | 2.2 Welding
label | b1eea125-aed2-5b13-b54f-fb616bf4ff90 |  | note | FREQUENCY: Each Weld
label | d7ce89d4-4393-51f1-8d3c-c69bc90eeba0 |  | note | ACCEPTANCE CRITERIA: Ensure conductors are correctly positioned in the mould, allowing the mould to close tightly.
label | 4a95ff94-4327-5aa8-be59-56f16c7b161d |  | note | ○ Ensure welding material has been insected and is intact.
label | 5f5401e1-9084-5cd9-b15d-725855c22b9c |  | note | ○ Ensure reaction is completed and molten material has solidified (allow 30 seconds post ignition)
label | ace84818-1309-5bda-8010-917f952faafe |  | note | REFERENCE DOCUMENTS: Eritech CADWELD, Exothermic Welding Manual Fig. 2, 3, 4
label | bf0a0b77-f367-50e9-97aa-ae985bc5eafb |  | note | INSPECTION/TEST METHOD: Verify
label | af0f0cbc-e72f-5c2c-a316-e1cf8d659bf5 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 40c1a173-bfca-599b-a00c-3f5d7eebb1ed |  | note | IP
label | 20db1856-fa48-55c0-b50a-fff7f03b63da |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 27160094-e615-54d8-88b1-d96e78c8a46a |  | textbox | Date Completed:
checkpoint-group | 9bdce20b-8430-4fc5-a860-4a929eaa768d |  | section | Testing
checkpoint-status | 6fa5ddc2-3255-45cf-91f7-550ed818daca |  | checkpoint | 3.1 Weld Review
label | cf2e279e-e0f4-575a-8ddf-2c0b8245f300 |  | note | FREQUENCY: Each lot
label | 4b42abfc-2312-5e71-89f4-b2f0f981917c |  | note | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made.All welds shall be inspected a Fulton Hogan engineer.
label | b8b49f0a-a0a9-5f18-8966-30598f39f04e |  | note | REFERENCE DOCUMENTS: Eritech CADWELD, Exothermic Welding Manual Fig. 2, 3, 4
label | 97552678-04c3-59ff-bd09-7237d80d417e |  | note | INSPECTION/TEST METHOD: Verify
label | ef400ff3-1bb1-5d26-82f4-0497ee965ba8 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 6add1245-260b-5bc4-bf30-2caa1f1097dd |  | note | TP
label | 164e39e6-d0e1-521f-a280-e9174a7939df |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | bb5c9867-ba38-5258-b557-a11ad8c1ba5f |  | textbox | Date Completed:
checkpoint-status | 0d606ae2-acfe-4bf1-b362-e0b6aa391273 |  | checkpoint | Final Inspection
label | 953d0342-612b-53e1-a03f-a47c6bf07e89 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 19b92a68-8423-5e78-9c78-5822c2a19b87 |  | textbox | Print Name:
text | 85411963-96d4-5d5e-9a0c-c7efd0b28af6 |  | textbox | Position:
text | b0e8da32-aef1-56f3-88e2-9dc3401763a6 |  | textbox | Date:
checklist-sectioned | 0bad39e2-2833-48ba-94dc-4a82b4a96221 |  | checklist | ITP-004a - Class 2 Base Course Placement Rev2 | itp |  |  |  | Yes | ITP-004a - Class 2 Base Course Placement Rev2 | b23514a5-237d-4933-8a95-3486bdeb348d
checkpoint-group | 42c74259-1eb3-4d4a-a782-46569987f4e6 |  | section | Preliminary Works
checkpoint-status | 331e2afb-3f7e-4e50-8023-bd73799448b6 |  | checkpoint | 1.1 Check for correct documentation
label | aa51d838-efb2-5409-895b-662c1034af9b |  | note | FREQUENCY: Prior to commencing any activity
label | 03f8c8c9-43f8-51e3-823f-cc673f11c9bb |  | note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
label | be35e619-9c5c-503d-816c-734da6294aea |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 3c47e7fe-fc49-552d-84d2-476182735a81 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 84068e42-9f23-5e06-93fc-9fb0f63430a2 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 153ead7d-c53b-5f71-8328-00fc3f58ba17 |  | note | HP*
label | 1e2d657e-aa2f-56fd-8b29-0ab88b4f0614 |  | note | RESPONSIBILITY: FH Engineer
text | 3bb067f9-68f1-5e21-8d4e-33c9df7be111 |  | textbox | Date Completed:
checkpoint-status | fe4b5803-8829-4af4-ab28-275578e29080 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 003aa821-5cb4-59ef-8f21-54a5a81c8aa0 |  | note | FREQUENCY: Prior to commencing any activity
label | f641c84a-1be0-55b6-8713-d66371191f3d |  | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
label | e03fcee2-9d1d-5447-bb85-b9d27045d923 |  | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
label | beffeb41-ab0c-5399-97f6-a0e336ab07fe |  | note | INSPECTION/TEST METHOD: Verify
label | d1ed0a49-8cb2-5ece-9857-b529317b7050 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4843810e-ab57-5830-b79b-941738c67182 |  | note | HP*
label | ce696844-c595-5980-a50e-2e5aa9dd424f |  | note | RESPONSIBILITY: FH Engineer
text | 80a0b73c-1463-5b71-aa2b-92f83cf3bcf0 |  | textbox | Date Completed:
checkpoint-status | 1e7673ef-6540-41ef-9b23-5e994735b832 |  | checkpoint | 1.3 Material Compliance
label | 6e363b11-e8ca-5a5d-a8f7-dbd8cb4909db |  | note | FREQUENCY: Prior to commencing any activity
label | d095c820-67c5-582c-a481-f61d08efc694 |  | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
label | 4e9cf958-1ea5-5c89-a164-7111a5872df1 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033
label | b70dadfa-bdf3-5a8c-b177-69926f857b55 |  | note | INSPECTION/TEST METHOD: Document Review
label | 1b5c9477-b7db-5aa4-93ce-c6376980119b |  | note | RECORD OF CONFORMITY: Test Reports from supplier
label | f1d712d0-dd9e-5beb-80b9-cc9958f8a955 |  | note | HP*
label | 5f7438e9-bcb1-5011-8d5d-613a0a1350a0 |  | note | RESPONSIBILITY: FH Engineer
text | e38fdf72-5624-5296-b71c-c4d83fa3583b |  | textbox | Date Completed:
checkpoint-group | 3d6b7101-7204-4b46-ac68-f971b201a884 |  | section | Construction Works
checkpoint-status | d7d54a8a-64a4-4041-a968-c1d4d3f95cd0 |  | checkpoint | 2.1 Sub Base
label | 080e24a6-13a7-5fde-962d-d9bbff6612d0 |  | note | FREQUENCY: Each Lot
label | 4af68ec1-7858-58c1-b79e-5e44bbdf08eb |  | note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
label | 2ebc533f-67b6-5806-a6d1-b60624f33d1c |  | note | ○ ITP-001 HP for subgrade inspection signed off
label | a81717e3-07ab-536c-8f4d-ee7113770225 |  | note | REFERENCE DOCUMENTS: VicRoads 173.03
label | 28b5f8c9-c3ff-52cf-84da-6bec7948948b |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | 77e78472-13c2-567d-b271-e7b67ecc0056 |  | note | RECORD OF CONFORMITY: This ITP signed
label | bf7e570f-c29d-544f-8f55-ceb4889dcaac |  | note | HP*
label | d6f53808-3646-5407-b294-795dfe1e722e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c12b4471-e199-500c-96e5-8f97ecf2b6b3 |  | textbox | Date Completed:
checkpoint-status | 55bb811d-5768-497f-83e8-3cafafb715ab |  | checkpoint | 2.2 Spreading material
label | 64f50c4a-33d5-5f48-a023-3fa5e0797a22 |  | note | FREQUENCY: Each lot
label | 00980653-4317-5783-b10b-fe5a39864224 |  | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
label | b71159d9-6a3e-5dd2-a922-7cc283febce3 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
label | 03e809f1-72e5-5aa0-8c48-48032d9d9a13 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | afab0205-fbe0-51a4-8a11-836bdc98fb5e |  | note | RECORD OF CONFORMITY: This ITP signed off
label | b909bfec-6cc7-5be3-8641-bcc2a260986c |  | note | IP
label | 3455ab92-2464-5230-ae75-17607de580c6 |  | note | RESPONSIBILITY: FH Engineer
text | 49f0405b-92ea-5003-8737-11054aed9ba8 |  | textbox | Date Completed:
checkpoint-status | 958f6743-5650-4835-bc46-dc23faa6b563 |  | checkpoint | 2.3 Compaction
label | e646ffdf-24a8-5139-9fba-fa89073d6549 |  | note | FREQUENCY: Each lot
label | 4453f019-f50d-55dd-a17b-9738f5c4f548 |  | note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content.
label | ec4bbe44-74cd-53df-a842-a9f429ea4502 |  | note | ○ Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction.
label | 499497fc-435a-5376-a93b-76214895a8be |  | note | ○ Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test.
label | 42f788bd-f8f8-5ef8-a20d-d6370e46e03b |  | note | ○ Compaction testing shall be carried out once per days production and shall comprise of three samples
label | d9d91c55-8bd7-582e-a84a-d0b34f566981 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
label | 932600e7-3a15-54e3-a94e-4d92befe679a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 44805c2c-024f-5918-a6f1-10913fbf23d8 |  | note | RECORD OF CONFORMITY: Test Results
label | 2fafcf51-dd27-5d6a-99fd-9f4746d220bf |  | note | TP
label | f9319021-92ef-558f-9082-dcbb16ef9583 |  | note | RESPONSIBILITY: FH Engineer
text | f686983b-8619-5de6-80d8-7535147e926d |  | textbox | Date Completed:
checkpoint-status | 5412c00c-b53b-48c8-aeb9-c11b104ec088 |  | checkpoint | 2.4 Level Checking and Conformance
label | 597a2e80-34fb-5a56-beae-40cf157ed39f |  | note | FREQUENCY:
label | 85db82f0-b4de-5330-9652-ff6e2bbe7827 |  | note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
label | 8854abbf-64b4-5773-bd3e-345d7804f41f |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
label | 45b833d2-e2fb-5d14-b952-27d46d77eb6d |  | note | INSPECTION/TEST METHOD: Verify
label | 53923b04-6d73-57f7-b9e3-1598c47f106d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | ad1f2295-a095-50ff-a5a2-efee1c524c47 |  | note | IP
label | a1232f0c-2d58-5c7a-84aa-bd46f14e3c75 |  | note | RESPONSIBILITY: FH Engineer
text | cde588f7-2722-5653-a899-d7afb7b4e6dd |  | textbox | Date Completed:
checkpoint-status | a538db62-12a7-49dd-9093-af99a4c31a64 |  | checkpoint | 2.5 Finished surface
label | 4bd85a91-3a59-527e-b47e-ac1ae1c30a8c |  | note | FREQUENCY: Each lot
label | 25e6b7bb-f1c3-5d69-be01-1735c74d6b0c |  | note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
label | f1253372-f8c4-5ca7-a59e-7cb65d767c7c |  | note | ○ Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
label | c16e740b-516d-5e81-b791-dfdf94c5551c |  | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 CL4.2.2.8, Contract drawings
label | 412f9c6e-18af-5ba9-8ff9-8a22e2f98a52 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 863d5763-e9c6-540b-915c-329ce51011d2 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 6f95f839-9094-585e-9ed0-f7e65ed02040 |  | note | SCP
label | a1c12491-c27c-5c69-adce-36b3ebcb4b6d |  | note | RESPONSIBILITY: Surveyor/ FH Engineer
text | 86d1b591-c440-5ea2-b1fe-9a9895dedc29 |  | textbox | Date Completed:
checkpoint-status | eb7b4c8d-863d-4692-9356-b8a5ca623085 |  | checkpoint | Final Inspection
label | 605c1b34-a717-50cd-a7d5-991f2a98d18d |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 52d71977-6ae3-579f-8436-332969447425 |  | textbox | Print Name:
text | 528c7ebf-37e1-5e53-8fa7-ccb013738ab5 |  | textbox | Position:
text | ec7b00c0-9409-5d55-a9fd-1f8d3c044146 |  | textbox | Date:
checklist-sectioned | dc0dc47e-2e0d-418f-9de2-b4b51ff789c4 |  | checklist | ITP-006 - Track Placement Rev3 | itp |  |  |  | Yes | ITP-006 - Track Placement Rev3 | eb749c76-f48a-447f-aed8-3423ee721b8e
checkpoint-group | 67692fb1-2d96-44f8-9ba8-3f74ebc86a27 |  | section | Preliminary Works
checkpoint-status | 2a4944e3-caab-40c7-af24-bea41d6d3c59 |  | checkpoint | 1.1 Check for correct documentation
label | d5754261-74a8-536a-b0a4-d53febdf5f60 |  | note | FREQUENCY: Prior to commencing works
label | 920eda08-af6e-5c4c-bd11-9094f71d270e |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
label | b71005a4-a7c6-59c6-8da5-73efa67889de |  | note | REFERENCE DOCUMENTS: Design Drawings and Register
label | 1cefe0c2-13e5-5603-9ccd-b50ca7dea866 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 55146f46-980a-5de0-ab1f-04f3b501701b |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 2c4d6495-76b5-5ee2-aeed-dbbd57b0da49 |  | note | HP*
label | 219e1230-1e18-5c25-b5ae-b66f04f2a990 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 807b6aec-09f6-5f65-a5f9-173eb39638a8 |  | textbox | Date Completed:
checkpoint-status | 3aa1ff37-d561-42df-8bca-0dcf99ac43fa |  | checkpoint | 1.2 Check materials
label | 92977fc2-2e9b-5587-b86d-a5edf54467fe |  | note | FREQUENCY: Prior to commencing works
label | 36ef8c8c-5e31-50a4-b36b-95ec438f4dd6 |  | note | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
label | 7bf0ea67-57c9-5414-b9b0-7cf94ef8b60e |  | note | ○ Check condition of rail sleepers
label | 6206d608-53a6-53fb-b18e-7d8a8ea8c168 |  | note | ○ Ensure rail jewellery is of sound condition
label | 2c67cd05-c43d-55aa-a689-c15a87a77769 |  | note | REFERENCE DOCUMENTS: AS 1085
label | cc56c9a5-0608-5682-896f-d38a5213690e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 31fc82d3-daca-55f6-af5a-9ce33051a181 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 6dc98fe5-084e-500a-aed6-6d8b843272bc |  | note | HP*
label | 9734a74c-7c86-5dbc-9e2a-075079c17223 |  | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
text | 19db69c0-738d-509b-bb4e-3ece94747cec |  | textbox | Date Completed:
checkpoint-status | 317c24a9-43c3-4b1d-8bc9-8c907672d22d |  | checkpoint | 1.3 Check special works components
label | 5c68bb75-09fe-5000-a97f-19b4c7335cd9 |  | note | FREQUENCY: Prior to commencing works
label | d9f4791e-29e5-56b4-ac63-7e47a2a4dc3c |  | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
label | 5b8e0fc1-ce8c-594c-84c5-a0a3ea914ef3 |  | note | ○ Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails. Superintendent to visit yard from intial inspection of the rail and fabrication plans.
label | b5eb4387-d082-5212-9c43-33ba6d675c82 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
label | 811bc705-e955-5183-aa30-9cfb0d77763f |  | note | INSPECTION/TEST METHOD: Verify
label | 6b0d7698-712f-51cb-abbc-19a3cfdc6486 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 1f0cf046-8f11-5b0d-b20f-5f01bc4111fd |  | note | IP
label | 7026087e-fefe-568a-9724-e031e11e6f4c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 0ec873c8-66a5-5c74-8349-ef5943b9e132 |  | textbox | Date Completed:
checkpoint-status | 22630dd4-13c9-4c5e-afd2-aed0e36de3ad |  | checkpoint | 1.4 Check curved rail
label | c6c0f9b8-b3e2-5f85-b8ca-76de87f3fdbe |  | note | FREQUENCY: Prior to commencing works
label | df19d030-a221-5b14-9bd8-1e0895c0d3d8 |  | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
label | 7f64e723-67ad-52ca-a4ea-3b119d50c2d6 |  | note | ○ Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails. This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
label | dd8919c2-4d40-554a-9848-13547ed6d29b |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
label | 6c1e4958-233a-522f-8f9c-bdd44b86a01e |  | note | INSPECTION/TEST METHOD: Verify
label | 1c54f631-685b-5c89-9db9-2ec5e834fa9e |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | dcd5367f-aaad-5ee3-b12f-95fabe60dc36 |  | note | HP*
label | 200165cc-6522-59ab-b4cd-fdabebac4e76 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 65ae8bd5-c4fb-5129-895a-f728faa8ba1b |  | textbox | Date Completed:
checkpoint-status | 5e59b6d6-8574-4e7e-8d9e-1ea669e5f451 |  | checkpoint | 1.5 Welders qualifications
label | 330f437d-453f-5624-a445-cd27a1aa0ea2 |  | note | FREQUENCY: Prior to commencing works
label | 48413068-a892-53bd-979c-299d3bac8235 |  | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements; TLIW2012 Grind Rails
label | a9614f4c-fc4b-57f1-b0e6-eb5dd65407a2 |  | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
label | 778abe95-ff1c-5ed2-a455-339d89f0fec1 |  | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
label | 6a0c639f-e798-5003-839b-d57fc1aac62b |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | d7352bf1-e31c-503c-ab02-6d9ff6cf5d90 |  | note | INSPECTION/TEST METHOD: Verify
label | 9ecd3c88-8361-5be4-82cd-0228c159681d |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 959e3ab9-8223-5540-9d6b-0c42fcad4805 |  | note | HP*
label | fc309662-1d0b-5623-94e5-3a4430aa63ef |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | a22dae03-d59c-5d7f-94d5-b4ed7e1d8095 |  | textbox | Date Completed:
checkpoint-status | 82301405-68d7-4a58-ac93-be972a4df894 |  | checkpoint | 1.6 Ultrasonic testers qualifications
label | 28ed0e8b-9c6d-5273-816e-5ca2912eef62 |  | note | FREQUENCY: Prior to commencing works
label | 592b6378-b214-5c03-9616-274e9a25c3d0 |  | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing.
label | 9c681567-6f9e-5606-8096-724872c7266d |  | note | ○ Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
label | b142ee05-99e4-5395-aa4f-c1e79c78f8bb |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | 410c0d37-f6e5-50f9-ad78-2012da5a5387 |  | note | INSPECTION/TEST METHOD: Verify
label | a37205c0-f70d-5221-93bf-ec6b6dd762c4 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 1377fdf9-5362-5c9a-8068-849870e40a3a |  | note | HP*
label | eb56ea25-7456-5a7b-9aed-a14a34d51d0e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | e6e223b8-44fe-5259-8825-89f27312dc1b |  | textbox | Date Completed:
checkpoint-group | e32b4a26-4997-43ed-aecc-250fd75f0fa4 |  | section | Construction Works
checkpoint-status | 92577a94-b439-4b79-9533-ffb949fc28b9 |  | checkpoint | 2.1 Installation of sleeper
label | c84b7163-58c4-572e-93d0-21b6ee2b2136 |  | note | FREQUENCY: Each lot
label | e0087637-da0e-503e-99b3-1ec7e224d874 |  | note | ACCEPTANCE CRITERIA: Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
label | 42a43b45-bd5a-5522-a8c7-44b54a5dbd0a |  | note | ○ Dual block sleepers shall also comply with the design offsets at each chainage
label | 780f6d5c-8ba0-5deb-a4ce-50855e2e4a3b |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
label | 19530ea4-a503-5bdc-93fb-68dde44f9466 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 32a280cd-7c1f-5b20-9075-e84a8b95c7f1 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | f4c5db8d-bb58-56d4-99e3-3cad02e8d91a |  | note | IP
label | 96dc1309-61f4-5a52-8b4e-99ef4c1f7211 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 66d2a5cb-d0dc-5d4e-b762-f93346365474 |  | textbox | Date Completed:
checkpoint-status | 04e1abf4-e1f6-41be-af14-da91b717d65b |  | checkpoint | 2.2 Placement of rail
label | fd28bcfa-d5a3-5fc4-8b5a-4b537761fcbb |  | note | FREQUENCY: Each lot
label | 15b10c85-7fea-58f7-945f-602bde83c539 |  | note | ACCEPTANCE CRITERIA: Ensure rail strings conform to rail plan
label | 17e4b0f9-2a8b-5126-8823-3d491932eaec |  | note | ○ All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
label | 262bf3de-4b68-5fbf-a052-49c44d01d101 |  | note | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
label | 0d76b75e-dec1-5200-9be2-e942dd79785d |  | note | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
label | 67f39cc0-9266-55b9-8052-0f437f68cc9f |  | note | ○ Geometry tolerances as follows:
label | 44848a92-aea4-515d-81df-a82a302c655e |  | note | – Centreline location: +/- 3mm
label | c8d8effe-ba76-5ba3-812c-85b5d74eb3a1 |  | note | – Level: +/- 3mm
label | 615f2d76-4a03-5daf-acbd-682d3c2a8a76 |  | note | – Line measured (>10m chord): +/- 3mm
label | b29689ee-5067-50ff-be9f-f42b1791c9f8 |  | note | – Twist (3.5m chord): +/- 2mm
label | 0d940fc0-a308-5e29-a4c6-5bd31e360ff6 |  | note | – Cant: +/- 3mm
label | 9500e362-4ee7-5419-9809-d8de768e18cd |  | note | – Gauge (open track): +3mm, -0mm
label | a3398c1f-c670-5875-af25-9e40d60f682d |  | note | – Gauge,Turnouts (opposite crossings):+2, -0mm
label | ce372d3f-5bcc-5b09-8572-12fd8979572d |  | note | – Gauge, Diamonds and ‘H’ Crossings:+2, -0mm Note: Cant shall be applied uniformly over transitions
label | 8ea8235a-9d1f-586b-9a81-29031e107f1a |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
label | 2609c144-3e7c-5815-86a3-428dcb845e77 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8808cbbf-3d0b-571c-86a5-1e6a8af21938 |  | note | RECORD OF CONFORMITY: Completion of track charts
label | 918a3f8d-c05e-5d3d-a7b7-d2bf8f403fbf |  | note | HP*
label | 82c50e97-e838-5339-b11d-011186b7bcf3 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 30fd816b-4db1-54bc-a986-03a42595c46b |  | textbox | Date Completed:
checkpoint-status | ac8e4dc9-5c11-4959-a58f-bd084a15a7de |  | checkpoint | 2.3 Placement of jewellery
label | 68d73913-9a50-5403-8dd3-1c0856ecd9f2 |  | note | FREQUENCY: Each lot
label | 4af6c506-7ef1-5792-a798-ec4c5e11cc38 |  | note | ACCEPTANCE CRITERIA: Each sleeper shall be fastened to track with approved jewellery and rail clips
label | 5f065255-cd4c-538b-b301-69cdf0ff47ff |  | note | ○ Clips shall be installed with panpuller or equivalent
label | 789f3b52-431f-5303-a821-a469785090b3 |  | note | ○ All fasteners shall be sealed as per agreed method with Yarra Trams
label | 4ba37467-2926-5839-9b6a-1feba9ce5597 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
label | 1886eaf9-75c2-511a-8811-9b4ebf4f45cd |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | dfe7baff-178e-5d69-a4d8-ee158ffef640 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 2310cbba-0b7f-570a-ab86-a1b103671e31 |  | note | WP
label | 2b2d1e48-52f7-5c6e-bd75-72c9d1d3a508 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 617daa30-79e2-5851-b9d5-a574ecf9b30f |  | textbox | Date Completed:
checkpoint-status | 41f12393-310e-4fde-bf1b-56b738b658cc |  | checkpoint | 2.4 Rail end preparation
label | 7ebf5a2d-a98e-585f-867e-8e929af6e1fb |  | note | FREQUENCY: Each lot
label | 3d178745-7dae-5a22-9b86-88d4a5fe7dbf |  | note | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
label | 7cb4f0e2-96b3-5445-b03d-18ba7d9547f7 |  | note | ○ Minimum closure length from proximity of welds shall be 2m
label | f0e9dac9-be31-5459-9a4e-85413a8e0664 |  | note | ○ Rail end conditions shall match (i.e flame cut - flame cut)
label | 6d0fe7dd-778b-5fbb-9626-a6eb18de147e |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
label | c8798861-999c-5257-9d02-ecc0c54574d2 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 669e6efe-b8ea-53b1-b099-f423b1b5eb70 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | ea2f2222-c50e-57fe-9885-53d157311aeb |  | note | WP
label | a92cc6f2-9413-59ff-b6f5-c5f135e81b15 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | f85bfa07-b46f-56ea-8025-0556ce78ee0a |  | textbox | Date Completed:
checkpoint-status | e7103fcd-8911-46eb-bf98-8f50aac9b1bc |  | checkpoint | 2.5 Welding of rail
label | d5179c73-2056-5779-8456-6a8fa073f334 |  | note | FREQUENCY: Each lot
label | 57bf0818-7c48-523c-97c4-e18336521987 |  | note | ACCEPTANCE CRITERIA: Joints shall be square across the track
label | 0ea199ef-bc4e-5d61-ad09-4e7cfaf8ecd4 |  | note | ○ Maximum skew at square joints shall be 65mm
label | 01fe91ac-7d05-54d3-b578-88f6a3365c79 |  | note | ○ Portions shall match rail type (i.e HHR, Ordinary)
label | 493d0479-60e3-5e56-96a4-0c8f149dd4e5 |  | note | ○ Welds shall not be within:
label | d26612d8-8e9f-5d50-893d-4ec787d09132 |  | note | 3m of another weld
label | 35c6d442-1629-5efb-a1d1-d4601c207d11 |  | note | 3m of a rail end
label | f9533dee-f509-5688-b782-f3932d37dbaa |  | note | 1.5m of a glued insulation joint assembly
label | 24e712c8-dc91-5efb-ad4c-bbec9872b702 |  | note | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
label | 2ecd698b-7062-540f-9fea-53b8f2b4a1e7 |  | note | ○ Weld Return forms shall be completed by qualified welder
label | 75c62a6e-ab2e-5a52-9c56-fbd39d7648f9 |  | note | ○ Welds shall be grinded after 1 hour
label | 83b3c4ab-838a-5864-b92f-2e53b3f43db0 |  | note | ○ Welds shall be free of water
label | 84d59b2c-6330-54f9-b271-7977bd7762c8 |  | note | ○ Post grinding, welds shall be cleaned for visual inspection
label | 5bfea3b2-8f24-5dea-acb7-e9f26fea4e96 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9. & Appendix C AS1085 Code of Practise SkV Elite Welding Proc.
label | 821174d5-d63c-54e3-b4fc-a678631f60cf |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d10ee702-af9d-578c-a94d-bc369e899f4a |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 9c3c469b-4986-566a-9c29-fdc901c9f7d8 |  | note | TP
label | 352e9032-683b-5a29-a885-719d51a8dbbc |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c862daed-623b-50c9-871e-d185bb9ad5de |  | textbox | Date Completed:
checkpoint-status | 0af55250-8c73-4934-92fe-c77ce2a411a2 |  | checkpoint | 2.6 Grinding & cleaning welds
label | 4e8d904d-7914-567e-b6dc-99fb6d79915f |  | note | FREQUENCY: Each lot
label | eaaf3f86-e9b4-5fe9-b8a7-c4e19179c645 |  | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
label | db0e4b4a-07cd-5750-a7aa-fddc0b2739e1 |  | note | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
label | dd96ea14-e1bc-5e2b-8474-8b2c79bfbbb1 |  | note | ○ The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
label | 02d95c95-f7c3-5eee-92e4-f63c5c27ae4c |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | 0ec700e8-d0ff-5bb3-9b03-1d9074f10e89 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | dc34fd73-b6f4-5587-839a-27a9d440d018 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | a2cc0549-8597-5c6a-8238-7560bf4de10c |  | note | IP
label | 050e9169-b7e2-55d0-951c-14cf054f2980 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b635abc4-9f15-570a-83e3-c82227cbcca1 |  | textbox | Date Completed:
checkpoint-status | dccc8adc-83fc-4674-a7b6-53ead6dd0ce2 |  | checkpoint | 2.7 Track adjustment
label | 068e1a27-657d-53ca-97e7-6595f850ff1f |  | note | FREQUENCY: Each lot
label | 8f6a3b7d-16c6-5c17-8d93-9d867995d651 |  | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with an approved type of thermometer.
label | a91ce94c-f5c0-510b-abe8-683852c6fde8 |  | note | ○ In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
label | 4b880c5f-840d-5f95-b998-c190886e7e83 |  | note | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
label | 0c655d26-6bd7-5365-b987-8c2927b96846 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C STD T9008
label | 28b9b79c-00cf-57db-a83f-14c8f4855d9f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 17b2906d-5aa4-57bd-9f2a-50487f2afcdf |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 32472a75-1a7b-58d5-bf02-ba754ee566c6 |  | note | IP
label | afe58108-368d-5a6d-8af3-d77b2f467c7f |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 634c91da-bcde-5d0c-96e5-0d50861718c7 |  | textbox | Date Completed:
checkpoint-status | 17a273f8-986a-4c8e-abcc-22c3b59afd70 |  | checkpoint | 2.8 Track bonds
label | cba75610-8e7f-5b21-9d5e-88b163d863f1 |  | note | FREQUENCY: Each lot
label | f3c49f08-3368-53f3-ad44-fcc92cda0cd5 |  | note | ACCEPTANCE CRITERIA: Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
label | e938a1c9-7bcd-591f-830c-7bd7abae6b6e |  | note | ○ Ensure bonds are sealed as per agreed method with Yarra Trams
label | 50eb030a-f0e3-550e-98df-ac00e67abc4c |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4 Appendix C Design Drawings
label | dfc6cd1c-3504-59c5-bd7a-a04fe199b846 |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | e3a5f3e0-615e-54b1-864f-0b1138a06631 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 1978efae-3a1f-51b2-a4ba-e3553451ce4a |  | note | IP
label | c7fd3d3b-8cc7-5b42-856c-ff313bcda18e |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 8ee31893-8f28-5c29-9e5d-dda71f3ae063 |  | textbox | Date Completed:
checkpoint-group | 701d980d-df36-4bb8-9de9-3b90b8e7bc37 |  | section | Testing
checkpoint-status | 88a34ab7-6a51-4cc2-a8da-291c5eb938da |  | checkpoint | 3.1 Track testing
label | 7532c138-6d64-588c-8a81-f1ab40f28b6f |  | note | FREQUENCY: Track testing
label | 36742b68-a8c8-5d6f-83c3-d9a2a63610ad |  | note | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator.
label | 0d8cd370-40af-5677-851f-cf632d729bf6 |  | note | ○ Failed welds shall be cut out and replaced
label | cc4fa4ac-5a24-5be6-8ede-0f49ecd8a6fa |  | note | ○ Testing documentation shall be recorded and supplied to the superintendent
label | a1be98e8-faa2-53ac-a845-5fb0fe2ca612 |  | note | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | 58b98d93-d084-500b-a494-af67385a023f |  | note | INSPECTION/TEST METHOD: Inspection / Test Method
label | 834bd05a-a059-528f-a9cb-99b118663448 |  | note | RECORD OF CONFORMITY: This ITP Signed Off
label | 124b889d-8997-51d1-98da-6689059d8e3c |  | note | TP
label | 57a430aa-52df-5559-927c-44597ddf1a5a |  | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
text | a1aee555-e194-5b33-bd02-0501c5cf940c |  | textbox | Date Completed:
checkpoint-status | 29afa25a-be9e-47b8-88a6-9a8fa1267c5d |  | checkpoint | Final Inspection
label | ffca4ec0-fbcc-54fd-8110-a902d5b70493 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | dbc534cc-b227-5ada-9237-34f45ff68fac |  | textbox | Print Name:
text | fcf5bc42-41e4-5353-a125-1df41b0fb3d7 |  | textbox | Position:
text | 63ec8a2e-161e-5dbb-8e2a-57749d6c623f |  | textbox | Date: