## Table 1
SEWER | MAIN RETICULATION |  |  |  |  | ITP No. CHA -01-ITP- SEWER 183011 | [6 empty] | Inspection Key C Check H Hold Point IP Inspection Point R Review S Subcontractor V Visual Verification WP Witness Point | [6 empty] | Responsibilities PM Chadoak PM LH Chadoak LH SP Supervisor SU Surveyor SR Spark Representative WR Water Authority (YVW)
Job Address: Calder level crossing removal
References: |  |  | WSA 02 – 2014-3.1 Project Risk Management Plan (PRMP) MRWA Standard Drawings Project Drawings – 21217s1B | [9 empty] | Prepared By: Renee Warren | [6 empty] | Date: |  |  | 2024-01-24
[13 empty] | Reviewed By: Luke McFarlane | [6 empty] | Date: |  |  | 2024-01-31
QM Approved for Use:
ITEM NO | OPERATIONAL ACTIVITIES |  |  | PERFORMANCE CRITERIA | [7 empty] | INSPECTION or TEST by
|  |  |  | Specification |  | Acceptan ce Criteria |  |  | Test/ Inspection Frequency |  |  | Key |  |  | By |  | Record/ evidence |  | Signed Responsible Representative
1.0 PRELIMINARIES
1.1 | The current Water Authority Approved revision drawings are being used including subcontractors copy |  |  |  |  | Current revision drawings are being used, ensure drawings have been Issued as IFC |  |  |  | Each Lot. |  | R |  |  | P M SP |  | This ITP signed
1.2 | Applicable Permits obtained (includes Excavation Permits, DBYD, Road Opening Permits & etc.) |  |  | Design Drawings (Refer to General Notes & Legend) |  | Permits obtained prior to demolition or construction from the relevant authorities |  |  |  | Before job start |  | R |  |  | P M SP |  | This ITP signed
1.3 | Site Set out Survey |  |  | Design Drawings |  | Confirm extent of works and ensure all services are pegged/marked Clearly labelled offset pegs indicating chainage and depth to invert. Ensure survey set out is to latest revision of drawings |  |  |  | Before job start |  | R |  |  | PM |  | Survey Pegs, records
2.0 MANHOLES
2.1 | Concrete Manhole |  |  | MRWA-S- 518 MRWA- S-520 |  | . Ensure Concrete Manhole are installed as per MRWA-S- 518 & 520 as per figure 518-F | [5 empty] | WP |  |  | SF | ITR-S-05.6
2.2 | Access Ladder |  |  | MRWA-S-314 |  | Ensure Access Ladder are installed as per MRWA-S-314 | [5 empty] | WP |  |  | SF | ITR-S-05.2 ITR-S-05.3 ITR-S-05.4 ITR-S-05.5 ITR-S-05.6 ITR-S-05.7
2.3 | Manhole Lid |  |  | IFC |  | Class B concrete lid to used
3.0 PIPE BACKFILL & COMPACTION
3.1 | Backfill Compaction |  |  | WSA 02–2014- 3.1 Section 20.1.4 Table 21.7 IFC MRWA Backfill Specification Design Drawings MRWA specification No. 04-03.2 |  | Material to be compacted in layers as specified Standard compaction test as nominated on the design drawings. 20mm CL4 or CL3 crushed rock or crushed concrete backfill. |  |  | Tests determined by length of section and depth |  |  | WP |  |  | SF | ITR-S-06
INSPECTION & TEST PLAN
Chadoak Pty Ltd, 168-188 Wellington Rd, Clayton, 3168, Vic, ABN: 46 005 063 249
WATER MAINS INSTALLATION CERTIFICATE OF COMPLIANCE & CONFORMANCE This certificate of compliance has been issued as verification that the following inspections and tests have been completed in accordance with the associated inspection test plan, and the installation has been deemed conforming and meets the quality control acceptance criteria prescribed
Project: |  | Calder level crossing removal – Authority works |  |  |  |  | Work Location: |  | Calder Park Drive Hillside | [8 empty] | Issue Date: |  |  |  | 2024-01-16
Inspection & Test Description |  |  |  |  | Work Zone Inspected Tested |  |  | Measuring Equipment Identification Reference | [5 empty] | Foreman / Supervisor |  |  |  | Signature | [5 empty] | Date
Final Inspection Verification Inspections tests have been completed |  |  |  |  | Foreman: | [5 empty] | Signature: | [9 empty] | Date:
Final Inspection Approval Inspections tests have been accepted |  |  |  |  | Project Supervisor: | [5 empty] | Signature: | [9 empty] | Date:
Plumbing Industry Commission Certificate of Compliance issued for hydraulic installation |  |  |  |  | Project Supervisor: | [5 empty] | Signature: | [9 empty] | Date: