## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-148-CIV-CPD-Chadoak Water Main Relocation | itp |  |  |  |  | ITP-148-CIV-CPD-Chadoak Water Main Relocation Rev 0
section | Referenced Documentation
checkpoint-no-status | Referenced Documentation
label | Document Title: CHA-02-ITP-WATERMAIN
label | ITP Description: WATER MAIN RETICULATION
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 24/07/2023
label | ITP created by: Daniel Griffin
label | References: WSA 03-2011-3.2 Project Risk Management Plan (PRMP) MRWA Standard Drawings
section | 1.0 PRELIMINARIES
checkpoint | 1.1 - The current Water Authority Approved revision drawings are being used. including subcontractors’ copy
label | Acceptance Criteria - Current revision drawings are being used, ensure drawings have been Issued as IFC
label | Test/Inspection Frequency - Each Lot
label | Key - R
label | By - PM SP
label | Record/evidence - This ITP signed
checkpoint | 1.2 - Applicable Permits obtained (includes Excavation Permits, BYD, Road Opening Permits, YVW Approvals & etc.)
label | Specification - Design Drawings (Refer to General Notes & Legend)
label | Acceptance Criteria - Permits obtained prior to demolition or construction from the relevant authorities
label | Test/Inspection Frequency - Before job start
label | Key - R
label | By - PM SP
label | Record/evidence - This ITP signed
checkpoint | 1.3 - Check pipeline material’s compliances
label | Specification - Design Drawings WSA 03-2011-3.2 Section 12.1
label | Acceptance Criteria - Use only products and materials specified by the Project Specification, Design Drawings or as approved by the Water Agency
label | Test/Inspection Frequency - Before job start
label | Key - R
label | By - PM
label | Record/evidence - Material Certificates
checkpoint | 1.4 - Delivery and On-Site Storage of Pipes and Fittings
label | Specification - Manufactures Requirements WSA 03-2011-3.2, 11.5.3.4
label | Acceptance Criteria - Goods received satisfactory condition. Handled and stored in accordance with manufacturer’s recommendations.
label | ○ Pipes are clean and free of mud/debris.
label | ○ Pipe Ends to be capped prior to installation to avoid Debris entering Pipe
label | Test/Inspection Frequency - Each Delivery
label | Key - R
label | By - PM
label | Record/evidence - This ITP signed
checkpoint | 1.5 - Delivery of Pipe Bedding and embedment
label | Specification - WSA 03-2011-3.2 14.2
label | Acceptance Criteria - Material to comply with WSA requirements. Material from an approved quarry From the Approved Products List
label | Test/Inspection Frequency - Each Delivery
label | Key - R
label | By - PM
label | Record/evidence - Material Certificates
checkpoint | 1.6 - Site Set out Survey
label | Specification - Design Drawings
label | Acceptance Criteria - Confirm extent of works and ensure all services are pegged/marked.
label | ○ Clearly labelled offset pegs indicating chainage and depth to invert.
label | ○ Ensure survey set out is to latest revision of drawings
label | Test/Inspection Frequency - Before job start
label | Key - R
label | By - PM
label | Record/evidence - Survey Pegs, records
section | 2.0 EXCAVATION (TRENCHING)
checkpoint | 2.1 - Excavate Topsoil within Clearing Limits
label | Specification - WSA 03-2011-3.2 13.12
label | Acceptance Criteria - Prior to excavating trenches, remove topsoil within the width of the Formation to a depth of 150mm
label | Test/Inspection Frequency - As required
label | Key - SP
label | Record/evidence - ITR-W- 02
checkpoint | 2.2 - Excavate to required Width and Depth
label | Specification - WSA 03-2011-3.2 13.9.1 MRWA-W-202
label | Acceptance Criteria - 1. Keep sides of the excavation vertical to at least 150 above the pipes in strata other than sand.
label | 2. Lay marking tape along route of the water main as per WSA03- 2012, MRWA edition.
label | 3. Maintain minimum clearances between mains and services in accordance with Table.
label | 5.5 of MRWA edition of WSA 03-2011.
label | 4. Excessive excavation to be treated in accordance with MRWA edition of WSA 03- 2011. 5. Lay pipes in a shared trench at the same invert level where possible.
label | 6. Maximum cover is 1.5 x minimum cover. This does not apply where main crosses under other services.
label | 7. Cross water mains above other services (except Gas) wherever practical. When water mains pass under other services or obstructions, clearance under the obstruction or other service shall be minimised.
label | Test/Inspection Frequency - Each Trench
label | Key - SP/CR (WP)
label | Record/evidence - ITR-W- 02
checkpoint | 2.3 - Ensure pipe work is installed as per Minimum cover requirements
label | Specification - MRWA-W-210
label | Acceptance Criteria - As per Table 210-A
label | ○ Railway 1600mm
label | ○ Waterways 1000mm
label | ○ Tramways 1200mm Major Roads 1200mm
label | Key - SP
section | 3.0 PIP INSTALLATION AND JOINTING
checkpoint | 3.1 - Pipe laying – Confirm Levels
label | Specification - WSA 03-2011-3.2 Section 15 MRWA-W- 202
label | Acceptance Criteria - Pipes are laid to levels, grade, and alignment as per drawings Tolerances:
label | ○ ±100mm lateral
label | ○ ± 50mm vertical
label | Test/Inspection Frequency - Each Pipe Section
label | Key - SP/CR (IP)
label | By - SP (WP)
label | Record/evidence - ITR-W-03
checkpoint | 3.2 - Pipe Joint – Deflection
label | Specification - As per applicable Design drawings. WSA 03-2011-3.2 Section 15.2
label | Acceptance Criteria - Joint deflection shall not exceed the maximum permitted deflection as recommended by the manufacturer.
label | Test/Inspection Frequency - Each Joint
label | Key - SP/CR (IP)
label | By - SP (WP)
label | Record/evidence - ITR-W-03
checkpoint | 3.3 - Pipe & Fittings Jointing
label | Specification - WSA 03-2011-3.2 15.1.4 MRWA-W-103
label | Acceptance Criteria - Pipe to be installed as per manufacturers. requirements.
label | ○ Pipes to have Witness mark and correct chamfer angle.
label | Test/Inspection Frequency - Every Joint
label | Key - SP/CR (IP)
label | Record/evidence - ITR-W-03
checkpoint | 3.4 - Installation of valves, air valves & hydrants
label | Specification - WSA 03-2011-3.2 Section 15.4 MRWA-W- 109, 205A, 300, 301, 302, 303, 304, 305, 307 and MRWA-W-308
label | Acceptance Criteria - Ensure fittings are installed as per specification
label | Test/Inspection Frequency - Every valve and fitting
label | Key - SP/CR (IP)
label | Record/evidence - ITR-W-03
checkpoint | 3.5 - Thrust and Anchor Blocks
label | Specification - WSA 03-2011-3.2 Section 15.7 MRWA-W- 104A, 104B, 204, 205A, 205B, 205C, 206, and MRWA-W207
label | Acceptance Criteria - Ensure anchor blocks are constructed to WSA Standard Drawing WAT 1205 Concrete to be approved supplier
label | Test/Inspection Frequency - Every valve and fitting
label | Key - SP/CR (IP)
label | Record/evidence - ITR-W-03
checkpoint | 3.7 - PE BUTT WELDING
label | Specification - MRWA 15.21.2
label | Acceptance Criteria - All joints for polyethylene mains and fittings are to be butt welded in accordance with MRWA. 15.21.2.
label | ○ Electrofusion welds and fittings are not permitted for use without the express written permission of YVW inspector.
label | ○ Butt welding equipment shall be inspected, tested, tagged, and calibrated every 12 months by an approved agent, and be subject to electrical equipment inspection test in accordance with AS/NZS 3760.
label | ○ Before commencing a welding operation, the operator shall check the machine as per manufacturer’s instructions, and the electrical cord shall not be damaged and check electrical test tag.
label | Conduct visual inspection of weld. Check:
label | – beads are same size and shape.
label | – beads are projected evenly around diameter of pipe.
label | – beads are acceptable height.
label | – no cracks or obvious faults in beads
label | Note: Randomly selected welds from pipeline should be removed and tested during operations.
label | Control static electricity build-up/discharge:
label | – wet entire exposed pipe surface (use anti-static liquid or dilute soap and water)
label | – wrap exposed pipe with wet tape conductors (or similar)
label | – Re-wet as needed.
label | Key - SP/CR (IP)
label | Record/evidence - Poly Weld Joint Report – WSA- ITR- W-03
section | 4.0. Backfill and Compaction
checkpoint | 4.1 - Embedment
label | Specification - WSA 03-2011-3.2 Section 16 Table 19.1 MRWA-W-200, 201, 202, & MRWA-W-203, MRWA Backfill Specification Design Drawings
label | Acceptance Criteria - Material to be worked around pipe to ensure all voids at haunches are filled.
label | ○ Standard compaction test as nominated on the design drawings
label | Test/Inspection Frequency - 1 Test at Start of Works
label | Key - SP (WP)
label | By - WR (WP)
label | Record/evidence - ITR-W-04 NATA Test Sheet
checkpoint | 4.2 - Backfill Material
label | Specification - WSA 03-2011-3.2 Section 17 Dwgs MRWA-W- 200, 201, 202, & MRWA-W-203
label | Acceptance Criteria - Non-Pavement - Backfilled using select backfill material.
label | ○ Pavement - Backfilled using 20mm Class 2 CR to underside of road preparation.
label | ○ Approved Materials to be used
label | Test/Inspection Frequency - Each Lot
label | Key - SP/CR (WP)
label | Record/evidence - ITR-W-04
checkpoint | 4.3 - Backfill Compaction
label | Specification - WSA 03-2011-3.2 Section 16 Table 19.1 Dwgs MRWA-W- 200, 201, 202, & MRWA-W-203, MRWA Backfill Specification Design Drawings
label | Acceptance Criteria - Material to be compacted in layers as specified.
label | ○ Standard compaction test as nominated on the design drawings
label | Test/Inspection Frequency - Tests determined by length of section and depth
label | Key - SP/CR (WP)
label | By - WR (WP)
label | Record/evidence - ITR-W-04
checkpoint | 4.4 - Detectable Marking Tape
label | Specification - WSA 03 2011 Section 15.12
label | Acceptance Criteria - Install detectable marking tape on top of the first compacted backfill layer of all water mains constructed using open-cut Trenching.
label | Test/Inspection Frequency - Entire pipeline length
label | Key - SP/CR (IP)
label | Record/evidence - ITR-W-04
section | 5.0 OTHER ITEMS
checkpoint | 5.1 - Marker Posts
label | Specification - WSA 03 2011-3.2 Section15.18 MRWA 300
label | Acceptance Criteria - Provide location marker posts, plates, and other markings for the location of hydrants and valves as per drawings.
label | Test/Inspection Frequency - Each
label | Key - SP/CR (WP)
label | Record/evidence - ITR-W-04
section | 6.0 TESTING & REINSTATEMENT
checkpoint | 6.1 - Swabbing of Mains
label | Specification - WSA 03 2011 3.2 Section 18.3
label | Acceptance Criteria - Entire pipe network to be swabbed to remove any foreign matter. Swab mains as nominated on the Design Drawings. Ensure Foam swabs are numbered and sized to be flushed through the pipe in full, and two swabs are used for each run.
label | Test/Inspection Frequency - As required
label | Key - SP/CR (WP)
label | Record/evidence - ITR-W-07.1
checkpoint | 6.2 - Flushing of Mains
label | Specification - WSA 03 2011 3.2 Section 18.3
label | Acceptance Criteria - Mains to be flushed in sections through hydrants of washouts which can develop a velocity of 0.75m/s. Mains shall then be drained and filled slowly with clean potable water.
label | Test/Inspection Frequency - As required
label | Key - SP/CR (IP)
label | Record/evidence - ITR-W-07.2
checkpoint | 6.3 - Hydrostatic Testing Mains
label | Specification - WSA 03 2011 3.2 Section 19.4 MRWA 19.4.1.1 Design Drawings
label | Acceptance Criteria - Test Mains to nominated pressure on design drawings.
label | ○ Duration and allowable top up volume as per MRWA 19.4.1.1
label | ○ Test pressures, durations and witnessing recorded on record sheet.
label | Test/Inspection Frequency - As required
label | Key - SP/CR (HP)
label | By - WR/SP (HP)
label | Record/evidence - ITR-W-07.3
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Reinstatement / Finished Surface Levels
label | Specification - WSA 03 2011 3.2 Section 21.4
label | Acceptance Criteria - ±5 mm in road reserves, including sealed pavements.
label | ○ ±5 mm in trafficable, private properties
label | ○ +50 mm, -20 mm in non- trafficable areas
label | Test/Inspection Frequency - Each Lot
label | Key - SP/CR (WP)
label | Record/evidence - ITR-W-07.4
checkpoint | 6.5 - Disinfection
label | Specification - WSA 03 2011 3.2 Section 20.1
label | Acceptance Criteria - Mains >225mm to be disinfected in accordance with the MRWA Water Quality Compliance Specification
label | Test/Inspection Frequency - Each Lot
label | Key - SP/CR (WP)
label | Record/evidence - ITR-W-07.5
checkpoint | 6.6 - Asset Recording
label | Specification - Design Drawings WSA 03-2011 3.2 Section 21 & 24
label | Acceptance Criteria - As-Built survey data, prepared, collated and submitted
label | Test/Inspection Frequency - At completion of each section and the job
label | Key - SP/CR (WP)
label | Record/evidence - As built Survey
checkpoint | Final Inspections Verification/Approval
label | ○ Inspections tests have been completed
label | ○ Inspections tests have been accepted
label | ○ Plumbing Industry Commission Certificate of Compliance issued for hydraulic installation
text | Foreman:
text | Project Supervisor:
date | Date:
holdpoint | Sign ITP
checklist | ITP-149-CIV-CPD-Chadoak Manhole | itp |  |  |  |  | ITP-149-CIV-CPD-Chadoak Manhole Rev 0
section | Referenced Documentation
checkpoint-no-status | Referenced Documentation
label | Document Title: CHA-01-ITP-SEWER 183011
label | ITP Description: SEWER MAIN RETICULATION
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 31/01/2024
label | ITP created by: Renee Warren
label | ITP approved for use by: Luke McFarlane
label | References: WSA 02 – 2014-3.1 Project Risk Management Plan (PRMP) MRWA Standard Drawings, Project Drawings – 21217s1B
section | 1.0 PRELIMINARIES
checkpoint | 1.1 - The current Water Authority Approved revision drawings are being used including subcontractors copy
label | Acceptance Criteria - Current revision drawings are being used, ensure drawings have been Issued as IFC
label | Test/Inspection Frequency - Each Lot.
label | Key - R
label | By - P M SP
label | Record/evidence - This ITP signed
checkpoint | 1.2 - Applicable Permits obtained (includes Excavation Permits, DBYD, Road Opening Permits & etc.)
label | Specification - Design Drawings (Refer to General Notes & Legend)
label | Acceptance Criteria - Permits obtained prior to demolition or construction from the relevant authorities
label | Test/Inspection Frequency - Before job start
label | Key - R
label | By - P M SP
label | Record/evidence - This ITP signed
checkpoint | 1.3 - Site Set out Survey
label | Specification - Design Drawings
label | Acceptance Criteria - Confirm extent of works and ensure all services are pegged/marked Clearly labelled offset pegs indicating chainage and depth to invert.
label | ○ Ensure survey set out is to latest revision of drawings
label | Test/Inspection Frequency - Before job start
label | Key - R
label | By - PM
label | Record/evidence - Survey Pegs, records
section | 2.0 MANHOLES
checkpoint | 2.1 - Concrete Manhole
label | Specification - MRWA-S- 518 MRWA- S-520
label | Acceptance Criteria - Ensure Concrete Manhole are installed as per MRWA-S- 518 & 520 as per figure 518-F
label | Key - WP
label | By - SF
label | Record/evidence - ITR-S-05.6
checkpoint | 2.2 - Access Ladder
label | Specification - MRWA-S-314
label | Acceptance Criteria - Ensure Access Ladder are installed as per MRWA-S-314
label | Key - WP
label | By - SF
label | Record/evidence - ITR-S-05.2, ITR-S-05.3, ITR-S-05.4, ITR-S-05.5, ITR-S-05.6, ITR-S-05.7
checkpoint | 2.3 - Manhole Lid
label | Specification - IFC
label | Acceptance Criteria - Class B concrete lid to used
section | 3.0 PIPE BACKFILL & COMPACTION
checkpoint | 3.1 - Backfill Compaction
label | Specification - WSA 02–2014-3.1 Section 20.1.4 Table 21.7 IFC MRWA Backfill Specification Design Drawings MRWA specification No. 04-03.2
label | Acceptance Criteria - Material to be compacted in layers as specified
label | ○ Standard compaction test as nominated on the design drawings.
label | ○ 20mm CL4 or CL3 crushed rock or crushed concrete backfill.
label | Test/Inspection Frequency - Tests determined by length of section and depth
label | Key - WP
label | By - SF
label | Record/evidence - ITR-S-06
checkpoint | Final Inspections Verification/Approval
label | ○ Inspections tests have been completed
label | ○ Inspections tests have been accepted
label | ○ Plumbing Industry Commission Certificate of Compliance issued for hydraulic installation
text | Foreman:
text | Project Supervisor:
date | Date:
holdpoint | Sign ITP