## Project Structure
Folder Structure |  |  |  |  | Checklists
Site QA
9757 - Mondelez
Switchboard
|  |  | MSSB-1E |  | MSSB checklist
|  |  | MSSB-2 |  | MSSB checklist
|  |  | MSSB-3 |  | MSSB checklist
Ventilation Fans
|  |  | SCF-WH/HB-1 |  | Ventilation Fans checklist
|  |  | SCF-WH/HB-2 |  | Ventilation Fans checklist
|  |  | SCF-WH/HB-3 |  | Ventilation Fans checklist
|  |  | SCF-WH/HB-4 |  | Ventilation Fans checklist
|  |  | SCF-WH/HB-5 |  | Ventilation Fans checklist
|  |  | SCF-WH/HB-6 |  | Ventilation Fans checklist
|  |  | SCF-WH/HB-7 |  | Ventilation Fans checklist
|  |  | SCF-WH/HB-8 |  | Ventilation Fans checklist
|  |  | SCF-WH/HB-9 |  | Ventilation Fans checklist
|  |  | SCF-WH/LB-10 |  | Ventilation Fans checklist
|  |  | SCF-WH/LB-11 |  | Ventilation Fans checklist
|  |  | SCF-WH/LB-12 |  | Ventilation Fans checklist
|  |  | SCF-WH/LB-13 |  | Ventilation Fans checklist
|  |  | SCF-WH/LB-14 |  | Ventilation Fans checklist
Pac Units
|  |  | PAC-WH/HB-1 |  | ERV / HRV Checklist
|  |  | PAC-WH/HB-2 |  | ERV / HRV Checklist
|  |  | PAC-WH/HB-3 |  | ERV / HRV Checklist
|  |  | PAC-WH/HB-4 |  | ERV / HRV Checklist
|  |  | PAC-WH/HB-5 |  | ERV / HRV Checklist
|  |  | PAC-WH/HB-6 |  | ERV / HRV Checklist
|  |  | PAC-WH/HB-7 |  | ERV / HRV Checklist
|  |  | PAC-WH/HB-8 |  | ERV / HRV Checklist
|  |  | PAC-WH/HB-9 |  | ERV / HRV Checklist
|  |  | PAC-WH/CP-10 |  | ERV / HRV Checklist
|  |  | PAC-WH/CP-11 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-12 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-13 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-14 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-15 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-16 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-17 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-18 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-19 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-20 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-21 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-22 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-23 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-24 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-25 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-26 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-27 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-28 |  | ERV / HRV Checklist
|  |  | PAC-WH/LB-29 |  | ERV / HRV Checklist
Main Office
Ground Floor
|  |  |  | FCU-OF-G.1 | FCU-AC checklist
|  |  |  | FCU-OF-G.2 | FCU-AC checklist
|  |  |  | FCU-OF-G.3 | FCU-AC checklist
|  |  |  | FCU-OF-G.4 | FCU-AC checklist
|  |  |  | BB-OF-1 | Branch Box checklist
|  |  |  | CU-OF-1 | AC Condensor checklist
|  |  |  | TEF-OF-1 | Ventilation Fans checklist
First Floor
|  |  |  | FCU-OF-1.1 | FCU-AC checklist
|  |  |  | FCU-OF-1.2 | FCU-AC checklist
|  |  |  | FCU-OF-1.3 | FCU-AC checklist
|  |  |  | FCU-OF-1.4 | FCU-AC checklist
|  |  |  | BB-OF-2 | Branch Box checklist
|  |  |  | AC-OF-COMMS-1 | FCU-AC checklist
|  |  |  | CU-OF-COMMS-1 | AC Condensor checklist
|  |  |  | AC-OF-COMMS-2 | FCU-AC checklist
|  |  |  | CU-OF-COMMS-2 | AC Condensor checklist
Dock Office
Ground Floor
|  |  |  | FCU-DO-G.1 | FCU-AC checklist
|  |  |  | CU-DO-G.1 | AC Condensor checklist
|  |  |  | TEF-DO-1 | Ventilation Fans checklist
First Floor
|  |  |  | FCU-DO-L1.1 | FCU-AC checklist
|  |  |  | CU-DO-L1.1 | AC Condensor checklist
Co-pack/Scorched
|  |  |  | FCU-CP-1 | FCU-AC checklist
|  |  |  | CU-CP-1 | AC Condensor checklist
|  |  |  | FCU-CP-2 | FCU-AC checklist
|  |  |  | CU-CP-2 | AC Condensor checklist
|  |  |  | FCU-CP-3 | FCU-AC checklist
|  |  |  | CU-CP-3 | AC Condensor checklist
|  |  |  | FCU-CP-4 | FCU-AC checklist
|  |  |  | CU-CP-4 | AC Condensor checklist
|  |  |  | FCU-SR-1 | FCU-AC checklist
|  |  |  | CU-SR-1 | AC Condensor checklist
|  |  |  | FCU-SR-2 | FCU-AC checklist
|  |  |  | CU-SR-2 | AC Condensor checklist
|  |  |  | OAF-WH-1 | Ventilation Fans checklist
|  |  |  | TEF-WH-1 | Ventilation Fans checklist
|  |  |  | BCEF-WH-1 | Ventilation Fans checklist
|  |  |  | GEF-SR-1 | Ventilation Fans checklist
|  |  |  | KEF-SR-1 | Ventilation Fans checklist
Gate House/Pump Room
|  |  |  | AC-GH-1 | FCU-AC checklist
|  |  |  | CU-GH-1 | AC Condensor checklist
|  |  |  | TEF-GH-1 | Ventilation Fans checklist
|  |  |  | GEF-PR-1 | Ventilation Fans checklist
Seismic
Equipment
|  |  |  | FCU-OF-G.1 | Seismic checklist
|  |  |  | FCU-OF-G.2 | Seismic checklist
|  |  |  | FCU-OF-G.3 | Seismic checklist
|  |  |  | FCU-OF-G.4 | Seismic checklist
|  |  |  | FCU-OF-1.1 | Seismic checklist
|  |  |  | FCU-OF-1.2 | Seismic checklist
|  |  |  | FCU-OF-1.3 | Seismic checklist
|  |  |  | FCU-OF-1.4 | Seismic checklist
|  |  |  | BB-OF-1 | Seismic checklist
|  |  |  | BB-OF-2 | Seismic checklist
|  |  |  | CU-OF-1 | Seismic checklist
|  |  |  | AC-OF-COMMS-1 | Seismic checklist
|  |  |  | CU-OF-COMMS-1 | Seismic checklist
|  |  |  | AC-OF-COMMS-2 | Seismic checklist
|  |  |  | CU-OF-COMMS-2 | Seismic checklist
|  |  |  | FCU-DO-G.1 | Seismic checklist
|  |  |  | CU-DO-G.1 | Seismic checklist
|  |  |  | FCU-DO-L1.1 | Seismic checklist
|  |  |  | CU-DO-L1.1 | Seismic checklist
|  |  |  | AC-GH-1 | Seismic checklist
|  |  |  | CU-GH-1 | Seismic checklist
|  |  |  | FCU-CP-1 | Seismic checklist
|  |  |  | CU-CP-1 | Seismic checklist
|  |  |  | FCU-CP-2 | Seismic checklist
|  |  |  | CU-CP-2 | Seismic checklist
|  |  |  | FCU-CP-3 | Seismic checklist
|  |  |  | CU-CP-3 | Seismic checklist
|  |  |  | FCU-CP-4 | Seismic checklist
|  |  |  | CU-CP-4 | Seismic checklist
|  |  |  | FCU-SR-1 | Seismic checklist
|  |  |  | CU-SR-1 | Seismic checklist
|  |  |  | CU-SR-1 | Seismic checklist
|  |  |  | FCU-SR-2 | Seismic checklist
|  |  |  | FCU-SR-2 | Seismic checklist
|  |  |  | CU-SR-2 | Seismic checklist
|  |  |  | PAC-WH/HB-1 | Seismic checklist
|  |  |  | PAC-WH/HB-2 | Seismic checklist
|  |  |  | PAC-WH/HB-3 | Seismic checklist
|  |  |  | PAC-WH/HB-4 | Seismic checklist
|  |  |  | PAC-WH/HB-5 | Seismic checklist
|  |  |  | PAC-WH/HB-6 | Seismic checklist
|  |  |  | PAC-WH/HB-7 | Seismic checklist
|  |  |  | PAC-WH/HB-8 | Seismic checklist
|  |  |  | PAC-WH/HB-9 | Seismic checklist
|  |  |  | PAC-WH/CP-10 | Seismic checklist
|  |  |  | PAC-WH/CP-11 | Seismic checklist
|  |  |  | PAC-WH/LB-12 | Seismic checklist
|  |  |  | PAC-WH/LB-13 | Seismic checklist
|  |  |  | PAC-WH/LB-14 | Seismic checklist
|  |  |  | PAC-WH/LB-15 | Seismic checklist
|  |  |  | PAC-WH/LB-16 | Seismic checklist
|  |  |  | PAC-WH/LB-17 | Seismic checklist
|  |  |  | PAC-WH/LB-18 | Seismic checklist
|  |  |  | PAC-WH/LB-19 | Seismic checklist
|  |  |  | PAC-WH/LB-20 | Seismic checklist
|  |  |  | PAC-WH/LB-21 | Seismic checklist
|  |  |  | PAC-WH/LB-22 | Seismic checklist
|  |  |  | PAC-WH/LB-23 | Seismic checklist
|  |  |  | PAC-WH/LB-24 | Seismic checklist
|  |  |  | PAC-WH/LB-25 | Seismic checklist
|  |  |  | PAC-WH/LB-26 | Seismic checklist
|  |  |  | PAC-WH/LB-27 | Seismic checklist
|  |  |  | PAC-WH/LB-28 | Seismic checklist
|  |  |  | PAC-WH/LB-29 | Seismic checklist
|  |  |  | SCF-WH/HB-1 | Seismic checklist
|  |  |  | SCF-WH/HB-2 | Seismic checklist
|  |  |  | SCF-WH/HB-3 | Seismic checklist
|  |  |  | SCF-WH/HB-4 | Seismic checklist
|  |  |  | SCF-WH/HB-5 | Seismic checklist
|  |  |  | SCF-WH/HB-6 | Seismic checklist
|  |  |  | SCF-WH/CP-7 | Seismic checklist
|  |  |  | SCF-WH/CP-8 | Seismic checklist
|  |  |  | SCF-WH/LB-9 | Seismic checklist
|  |  |  | SCF-WH/LB-10 | Seismic checklist
|  |  |  | SCF-WH/LB-11 | Seismic checklist
|  |  |  | SCF-WH/LB-12 | Seismic checklist
|  |  |  | SCF-WH/LB-13 | Seismic checklist
|  |  |  | SCF-WH/LB-14 | Seismic checklist
Greenstar
|  |  |  | Photo Identification | Greenstar checklist

## Checklists
type | name | values
checklist | MSSB checklist
checkpoint | MSSB mounted in position
checkpoint | MSSB labelled correctly
checkpoint | Required clearance provided to MSSB
checkpoint | Cables connected into MSSB and all terminated and labelled
checkpoint | Main power connected to MSSB
checkpoint | MSSB energisation form provided to builder
checkpoint | Fire interface cable supplied & fitted off.
checkpoint | MSSB commissioned and operational
checklist | Fire Damper checklist
checkpoint | Fire damper installed correctly
checkpoint | Fire damper labelled
checkpoint | Fire damper sealed correctly
checkpoint | Photo required of installation
Drop test
checklist | Ventilation Fans checklist
checkpoint | Technical data from Unit, Motor & drives match equipment schedules |  | Solid ductwork install complete and levelled
checkpoint | Equipment Identification labels installed. |  | All flexible/canvas ductwork connections installed
checkpoint | All components installed as per Mechanical shop drawings |  | Fan installed into position and correctly aligned/Level and in direction of flow
checkpoint | Transport bolts and packing material Removed |  | Vibration isolation installed
checkpoint | Mounting and anti vibration mounts installed |  | Dampers installed to duct (NRD, VC, FD, MVCD) Correctly
checkpoint | Fan & motor rotate freely
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Electrical connections complete and Mains power available |  | All items correctly insulated if required
checkpoint | Control wiring complete including any local operating controllers |  | Fire Shutdown cable roughed in
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC |  | VSD installed to Fan including electrical and controls
checkpoint | Mechanical electrical contractor has verified operating voltage & amps |  | Works area tidy and clean of debris
checkpoint | Fan rotation verified by electrical contractor |  | General area inspection for defects
checkpoint | Controls functionality programmed and operational |  | Solid ductwork capped, covered, sealed and seams weatherproofed
checkpoint | System is ready to be put into manual / automatic operation. |  | Overflashings installed and weatherproofed
checkpoint | System has been commissioned & balanced. |  | Filters installed and are removable
checkpoint | Fire interface connected and operational |  | Electrical installation fitted off
checkpoint | System correctly operational & placed into Automatic service. |  | Control works fitted off including all sensors, controllers
Fire Shutdown connected
checklist | AC Condensor checklist |  | Grilles/louvres installed if required
checkpoint | Technical data from Unit,Motor & drives match equipment schedules |  | labels installed
checkpoint | All components installed as per Mechanical shop drawings |  | Take photp of Fan model and serial name plate
checkpoint | Equipment Identification labels installed. |  | All dampers are fully open
checkpoint | Transport bolts and packing material Removed |  | Works area tidy and clean of debris
checkpoint | Mounting and anti vibration mounts installed |  | General area inspection for defects
checkpoint | Condensate drains / safety trays connected and tested for correct operation |  | Equipment ready for commissioning
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Associated interface cards installed and addressed as per manufacturers schematic
checkpoint | M.NET and refrigeration addressing set as per manufacturers schematic.
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Mechanical electrical contractor has energised Condensing units 24hrs prior to energising indoor equipment.
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | Branch Box checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Associated interface cards installed and addressed as per manufacturers schematic
checkpoint | M.NET and refrigeration addressing set as per manufacturers schematic.
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Mechanical electrical contractor has energised Condensing units 24hrs prior to energising indoor equipment.
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | FCU-AC checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Filters installed (temporary pre filter be installed if required)
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Associated interface cards installed and addressed as per manufacturers schematic
checkpoint | M.NET and refrigeration addressing set as per manufacturers schematic.
checkpoint | All volume control dampers in the open position (non motorised & motorised) & stroked correctly to match fire matrix intent
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Mechanical electrical contractor has energised Condensing units 24hrs prior to energising indoor equipment.
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | ERV / HRV Checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Fans & Motors rotate freely
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Filters installed (temporary pre filter be installed if required)
checkpoint | All volume control dampers in the open position (non motorised & motorised) & stroked correctly to match fire matrix intent
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | VSD checklist
checkpoint | Technical data from VSD matches equipment schedules
checkpoint | VSD mounted in position
checkpoint | VSD labelled correctly
checkpoint | Cables connected into VSD and all terminated
checkpoint | Main power connected to MSSB
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | VSD has been commissioned programmed & Parameter list recorded.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | Seismic checklist
checkpoint | Seismic installed as design
checkpoint | Seismic location/drawing
Seismic photos
checklist | Greenstar checklist
checkpoint | PVC pipe
reciepts
Solvents/silicon
Solid Duct plastic wrapped