## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | VRF Wall IDU |  |  |  |  | Yes | VRF Wall IDU | 0759c5d9-2024-4be0-b63d-33219893f2d9
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Ref piping run and sticking out of wall at correct height
checkpoint-status |  |  | checkpoint | Refnets installed
checkpoint-status |  |  | checkpoint | piping connected to branch box
checkpoint-status |  |  | checkpoint | Drains run from IDU to tundish
checkpoint-status |  |  | checkpoint | Drain correct spacing from ref. piping
checkpoint-group |  |  | section | Fit off
checkpoint-status |  |  | checkpoint | IDU installed
checkpoint-status |  |  | checkpoint | piping connected to IDU
checkpoint-status |  |  | checkpoint | Drain connected to IDU
checklist-flat |  |  | checklist | Grilles |  |  |  |  | Yes | Grilles | 0b48fa1f-9c4b-4922-af61-835a1aa7d3f1
checkpoint-status |  |  | checkpoint | Plasterer/carpenter has framed out grilles
checkpoint-status |  |  | checkpoint | Cutout done
checkpoint-status |  |  | checkpoint | Grille installed
checklist-sectioned |  |  | checklist | FIP Testing |  |  |  |  | Yes | FIP Testing | 0d58cbe4-fc21-4bc6-b23e-37516f3eafc9
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | FA operation.
checkpoint-status |  |  | checkpoint | Run indication.
checkpoint-status |  |  | checkpoint | Run override.
checkpoint-status |  |  | checkpoint | Stop override.
checklist-flat |  |  | checklist | Fire Dampers |  |  |  |  | Yes | Fire Dampers | 0e2e81e4-9470-4853-b202-0e3c82625571
checkpoint-status |  |  | checkpoint | Fire damper correctly installed in position
checkpoint-status |  |  | checkpoint | fire damper packing
checkpoint-status |  |  | checkpoint | breakaway bolts securing FD to ducts
checkpoint-status |  |  | checkpoint | Fire rated mastic
checkpoint-status |  |  | checkpoint | Fire damper labelled
checkpoint-status |  |  | checkpoint | Access panels on ducts
checklist-flat |  |  | checklist | VRF Ducted IDU |  |  |  |  | Yes | VRF Ducted IDU | 1b52e739-9dd2-4f26-85da-58f450f2c8b5
checkpoint-status |  |  | checkpoint | AC unit/cushion box positions marked on ceiling
checkpoint-status |  |  | checkpoint | IDU installed
checkpoint-status |  |  | checkpoint | Plenum(s) installed
checkpoint-status |  |  | checkpoint | piping connected to IDU
checkpoint-status |  |  | checkpoint | Refnets installed
checkpoint-status |  |  | checkpoint | piping connected to branch box
checkpoint-status |  |  | checkpoint | IDU cushion boxes installed
checkpoint-status |  |  | checkpoint | pipes insulated
checkpoint-status |  |  | checkpoint | AC flex ducts run
checkpoint-status |  |  | checkpoint | Drain connected to IDU
checkpoint-status |  |  | checkpoint | Drains run from IDU to tundish
checkpoint-status |  |  | checkpoint | Access panel marked on ground
checkpoint-status |  |  | checkpoint | AC grilles framed out by plasterer/carpenter
checkpoint-status |  |  | checkpoint | Penetrations fire rated
checklist-flat |  |  | checklist | ODU / Mini VRF |  |  |  |  | Yes | ODU / Mini VRF | 1c066eb9-1335-40c3-8cc2-745009a361e4
checkpoint-status |  |  | checkpoint | blocks/waffle pad/brackets secured
checkpoint-status |  |  | checkpoint | ODU installed
checkpoint-status |  |  | checkpoint | ODU piping run
checkpoint-status |  |  | checkpoint | ODU piping connected to outdoor unit
checkpoint-status |  |  | checkpoint | Piping insulated
checkpoint-status |  |  | checkpoint | Pipes Capped
checklist-sectioned |  |  | checklist | Ducts |  |  |  |  | Yes | Ducts | 2974d459-d19b-44a2-b835-8342e405d66d
checkpoint-group |  |  | section | Solid Ducts
checkpoint-status |  |  | checkpoint | Run + hanger positions marked
checkpoint-status |  |  | checkpoint | Rods installed
checkpoint-status |  |  | checkpoint | Straight ducts installed
checkpoint-status |  |  | checkpoint | Bends/Transitions installed
checkpoint-status |  |  | checkpoint | Riser ducts complete
checkpoint-status |  |  | checkpoint | Foam tape / gaps sealed on all ducts
checkpoint-status |  |  | checkpoint | Cleats installed
checkpoint-status |  |  | checkpoint | Peno flashings installed and siliconed
checkpoint-status |  |  | checkpoint | Cushion boxes installed
checkpoint-group |  |  | section | MOS
checkpoint-status |  |  | checkpoint | MOS ducts measured
checkpoint-status |  |  | checkpoint | MOS ducts delivered
checkpoint-status |  |  | checkpoint | MOS ducts installed
checkpoint-group |  |  | section | Flexible Ducts
checkpoint-status |  |  | checkpoint | Flexible ducts hung
checkpoint-status |  |  | checkpoint | Ducts fixed with panduit straps and duct tape
checkpoint-status |  |  | checkpoint | Hanging straps installed to hang ducts
checklist-flat |  |  | checklist | CO Sensors and Alarms |  |  |  |  | Yes | CO Sensors and Alarms | 2ead38f8-f602-472d-870c-d76c9d8094ea
checkpoint-status |  |  | checkpoint | CO Sensor/Alarm Installed
checkpoint-status |  |  | checkpoint | Cable run from CO sensor/alarm to MSSB
checkpoint-status |  |  | checkpoint | Cable fit off to CO sensor/alarm
checkpoint-status |  |  | checkpoint | Cable fit off in MSSB
checklist-flat |  |  | checklist | Defects / Tasks to be completed |  |  |  |  | Yes | Defects / Tasks to be completed | 33246bed-373a-4740-b70c-6234103b8769
checkpoint-no-status |  |  | checkpoint | Defect details / details of task to be completed (add in comments)
text | 021d069e-a1f6-59d8-bd0a-8d61cb5351e7 |  | textbox | Materials required (if applicable)
checkpoint-status |  |  | checkpoint | PASS once defect/task has been closed out
checklist-flat |  |  | checklist | Fans |  |  |  |  | Yes | Fans | 34eb41ab-c332-476c-9081-5fa14fbf19b8
checkpoint-status |  |  | checkpoint | Fan position marked
checkpoint-status |  |  | checkpoint | Rods Installed
checkpoint-status |  |  | checkpoint | Flex fan connections installed
checkpoint-status |  |  | checkpoint | Fan installed
checkpoint-status |  |  | checkpoint | Fan connected to adjacent ducts/grilles
checklist-flat |  |  | checklist | VRF Commissioning |  |  |  |  | Yes | VRF Commissioning | 3ea80f1e-5888-406e-8492-0cebae2f870f
checkpoint-status |  |  | checkpoint | Pressure test pass
checkpoint-status |  |  | checkpoint | Vac Pass and refrigerant added
checkpoint-status |  |  | checkpoint | Auto Addressing Pass
checkpoint-status |  |  | checkpoint | Auto Piping Pass
checkpoint-status |  |  | checkpoint | Central Controller LG Setup
checkpoint-status |  |  | checkpoint | LG PDI Commissioning Complete
checklist-flat |  |  | checklist | MSSB |  |  |  |  | Yes | MSSB | 42a67acf-bb5d-418c-9e11-65d9e4d80867
checkpoint-status |  |  | checkpoint | MSSB Mounted/installed
checkpoint-status |  |  | checkpoint | Breakers Installed
checkpoint-status |  |  | checkpoint | Submains connected
checkpoint-status |  |  | checkpoint | Cables brought in and terminated
checkpoint-status |  |  | checkpoint | GFA stop, start, run indication, fault/phase fail indication fit off
checkpoint-status |  |  | checkpoint | VRF Refrigerant schematic printed, inside board
checklist-sectioned |  |  | checklist | Apartment Rough In checklist |  |  |  |  | Yes | Apartment Rough In checklist | 4cc50f73-48b1-4e9e-9597-43512332f816
checkpoint-group |  |  | section | Duct
checkpoint-status |  |  | checkpoint | Duct run marked out on ceiling
checkpoint-status |  |  | checkpoint | Flat Duct
checkpoint-status |  |  | checkpoint | Flat duct connected to cushion box/plate
checkpoint-status |  |  | checkpoint | Flex Duct, including duct tape
checkpoint-status |  |  | checkpoint | Rangehood Semi Rigid
checkpoint-status |  |  | checkpoint | Ceiling fan marked on ground
checkpoint-group |  |  | section | Air Conditioning (Common VRF)
checkpoint-status |  |  | checkpoint | AC unit/cushion box positions marked on ceiling
checkpoint-status |  |  | checkpoint | IDU installed
checkpoint-status |  |  | checkpoint | Plenum(s) installed
checkpoint-status |  |  | checkpoint | piping connected to IDU
checkpoint-status |  |  | checkpoint | refnets installed
checkpoint-status |  |  | checkpoint | piping connected to branch box
checkpoint-status |  |  | checkpoint | pipes insulated
checkpoint-status |  |  | checkpoint | IDU cushion boxes installed
checkpoint-status |  |  | checkpoint | AC flex ducts run
checkpoint-status |  |  | checkpoint | Drain connected to IDU
checkpoint-status |  |  | checkpoint | Drains run from IDU to tundish
checkpoint-status |  |  | checkpoint | Access panel marked on ground
checkpoint-status |  |  | checkpoint | AC grilles framed out by plasterer/carpenter
checkpoint-status |  |  | checkpoint | Penetrations fire rated
checkpoint-group |  |  | section | AC Wiring
checkpoint-status |  |  | checkpoint | Power cable run from IDU to IDU/BB
checkpoint-status |  |  | checkpoint | Comms cable run from IDU to IDU/BB
checkpoint-status |  |  | checkpoint | Controller cable
checklist-flat |  |  | checklist | VRF IDU Elec |  |  |  |  | Yes | VRF IDU Elec | 4dd074fd-e396-40d3-ad0c-6bf890a51c03
checkpoint-status |  |  | checkpoint | Power cable run from IDU to IDU/BB
checkpoint-status |  |  | checkpoint | Comms cable run from IDU to IDU/BB
checkpoint-status |  |  | checkpoint | Controller cable run
checkpoint-status |  |  | checkpoint | IDU power cable fitoff, incl. isolator/plug
checkpoint-status |  |  | checkpoint | IDU Comms cable fitoff
checkpoint-status |  |  | checkpoint | IDU controller cable fitoff
checkpoint-status |  |  | checkpoint | power cable fit off in MSSB
checklist-flat |  |  | checklist | Door Grilles |  |  |  |  | Yes | Door Grilles | 5325c1a8-09f8-4ec8-bdac-382af7c831df
checkpoint-status |  |  | checkpoint | Door Grilles given to builder
checkpoint-status |  |  | checkpoint | Builder has installed door grilles
checklist-flat |  |  | checklist | Temp Sensors |  |  |  |  | Yes | Temp Sensors | 5c7c218e-a02d-466b-9277-a415ae1adb8b
checkpoint-status |  |  | checkpoint | temperature sensor installed
checkpoint-status |  |  | checkpoint | temperature sensor ranges set
checkpoint-status |  |  | checkpoint | Comms cable for temp sensor run
checkpoint-status |  |  | checkpoint | Comms cable fit off to temp sensor
checkpoint-status |  |  | checkpoint | Comms cable fit off in MSSB
checklist-sectioned |  |  | checklist | Apartment Fit Off checklist |  |  |  |  | Yes | Apartment Fit Off checklist | 60df8864-4068-432e-9b70-d75f373e5caa
checkpoint-group |  |  | section | Exhaust Diffusers
checkpoint-status |  |  | checkpoint | Main Bath
checkpoint-status |  |  | checkpoint | Ensuite
checkpoint-status |  |  | checkpoint | Laundry
checkpoint-group |  |  | section | AC Grilles
checkpoint-status |  |  | checkpoint | Living room grille
checkpoint-status |  |  | checkpoint | Bed 1 grille
checkpoint-status |  |  | checkpoint | Bed 2 grille
checkpoint-status |  |  | checkpoint | Bed 3 grille
checkpoint-status |  |  | checkpoint | IDU Tundish Connected
checkpoint-group |  |  | section | AC Wiring Fitoff
checkpoint-status |  |  | checkpoint | IDU Comms cable fitoff
checkpoint-status |  |  | checkpoint | IDU power cable fitoff, incl. isolator/plug
checkpoint-status |  |  | checkpoint | IDU controller cable fitoff
checkpoint-group |  |  | section | Rangehoods
checkpoint-status |  |  | checkpoint | Rangehood duct connected and plugged in
checkpoint-status |  |  | checkpoint | Rangehood installed
checkpoint-group |  |  | section | External WPLs
checkpoint-status |  |  | checkpoint | External WPLs installed
checklist-flat |  |  | checklist | Central Controller |  |  |  |  | Yes | Central Controller | 76c7a4ee-a5d0-4fdc-af2a-eff3fe55a797
checkpoint-status |  |  | checkpoint | Comms cable run to CC location from ODU
checkpoint-status |  |  | checkpoint | Comms cable fitoff to CC
checkpoint-status |  |  | checkpoint | Power cable plugged into wall socket and CC
checkpoint-status |  |  | checkpoint | Ethernet cable plugged into CC
checkpoint-status |  |  | checkpoint | CC mounted on wall
checklist-flat |  |  | checklist | VRF BB Elec |  |  |  |  | Yes | VRF BB Elec | 76ecaaf7-c913-4924-ae4c-1bcf568cbd85
checkpoint-status |  |  | checkpoint | Power cables run from MSSB to BB
checkpoint-status |  |  | checkpoint | Comms cable run from ODU to BB
checkpoint-status |  |  | checkpoint | Power cables fit off in BB
checkpoint-status |  |  | checkpoint | Comms cable fit off in BB
checklist-flat |  |  | checklist | Apartment Commissioning |  |  |  |  | Yes | Apartment Commissioning | 78518a57-bbe2-4a90-b22a-e1aeca482b60
checkpoint-status |  |  | checkpoint | Main Bath Airflow (25L/s pass)
checkpoint-status |  |  | checkpoint | Ensuite Airflow (25L/s pass)
checkpoint-status |  |  | checkpoint | Laundry Airflow (40L/s pass)
checkpoint-status |  |  | checkpoint | Rangehood Airflow (40L/s pass)
checkpoint-status |  |  | checkpoint | AC Heating / Cooling correctly
checklist-flat |  |  | checklist | VRF ODU |  |  |  |  | Yes | VRF ODU | 8328d278-122d-488a-9199-1a85a24fb516
checkpoint-status |  |  | checkpoint | blocks mounted
checkpoint-status |  |  | checkpoint | ODU installed
checkpoint-status |  |  | checkpoint | cable tray installed
checkpoint-status |  |  | checkpoint | ODU piping run in cable tray (after cables)
checkpoint-status |  |  | checkpoint | Piping insulated to BB
checkpoint-status |  |  | checkpoint | ODU piping connected to outdoor unit
checkpoint-status |  |  | checkpoint | Pipes Capped / Cable tray lid installed
checklist-flat |  |  | checklist | Power Proportioning |  |  |  |  | Yes | Power Proportioning | 8e294844-dd16-46d0-85d1-1f1ffff6e6a5
checkpoint-status |  |  | checkpoint | PDIs installed
checkpoint-status |  |  | checkpoint | Watt meters installed
checklist-flat |  |  | checklist | Refrigerant Pipe Riser |  |  |  |  | Yes | Refrigerant Pipe Riser | a70ca885-51e9-4538-af19-11a6099d1f8a
checkpoint-status |  |  | checkpoint | All refrigerant pipes in the riser complete for this floor
checklist-flat |  |  | checklist | Labelling |  |  |  |  | Yes | Labelling | b8762340-1a08-4ce5-94ca-3bf80e7fbe94
checkpoint-status |  |  | checkpoint | Plant labelled (not on removable panels)
checkpoint-status |  |  | checkpoint | Access Panel/Controller labelled
checklist-sectioned |  |  | checklist | Elec FIP Commissioning |  |  |  |  | Yes | Elec FIP Commissioning | b8aa8f58-7d22-4d5e-8d94-7f382d35ca34
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | On with GFA
checkpoint-status |  |  | checkpoint | On with pump run
checklist-flat |  |  | checklist | Fire Pump Elec |  |  |  |  | Yes | Fire Pump Elec | ba7f01d6-bf12-431e-8109-1d50764c8bc2
checkpoint-status |  |  | checkpoint | 24VAC cable run from MSSB to elec box
checkpoint-status |  |  | checkpoint | 24VAC cable fit off in elec box
checkpoint-status |  |  | checkpoint | 24VAC cable fit off MSSB
checklist-flat |  |  | checklist | Air Dampers |  |  |  |  | Yes | Air Dampers | c8a4cae5-2430-4d75-ae91-800a013c1283
checkpoint-status |  |  | checkpoint | Air damper installed
checkpoint-status |  |  | checkpoint | Air damper set to correct opening amount
checklist-flat |  |  | checklist | Elec Connections |  |  |  |  | Yes | Elec Connections | ce2c27a7-9f5a-4099-bada-00eaf5dec4f6
checkpoint-status |  |  | checkpoint | power cables run
checkpoint-status |  |  | checkpoint | Isolator installed
checkpoint-status |  |  | checkpoint | power cable fit off to isolator and plant
checkpoint-status |  |  | checkpoint | power cable fit off in VSD/MSSB
checklist-flat |  |  | checklist | Light Switch Elec |  |  |  |  | Yes | Light Switch Elec | d0f97ab6-ad49-4d26-a000-0c2ad7400f35
checkpoint-status |  |  | checkpoint | Plug base installed on light circuit
checkpoint-status |  |  | checkpoint | Fan plugged into plug base
checklist-flat |  |  | checklist | Roof Cowls |  |  |  |  | Yes | Roof Cowls | d156d4af-3276-49cb-ac98-b76d5c3207ee
checkpoint-status |  |  | checkpoint | Roof cowl installed
checkpoint-status |  |  | checkpoint | Dectite/flashing installed and sealed
checklist-flat |  |  | checklist | Penetrations |  |  |  |  | Yes | Penetrations | e32da940-5473-4ae5-bcf2-f4b9e47bde37
checkpoint-status |  |  | checkpoint | Penetrations exist and correct location and size
checkpoint-status |  |  | checkpoint | Penetrations marked to be cut
checklist-flat |  |  | checklist | Filters |  |  |  |  | Yes | Filters | e63331cd-9f7f-403c-b131-42853b222ab3
checkpoint-status |  |  | checkpoint | Filter plenums/ducts installed
checkpoint-status |  |  | checkpoint | Filters installed
checklist-flat |  |  | checklist | VSDs |  |  |  |  | Yes | VSDs | e688ed00-6826-47ca-a03b-292533a3d83d
checkpoint-status |  |  | checkpoint | VSDs installed
checkpoint-status |  |  | checkpoint | VSDs programmed
checklist-flat |  |  | checklist | Air Conditioning (balcony) |  |  |  |  | Yes | Air Conditioning (balcony) | e7eb0e9c-fab8-4f82-bf99-a4774d0a37e1
checkpoint-status |  |  | checkpoint | AC unit/cushion box positions marked on ceiling
checkpoint-status |  |  | checkpoint | IDU installed
checkpoint-status |  |  | checkpoint | Plenum(s) installed
checkpoint-status |  |  | checkpoint | piping connected to IDU
checkpoint-status |  |  | checkpoint | piping connected to branch box
checkpoint-status |  |  | checkpoint | IDU cushion boxes installed
checkpoint-status |  |  | checkpoint | AC flex ducts run
checkpoint-status |  |  | checkpoint | Drain connected to IDU
checkpoint-status |  |  | checkpoint | Drains run from IDU to tundish
checkpoint-status |  |  | checkpoint | Access panel marked on ground
checkpoint-status |  |  | checkpoint | AC grilles framed out by plasterer/carpenter
checkpoint-status |  |  | checkpoint | pair coil roughed in to window
checkpoint-status |  |  | checkpoint | pair coil run through window/wall
checkpoint-status |  |  | checkpoint | noodles installed
checklist-flat |  |  | checklist | Fire Spray/Wrap |  |  |  |  | Yes | Fire Spray/Wrap | ef47ab0a-b97b-4b65-9cac-3bb730559a73
checkpoint-status |  |  | checkpoint | ducts fire sprayed/wrapped
checkpoint-status |  |  | checkpoint | Access panels every 3m and bends for kitchen exhaust
checklist-flat |  |  | checklist | VRF ODU Elec |  |  |  |  | Yes | VRF ODU Elec | f5221e80-d0ec-4425-afc9-de32462d20ee
checkpoint-status |  |  | checkpoint | power cable fit off in MSSB
checkpoint-status |  |  | checkpoint | Power cable run from MSSB/DB to isolator
checkpoint-status |  |  | checkpoint | Isolator installed
checkpoint-status |  |  | checkpoint | power cable fit off to isolator and plant
checkpoint-status |  |  | checkpoint | comms cable run to ODU
checkpoint-status |  |  | checkpoint | comms cable fitoff in ODU
checklist-flat |  |  | checklist | Branch Boxes |  |  |  |  | Yes | Branch Boxes | f91db82a-d361-40fe-9e78-8c5846dd413c
checkpoint-status |  |  | checkpoint | Branch box position marked out
checkpoint-status |  |  | checkpoint | Branch Box Installed
checkpoint-status |  |  | checkpoint | IDU side piping connected to BB
checkpoint-status |  |  | checkpoint | IDU side piping insulated
checkpoint-status |  |  | checkpoint | ODU side piping connected to BB
checkpoint-status |  |  | checkpoint | ODU side piping insulated
checkpoint-status |  |  | checkpoint | Access panel marked on ground