## Project Breakdown
| PROJECT BREAKDOWN |  |  |  | CHECKLISTS
Job Details |  | Standard
Pre-Commencment Checks |  | Standard
| H&S |  |  |  | Pre checks H&S Checklist
Quality
Quality Management Plan Completed, Agreed & Attached
Inspection & Test Plan Completed, Agreed & Attached
Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
Conqa Setup & Project Team Trained & Given Access
Review Access Granted to Main Contractor & Relevant Parties
Matrix/Insights Setup (if required)
On Site QA | WBS Level 1 (Locked) | WBS Level 2 (Locked)
| Enabling Works | GPE
|  |  | Daily QC Checklist | ability to add | 01) Add Daily QC Checklist
|  |  | QC Inspection Report | ability to add | 03) Add QA/QC Inspection Report
|  |  | QA Inspection Report | ability to add | 03) Add QA/QC Inspection Report
|  |  | Area Completion | prepopulate | Area Completion Checklist
FX9500
|  |  | Daily QC Checklist | ability to add | 01) Add Daily QC Checklist
|  |  | QC Inspection Report | ability to add | 03) Add QA/QC Inspection Report
|  |  | QA Inspection Report | ability to add | 03) Add QA/QC Inspection Report
|  |  | Area Completion | prepopulate | Area Completion Checklist
HBR
|  |  | Daily QC Checklist | ability to add | 01) Add Daily QC Checklist
|  |  | QC Inspection Report | ability to add | 03) Add QA/QC Inspection Report
|  |  | QA Inspection Report | ability to add | 03) Add QA/QC Inspection Report
|  |  | Area Completion | prepopulate | Area Completion Checklist
Compliance Documentation
PS3 Completed and Attached
Any Additional Compliance Documentation

## Checklists
checklist-flat | 02) Add Additional Application
checkpoint | Coat
text | Coat:
text | Brand Name
text | Batch Number
text | Colour
text | % Thinner Used
select | Type | Brush,Roller,Spray (airless),Spray (conventional),Spray (plural)
text | Required Wet film thickness |  | μm
text | Required Dry film thickness |  | μm
text | Specified Maximum (if applicable) |  | μm
text | Specified Minimum |  | μm
text | Number of readings taken
text | Average |  | μm
text | Quantity Used |  | Litres
checklist-sectioned | 01) Add Daily QA Checklist
section | Preparation
checkpoint | Hold Point Inspections
text | Location & Description
boolean | Weather and Site Conditions
boolean | Pre Surface prep/condition & cleanliness
boolean | Post surface prep/cleanliness & profile
boolean | Application monitoring/wet film thickness (WFT)
boolean | Post application/application defects
boolean | Post cure/dry film thickness (DFT)
boolean | Corrective action follow up & final inspection
checkpoint | Surface Conditions
boolean | New
boolean | Scale
boolean | Maint
boolean | Pitting/Holes
boolean | Age
boolean | Crevices
boolean | Dry
boolean | Sharp Edges
boolean | Cure
boolean | Pinholes
boolean | Concrete
boolean | Runs/Sags
boolean | Steel
boolean | Holidays
boolean | Weld
boolean | Galvanised
boolean | Abrasions
text | Cl |  | μg/cm2/ppm
text | Fe |  | ppm
text | pH
text | Hazardous substances identified in existing coating or substrate?
text | Moisture/Oils
text | Degree of Contamination
text | Degree of Corrosion
text | Painted Surface Condition
checkpoint | Ambient Conditions
text | Time
text | Air Temp |  | Deg c
text | Surface Temp |  | Deg c
text | Relative Humidity |  | %
text | Dew Point Temp |  | Deg c
text | Weather Conditions
text | Wind Direction/Speed
checkpoint | Surface Preparation
text | Start Time:
text | Finish Time:
text | Approximate Area: |  | m2
boolean | Solvent Clean
boolean | Hand Tool
boolean | Power Tool
boolean | Waterblasting
text | HP Wash: |  | PSI
boolean | Abrasive Blast
text | Abrasive Type:
boolean | Abrasive Sample
text | Blast Hose Size:
text | Nozzle Size/Psi:
text | Air Supply: |  | CFM
boolean | Air Supply Clean
boolean | Water/Oil Trap Check
boolean | Equipment Condition Check
section | Application
checkpoint | Ambient Conditions
text | Time
text | Air Temp |  | Deg c
text | Surface Temp |  | Deg c
text | Relative Humidity |  | %
text | Dew Point Temp |  | Deg c
text | Weather Conditions
text | Wind Direction/Speed
checkpoint | Coat
text | Coat:
text | Brand Name
text | Batch Number
text | Colour
text | % Thinner Used
select | Type | Brush,Roller,Spray (airless),Spray (conventional),Spray (plural)
text | Required Wet film thickness |  | μm
text | Required Dry film thickness |  | μm
text | Specified Maximum (if applicable) |  | μm
text | Specified Minimum |  | μm
text | Number of readings taken
text | Average |  | μm
text | Quantity Used |  | Litres
checklist-flat | 03) Add QA Inspection Report
checkpoint | Inspection Info
text | Inspection By:
text | Area:
text | Description:
text | Coat:
text | Time:
checkpoint | Documentation Review
boolean | Daily inspection reports completed and up to date
boolean | Daily Presart completed and viewed
boolean | Specified products being used on site
boolean | Specification available on site
boolean | Product data sheet available on site
boolean | Material Safety Data Sheet (MSDS) available on site
boolean | Product batch numbers being recorded
checkpoint | Site Inspection Review
boolean | Visual inspection completed
label | Visible defects identified and marked (if applicable)
boolean | Non-drying film
boolean | Blushing
boolean | Holidays
boolean | Chalking
boolean | Cratering
boolean | Air voids
boolean | Pinholing
boolean | Discolouration
boolean | Heat related damage
boolean | Blistering
boolean | Cracking & Detachment
boolean | Checking
boolean | Adhesion failure
boolean | Failure on edges
boolean | Gouges
boolean | Water damage
text
boolean | DFT survey completed
text | Number of readings taken
text | Specified
text | Average
text | Max
text | Min
checkpoint | Notes & Recomendations
boolean | Remedial actions required
text
boolean | Inspection complete with no actions required
text
checkpoint | Handover Accepted By Client
holdpoint | Request Signature
checklist | Area Completion Checklist
checklpoint | All works completed, reviewed and approved
holdpoint | Request Signoff
checklist | Pre checks H&S Checklist
checklpoint | SSSP