## Wall And Slab Installation
Wall And Slab Installation Inspection and Test Plan
Project: Arnold Dam
Number and Revision: DS2672-ITP-S116 - Rev 4
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 8 – CONSTRUCTION ACTIVITY – CONCRETE CONSTRUCTION (Excluding Jet-Grouting)
5.04 | Placement and Compaction of Fill General
5.04.01 | Retaining Wall foundation Inspection | Excavated natural ground in foundation area of retaining wall upgrade/extension works prior to placement of fill or concrete must be inspected by the Engineer prior to further work being carried out in the area. | 14AED/AD4-C - 030.3 | Hold Point Release | 48 Hours Notice Prior to Each Occurrence | HP | ENG
8.01 | Concrete Subgrade Preparation
8.01.01 | Wall Type 1 Subgrade Preparation | Concrete of the existing dam surface to be water blast cleaned and roughened to provide NZS3109 Type B Construction Joint. | RSV - GS - 1.1 | Approved Surface | Prior to Pour | HP | ENG
8.01.02 | Wall Type 2 Subgrade Preparation | Existing concrete under and to the sides of the foundation to be thoroughly water blasted back to sound concrete. | RSV - GS - 1.1 | Approved Surface | Prior to Pour | HP | ENG
8.01.03 | Wall Type 3 & 4 Subgrade Preparation | Any soft soil or silts to be removed from site and subgrade to be inspected. Fill to underside of foundation with AP40 or approved fill. Fill to be compacted in 200mm layers. | RSV - GS - 1.1 | Approved Subgrade | Prior to Pour | HP | ENG
8.01.04 | Return Wall Subgrade Preparation | Ground excavated to footing level. Backfill as required with AP40 or approved fill. Fill to be compacted in 200mm layers. | RSV - GS - 1.1 | Approved Backfill | Prior to Pour | HP | ENG
8.02 | Concrete Pour (Pre Pour Checksheet)
8.02.01 | Construction Joint Locations | Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour. | RSV - CS - 1.15 | Site Records | Prior to Pour | R | SE
8.02.02 | Grouting of Bars | Reinforcement installed into existing concrete shall be epoxied into the cured concrete with Hilti HIT RE 500 V3 epoxy mortar to the depth shown on the drawings and all strictly installed to the manufacturers written instructions. | RSV - CS - 1.18 | Photos | Prior to Pour | R | SE
8.02.04 | Pre-Pour Inspections | Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area with a signed pre pour checksheet attahced. | P&G 14 | Pre Pour Checksheet | 48 Hours Notice Prior to Each Occurrence | HP | ENG
8.02.05 | Delivery Dockets | The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size. | RSV - CS - 1.9 | Dockets | Each Pour | R | PE
8.02.06 | Slump Testing | Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor. | RSV - CS - 1.12 | Concrete Register | Each Pour | R | PE
8.02.07 | Compression Testing | A set of specimens for concrete tests shall consist of four specimens from each major pour of concrete, one of which shall be tested at 7 days and the remaining three at 28 days after casting. | RSV - CS - 1.12 | Test Results | Each Pour | R | PE
Concrete Pour (Post Pour Checksheet)
| Post-Pour Inspection | Conformation that the pour was acceptable and apporved by the Engineer |  | Post Pour Checksheet | Each Pour | R | SE