## Sheet1
Inspection and Test Plan Te Ara o Te Ata MMA-QA-ITP-Z07-EW-GE003
This ITP has been prepared by |  |  |  | Reviewed by [as applicable or reviewed on Teams] |  |  |  | Reviewed by DSR
Rev Number |  | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 01
Rev 02
Rev 03
ITP NO: CONQA # Rev.01 |  |  | Project: Te Ara o Te Ata |  | Construction Process |  |  |  | Location:
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. Surveillance [R] – An Activity that is subject to ongoing monitoring. |  |  | Reference Documents: CWP Number: MMA-CON-CWP-Z07-EW-GE003 NZS 3109:1997 - Concrete Construction | [5 empty] | Responsibilities MTME = MTM Alliance Construction CPS = Construction Phase Services SE/PE = Site Engineer/Project Engineer SUP = Supervisor QM = Quality Manager
Activity/Specification: Earthworks Cut
Item | Titles | Description |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Verification Activity by |  |  |  | Verifying Records
[6 empty] | Method/ Description | Test frequency |  | Conformance Criteria | Constructor | CPS | Designer | IOM
1.0 Pre-Construction
1.01 | Approved CWP | CWP |  | Health and safety management plan |  | Document Review | Prior to personal starting |  | Ensure all crew members are briefed on the CWP | H |  |  |  | Signed off CWP
1.02 | IFC issued | Design |  | Consent conditions |  | Document Review | Prior to starting |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H |  |  |  | IFC drawings or written approval from PAB
1.03 | Pre-construction sign offs | TMP and
2.0 During Construction
2.01 | Survey Set Out | Set out piles and check against design |  | IFC Drawings and/or IFC Model |  | Survey/visual | Prior to Commencement |  | Consistent with latest IFC drawings and marked out within specification tolerances | H | R
2.02 | Steel Material Classification | Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings |  | AS/NZS4671&NZS3109 |  | Document review | Prior to commencement |  | Mill certificates match the grade called up in the drawings | H |  |  |  | Mill Certificates
2.03 | Splicing Piles | Any welding or mechanical splicing to be approved in writing by the Design Engineer |  | AS/NZS4671&NZS3109 |  | Document review | Prior to welding or splicing |  |  | H | I | H |  | Mark Up As Built Drawings
2.04 | Piling Auguring | Piling log to be completed daily. Record to detail daily piling progress, when each pile was completed and any issues faced. |  | 20230821 Fill 14 Landslide SH3 Retaining Wall |  | Visual/measure | Daily during piling operations |  | Completion of daily piling log | H | R |  |  | Piling Log
2.05 | Pre pour inspection | Pre-pour checks for pile depth, rock depth, reinforcement, position and alignment. Construction team and DSR to sign off pre pour inspection. |  | 20230821 Fill 14 Landslide SH3 Retaining Wall |  | Visual/measure Document review | Prior to concrete pour |  | Completed Checksheet | H | H |  |  | Pile Pre Pour Checksheet
2.06 | Concrete supply | All concrete delivered to site shall be minimum 30 Mpa. All concrete dockets to be checked to make sure the correct mix has been delivered. |  | 20230821 Fill 14 Landslide SH3 Retaining Wall |  | Supply docket review | During pour |  | Correct mix and conforming testing | H |  |  |  | Concrete Delivery Dockets and Test Results
2.07 | Concrete Testing | A set of 3 test cylinders for compressive testing to be taken at the concrete plant. One to be tested at 7 days and two to be tested at 28 days. |  | 20230821 Fill 14 Landslide SH3 Retaining Wall |  | Test | Each pour |  | Achieve the design concrete strength of 30 & 40 MPa | W/R | R |  |  | Test Results
2.08 | Concrete Finish | Concrete to be finished flush with the surrounding ground. No part of the pile to be standing proud. Concrete is to be finished in a way that prevents water ponding. |  | 20230821 Fill 14 Landslide SH3 Retaining Wall |  | Visual Inspection | At the completion of the pour |  | Pile to be finished flush with existing ground | I | I |  |  | Pile Pre Pour Checksheet
3.0 Post Construction
3.01 | Survey As-builts | Survey As-builts |  |  |  | Survey As-built | During construction and at end |  | Ensure all piles are captured. | H |  |  |  | Digital file
3.02 | Red Line Mark Ups | As-builts |  |  |  | Red Pen Mark up | End of construction |  | All variances captured | H | R |  |  | Red Pen mark ups
4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
ITP Close-Out by
Site Engineer/ Project Engineer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Zone Manager Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Construction Manager Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Quality Manager Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Note on N14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If applicable, otherwise, leave it blank.
Note on O14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If applicable, otherwise, leave it blank.