## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-007 – Palisade Wall | itp |  |  |  | Yes | ITP-007 - Palisade Wall
section | 1.0 Pre-Construction
checkpoint | 1.01 - Approved CWP
label | Method/Description - Document Review
label | Test frequency - Prior to personal starting
label | Constructor - H
label | Verifying Records - Signed off CWP
checkpoint | 1.02 - IFC issued
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Constructor - H
label | Verifying Records - IFC drawings or written approval from PAB
section | 2.0 During Construction
checkpoint | 2.01 - Survey Set Out
label | Method/Description - Survey/visual
label | Test frequency - Prior to Commencement
label | Constructor - H
label | CPS - R
checkpoint | 2.02 - Steel Material Classification
label | Method/Description - Document review
label | Test frequency - Prior to commencement
label | Constructor - H
label | Verifying Records - Mill Certificates
checkpoint | 2.03 - Splicing Piles
label | Method/Description - Document review
label | Test frequency - Prior to welding or splicing
label | Constructor - H
label | CPS - I
label | Designer - H
label | Verifying Records - Mark Up As Built Drawings
holdpoint | HOLDPOINT
checkpoint | 2.04 - Piling Auguring
label | Method/Description - Visual/measure
label | Test frequency - Daily during piling operations
label | Constructor - H
label | CPS - R
label | Verifying Records - Piling Log
checkpoint | 2.05 - Pre pour inspection
label | Method/Description - Visual/measure Document review
label | Test frequency - Prior to concrete pour
label | Constructor - H
label | CPS - H
label | Verifying Records - Pile Pre Pour Checksheet
checkpoint | 2.06 - Concrete supply
label | Method/Description - Supply docket review
label | Test frequency - During pour
label | Constructor - H
label | Verifying Records - Concrete Delivery Dockets and Test Results
checkpoint | 2.07 - Concrete Testing
label | Method/Description - Test
label | Test frequency - Each pour
label | Constructor - W/R
label | CPS - R
label | Verifying Records - Test Results
checkpoint | 2.08 - Concrete Finish
label | Method/Description - Visual Inspection
label | Test frequency - At the completion of the pour
label | Constructor - I
label | CPS - I
label | Verifying Records - Pile Pre Pour Checksheet
section | 3.0 Post Construction
checkpoint | 3.01 - Survey As-builts
label | Method/Description - Survey As-built
label | Test frequency - During construction and at end
label | Constructor - H
label | Verifying Records - Digital file
checkpoint | 3.02 - Red Line Mark Ups
label | Method/Description - Red Pen Mark up
label | Test frequency - End of construction
label | Constructor - H
label | CPS - R
label | Verifying Records - Red Pen mark ups
section | 4.0 CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
label | Site Engineer/Project Engineer
label | Zone Manager Approval
label | Construction Manager Approval
label | Quality Manager Approval
date | Date:
holdpoint | SIGNATURE