## Wall
Standard wall checklist
checklist | Setout
checkpoint | Set out walls
button | As per approved for construction drawings. AR-0-140 series | Yes / No / NA
button | Current revision (photo) | Yes / No / NA | * mandatory photo
button | Wall types clearly identified - Fire / smoke / standard | Yes / No / NA
checklist | Wall Framing
checkpoint | Metal stud wall frame
button | Stud configeration conforms to Wall Types AR-0-230 series
button | Fixings max 600 centres in track fixed using (Product used) | Yes / No / NA
button | Stud spacings max 600 centres | Yes / No / NA
button | Conforms to Rondo / Studco seismic design (Checkpoint applicable design) | Yes / No / NA
button | In accordance with Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | Yes / No / NA
checkpoint | Frame Noggin
button | Noggin track installed to suit stud spacing and in accordance with approved design | Yes / No / NA
checkpoint | screws in deflection head | Yes / No / NA
button | Check no screws in deflection head | Yes / No / NA
checkpoint | Door Frames | Yes / No / NA
button | Installed in conjunction with door fiunction schedule AR-0-280 series | Yes / No / NA
button | Door frame installed square and plumb to correct height | Yes / No / NA
button | Door number marked on spreader bar in accordance with AR-0-110 plan | Yes / No / NA
checkpoint | Noggins
button | Services / joinery / fixtuire and fittings noggins are installed | Yes / No / NA
button | Steel for drug / gun safes installed | Yes / No / NA
checklist | Wall Sheeting
Hold Point | Service Check for pre- installation of sheets | Yes / No / NA
| HOLD POINT: All in wall services and noggins are installed and approval to sheet from Multiplex | Yes / No / NA
checkpoint | Track clean and clear of any dust / debris
button | Track vacuumed out
button | No dust / rubbish / waste inside wall cavity | Yes / No / NA | * mandatory photo
checkpoint | Check insulation in walls | Yes / No / NA
button | Approved insulation installed as per approved drawings AR-0-230 drawings | Yes / No / NA
button | Installed tight between studs with no gaps (input insulation type / photo) | Yes / No / NA | * mandatory photo
checkpoint | Sheet all walls
button | Conformation type & location AR-0-230 series (Checkpoint: standard / Wet area) | Yes / No / NA
button | Standard rooms - plaster extends minimum 100mm above ceiling height | Yes / No / NA
button | Bathrooms - plaster extend full height | Yes / No / NA
button | Screw spacings to Edge (200mm max) field (300mm max) | Yes / No / NA
button | No gaps - square and plumb | Yes / No / NA
button | Overlap at corner junctions | Yes / No / NA
checkpoint | Verify correct plaster sheet used | Yes / No / NA
button | standard- wet area (MR)- acoustic- impact | Yes / No / NA
checklist | Finishing
checkpoint | Stopping to walls
button | Walls stopped and sanded to approved class of finish | Yes / No / NA
button | Area clean and no excess plaster on slab / plaster dust removed | Yes / No / NA

## Fire Smoke wall
Fire / Smoke / Presurised room wall checklist
checklist | Setout
checkpoint | Set out walls
button | As per approved for construction drawings. AR-0-140 series | Yes / No / NA
button | Current revision (photo) | Yes / No / NA
button | Wall types clearly identified - Fire / smoke / standard | Yes / No / NA
checklist | Wall Framing
checkpoint | Metal stud wall frame
button | Stud configeration conforms to Wall Types AR-0-230 series
button | Fixings max 600 centres in track fixed using ?????? | Yes / No / NA
button | Stud spacings max 600 centres | Yes / No / NA
button | Conforms to Rondo / Studco seismic design (Checkpoint applicable design) | Yes / No / NA
button | In accordance with Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | Yes / No / NA
checkpoint | Frame Noggin
button | Noggin track installed to suit stud spacing and in accordance with approved design | Yes / No / NA
checkpoint | screws in deflection head | Yes / No / NA
button | Check no screws in deflection head | Yes / No / NA
checkpoint | Door Frames | Yes / No / NA
button | Installed in conjunction with door fiunction schedule AR-0-280 series | Yes / No / NA
button | Door frame installed square and plumb to correct height | Yes / No / NA
button | Door frame filled in accordance with manufacturers requirements
button | Door number marked on spreader bar in accordance with AR-0-110 plan | Yes / No / NA
checkpoint | Noggins
button | Services / joinery / fixture and fittings noggins are installed | Yes / No / NA
button | Steel for drug / gun safes installed | Yes / No / NA
checklist | Wall Sheeting
Hold Point | Service Check for pre- installation of sheets | Yes / No / NA
| HOLD POINT: All in wall services and noggins are installed and approval to sheet from Multiplex | Yes / No / NA
checkpoint | Track clean and clear of any dust / debris
button | Track vacuumed out | Yes / No / NA
button | No dust / rubbish / waste inside wall cavity | Yes / No / NA
checkpoint | Check insulation in walls
button | Approved insulation installed as per approved drawings AR-0-230 drawings | Yes / No / NA
button | Installed tight between studs with no gaps (input insulation type / photo) | Yes / No / NA
checkpoint | Sheet all walls
button | Conformation type & location AR-0-230 series | Yes / No / NA
button | Screw spacings to Edge (200mm max) field (300mm max) | Yes / No / NA
button | Confirm all butt joins overlap by minimum 200mm | Yes / No / NA
button | No gaps between sheets- square and plumb | Yes / No / NA
button | Overlap at corner junctions | Yes / No / NA
checkpoint | Verify correct plaster sheet used - FR Board | Yes / No / NA
checklist | Finishing
checkpoint | Stopping to walls
button | Walls stopped and sanded to approved class of finish | Yes / No / NA
button | Area clean and no excess plaster on slab / plaster dust removed | Yes / No / NA
checkpoint | Caulking - Fire / Smoke / Pressurised rooms
button | Caulked top and bottom junction to slab and soffit full length using ?????? | Yes / No / NA
button | All gaps sealed around presurised boxes and gaps in plaster | Yes / No / NA

## Lead line room (WIP)
Lead line walls
checklist | Setout
checkpoint | Set out walls
button | As per approved for construction drawings. AR-0-140 series | Yes / No / NA
button | Current revision (photo) | Yes / No / NA
button | Wall types clearly identified - Fire / smoke / standard / Lead lined | Yes / No / NA
checklist | Wall Framing
checkpoint | Metal stud wall frame
button | Stud configeration conforms to Wall Types AR-0-230 series
button | Fixings max 600 centres in track fixed using ?????? | Yes / No / NA
button | Stud spacings max 600 centres | Yes / No / NA
button | Conforms to Rondo / Studco seismic design (Checkpoint applicable design) | Yes / No / NA
button | In accordance with Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | Yes / No / NA
checkpoint | Frame Noggin
button | Noggin track installed to suit stud spacing and in accordance with approved design | Yes / No / NA
checkpoint | screws in deflection head | Yes / No / NA
button | Check no screws in deflection head | Yes / No / NA
checkpoint | Lead lining | Yes / No / NA
button | Verified thickness of lead sheet | Yes / No / NA
button |  | Yes / No / NA
button |  | Yes / No / NA
button |  | Yes / No / NA
checkpoint | Door Frames | Yes / No / NA
button | Installed in conjunction with door fiunction schedule AR-0-280 series | Yes / No / NA
button | Door frame installed square and plumb to correct height | Yes / No / NA
button | Door frame lead lined with no gaps | Yes / No / NA
button | Door number marked on spreader bar in accordance with AR-0-110 plan | Yes / No / NA
checkpoint | Noggins
button | Services / joinery / fixture and fittings noggins are installed | Yes / No / NA
checklist | Wall Sheeting
Hold Point | Service Check for pre- installation of sheets | Yes / No / NA
| HOLD POINT: All in wall services and noggins are installed and approval to sheet from Multiplex | Yes / No / NA
checkpoint | Track clean and clear of any dust / debris
button | Track vacuumed out | Yes / No / NA
button | No dust / rubbish / waste inside wall cavity | Yes / No / NA
checkpoint | Check insulation in walls
button | Approved insulation installed as per approved drawings AR-0-230 drawings | Yes / No / NA
button | Installed tight between studs with no gaps (input insulation type / photo) | Yes / No / NA
checkpoint | Sheet all walls
button | Conformation type & location AR-0-230 series | Yes / No / NA
button | Screw spacings to Edge (200mm max) field (300mm max) | Yes / No / NA
button | Confirm all butt joins overlap by minimum 200mm | Yes / No / NA
button | No gaps between sheets- square and plumb | Yes / No / NA
button | Overlap at corner junctions | Yes / No / NA
checkpoint | Verify correct plaster sheet used - FR Board | Yes / No / NA
checklist | Finishing
checkpoint | Stopping to walls
button | Walls stopped and sanded to approved class of finish | Yes / No / NA
button | Area clean and no excess plaster on slab / plaster dust removed | Yes / No / NA
checkpoint | Caulking - Fire / Smoke / Pressurised rooms
button | Caulked top and bottom junction to slab and soffit full length using ?????? | Yes / No / NA
button | All gaps sealed around presurised boxes and gaps in plaster | Yes / No / NA