## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Production and Testing ITPs |  |  |  |  | Yes | Production and Testing ITPs | 21a70bf6-59b2-46e5-8f4b-6bddde70f403
checkpoint-status |  |  | checkpoint | Production and Testing ITPs
checklist-sectioned |  |  | checklist | ITP - Sealing - Stabilised Pavement Layer | itp |  |  |  | Yes | ITP - Sealing - Stabilised Pavement Layer - Abattoir Road | 4513ea7c-2666-47a9-8c8f-0d5ab24529f4
checkpoint-group |  |  | section | 4.0. SETOUT AND PREPARATION
checkpoint-status |  |  | checkpoint | 4.0.1 - Mark out and approve
label | c0a6822b-381a-5fba-a356-b20821edf098 |  | note | Detail of Activity - Set out and record existing line markling within the treatment area
label | 31fd9faa-2b33-56f8-ae6f-9759ba405ef5 |  | note | Action (Hold, Monitor, Witness) - H
label | bb754895-d9d2-59f5-8688-de3915e52fbc |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - All areas of unbound granular pavement layers
label | 48f43835-7584-50e2-b9ea-b4e1262c3617 |  | note | Inspection / Test method - NZTA Z/16
label | 404aafe3-c75c-5743-b60b-c5378db58e77 |  | note | Acceptance Criteria - N/A
label | c396b56c-30dc-5455-b780-82411107e9bf |  | note | Record documents - Contractor's site diary
label | b645c11d-494d-5251-8e68-0f142ead0a7a |  | note | Responsibility - Contractor
label | 7a423273-2faa-50ee-94f8-ff6abfa3bb1c |  | note | Comments - Treatment area marked up jointly by Contractor and Eng.Rep.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.0.2 - Level Control
label | 73f2a5b4-40af-5202-a949-bbf43acec47a |  | note | Detail of Activity - Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking
label | 39771448-f5a3-5131-8d9f-c9733f979605 |  | note | Action (Hold, Monitor, Witness) - M
label | bffed23f-e335-51a3-9f9b-5ff2cfce4161 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to works
label | 03b1f155-8e09-5dd8-98c5-c2478a60a19a |  | note | Inspection / Test method - NZTA Z/16
label | 5dbae35c-29c5-5c9d-bc3f-1b0176e13cf1 |  | note | Acceptance Criteria - Document existing furniture
label | 373a2a30-c2fa-52eb-a23d-6e5eec4db69a |  | note | Record documents - Site Diary
label | 072c90b6-8a55-5893-a7a2-225e1bfe4163 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.0.3 - Determine levels of substrate before placing materials
label | fab61878-8446-5b22-822c-1e25fb133555 |  | note | Detail of Activity - Check top of substrate levels
label | 8e0c5814-1cac-5019-bc83-834141a65560 |  | note | Action (Hold, Monitor, Witness) - M
label | 8d5bfb14-d2cf-5e9f-a892-5d4ba4b7153c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 20m
label | b88b78d8-378e-5f81-9cc3-9d125c1c6e78 |  | note | Inspection / Test method - NZTA Z/16
label | 35bc45d5-75ce-5c3a-aab6-714259888cc9 |  | note | Acceptance Criteria - Subgrade: check NZTA F/1 and/or project specifications.
label | 162aa05e-c1bd-523b-8ec7-50bd33d5495a |  | note | ○ Subbase: No Concrete Channel: -25mm + 5mm with Concrete Channel: -25mm + 5mm
label | 5f42a1f9-c07b-5cea-8c13-5e74e44e842a |  | note | Record documents - Survey Diary or CAD
label | a393cac0-ae9e-5d78-9843-e68b5957e120 |  | note | Responsibility - Surveyor / contractor
checkpoint-status |  |  | checkpoint | 4.0.4 - Modification Agent(s) Optimisation
label | 417fa24d-4028-5476-8dfd-db16b668b9c3 |  | note | Detail of Activity - Stabilised material strength - ITS
label | 87f5857a-ae24-506c-a745-824bbf4d13a8 |  | note | Action (Hold, Monitor, Witness) - H
label | 28ff0e56-4dde-5511-a1b5-024b8473eb0c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Optimisation test per aggregate type
label | 3b94a0e7-5681-50a5-8528-7612c693af7b |  | note | Inspection / Test method - NZTA T/19
label | 680b1d26-99c4-52d0-abcc-026aad53ffa7 |  | note | Acceptance Criteria - Check Project Specs.
label | 00770c7a-ce11-531c-96a8-4d17fd4c58c4 |  | note | Modified materials should be:
label | ad297e4b-e6cf-5284-864b-f883042d4a2a |  | note | Dry ITS: 175kPa to 400 kPa
label | 462dd87e-dcf0-5ebf-b63f-8f491c136654 |  | note | Soaked ITS: 150 kPa to 350 kPa
label | 708f7a89-51d2-5c47-a1fc-19a95c81f409 |  | note | Record documents - IANZ Report
label | 23c2f09c-cde1-58be-a3ee-cd5438bbba2b |  | note | Responsibility - Client
label | 01247dfe-35ea-51b0-a968-02a054045f3b |  | note | Comments - Must be submitted to the pavement designer for approval at least 5 working days before modification works comence
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 4.1. MATERIALS - SUBBASE / BASECOURSE
checkpoint-status |  |  | checkpoint | 4.1.1 - Check raw materials (whichever applicable)
label | c116ec94-1da2-5022-83a7-f596e8b113c7 |  | note | Detail of Activity - Cement
label | aa88b3d5-f1eb-5982-ae95-aa8bdb80f6b6 |  | note | Action (Hold, Monitor, Witness) - M
label | 9fd16f4e-ddc9-5370-803e-8d8ddccdba44 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | 6219baed-684b-5a6a-ba4a-1439fcc69f0e |  | note | Inspection / Test method - NZ 3122
label | 3bf185f1-e0af-59eb-9a1c-684e7a29a86c |  | note | Record documents - Certificate in contractor's site folder
label | 910f463a-a2cd-5439-9251-d7b21d8d3d4e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.1.2 - Check raw materials (whichever applicable)
label | b3e8e2a8-e41e-5f7f-af03-2ab3e42f65ad |  | note | Detail of Activity - Lime
label | cd86f62e-10d6-5276-bf90-5af74f822436 |  | note | Action (Hold, Monitor, Witness) - M
label | 74b88120-305c-505b-95d2-2bda302219c9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | f83f0859-4e4a-5d1f-8bce-b58be9fa577b |  | note | Inspection / Test method - NZTA M/15
label | 623da8dc-5a58-5015-a846-bd0519f26b10 |  | note | Record documents - Certificate in contractor's site folder
label | b6678c1d-de8a-5f6f-9794-d4607af64a37 |  | note | Responsibility - Contractor
label | ee4132c6-b93e-516a-ab7b-2182ca926d58 |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 4.1.3 - Check raw materials (whichever applicable)
label | a1ec1e8c-f547-5f6b-9892-15fc1f68ed60 |  | note | Detail of Activity - Cement / Lime Supply and Storage Pods
label | 3f56202d-040a-5c57-a61d-6aae94f49936 |  | note | Action (Hold, Monitor, Witness) - M
label | 1703a375-deae-5017-a28d-12e7b837159a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to commencement
label | 9a4716b0-189a-51d5-adc2-ca7604d29e3e |  | note | Inspection / Test method - Document Review
label | bc7e6725-d317-5c5c-bc96-63621274a346 |  | note | Acceptance Criteria - All test certificates with supply and storage pods
label | fd99a63e-5a98-54cd-8848-81e6314ca351 |  | note | Record documents - Certificate in contractor's site folder
label | 9652ba6e-cce6-503e-acc2-8fd27f44e306 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.1.4 - Check raw materials (whichever applicable)
label | b7712dd4-d79b-5c1c-b513-49e5b1548c9d |  | note | Detail of Activity - Bitumen for Stabilisation (FBS or BE)
label | 91b410b7-30e5-5d01-93f6-2b1e8648e4ab |  | note | Action (Hold, Monitor, Witness) - M
label | 03447068-d2b7-5548-a268-492ea786b145 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | 093d0ee5-b4fd-5de9-a3ed-18278e0c1c48 |  | note | Inspection / Test method - NZTA M/01 and visual foaming at test nozzle
label | 34154cf5-add6-502f-aa3e-e3a355de92eb |  | note | Acceptance Criteria - Pen 80/100 Bitumen or Pen 180/200 (if approved) Bitumen able to achieve min 10x expansion and min. 6s half life
label | c99a54b2-87e6-5d5e-a321-93cc879eeb26 |  | note | Record documents - Certificate in contractor's site folder
label | ae62aa88-ddf7-5831-a8b1-3811ce8eadd2 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.1.5 - Check raw materials (whichever applicable)
label | be0abb1b-d518-561a-af52-5f67ff895600 |  | note | Detail of Activity - Bitumen Supply and Storage Tanks
label | e9e24f62-c532-5868-9a22-06a3100c4040 |  | note | Action (Hold, Monitor, Witness) - M
label | 0b1e5a20-594a-522f-b059-6014e2f21e2c |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to commencement
label | 1a4401e0-f8da-576e-ae00-b85288be5db8 |  | note | Inspection / Test method - Document Review
label | 4af56390-e4d8-5c9c-9054-69cf2faaa87f |  | note | Acceptance Criteria - All test certificates with supply and storage pods
label | 8a0a213a-b18e-59b9-a70f-caf3dfdc422d |  | note | Record documents - Certificate in contractor's site folder
label | fe745cc6-fa04-5b3e-aafd-742ee135780e |  | note | Responsibility - Contractor
label | 1c59923f-f417-5396-a8d2-f75144773976 |  | note | Comments - Retain for testing if required
checkpoint-status |  |  | checkpoint | 4.1.6 - Check raw materials (whichever applicable)
label | 0f5b9935-d2e3-54f0-be59-fc1601b928c6 |  | note | Detail of Activity - Sub-base Aggregate
label | 03e7bb9c-d1f8-5496-ba9e-48b7bc395842 |  | note | Action (Hold, Monitor, Witness) - M
label | 362c2698-7345-5747-b9bf-52c3837aab15 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | fb2776e7-6c92-557a-8a99-e870ce5a5f6e |  | note | Inspection / Test method - USE ITP LABELLED UBG SUBBASE
label | e978b5aa-19fb-53d2-8443-4a4e310e4889 |  | note | Acceptance Criteria - NZTA M03 / Project Spec
label | b2f23344-da3e-52c9-959e-3ca3a1c99548 |  | note | Record documents - Certificate in contractor's site folder
label | 854d9449-8f6d-5f04-9ed9-212ab9effc30 |  | note | Responsibility - Contractor
label | 2238a182-be2d-5eb2-b0d9-f148fb170f67 |  | note | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint-status |  |  | checkpoint | 4.1.7 - Check raw materials (whichever applicable)
label | 2e4a0419-9db7-5d3c-8add-5938e6cc4fdf |  | note | Detail of Activity - Basecourse Aggregates
label | d9ade27e-ba9b-5f06-8b0d-a6a042e675be |  | note | Action (Hold, Monitor, Witness) - M
label | ffcd0f9d-9395-5df6-a3de-09ae02e2b475 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | f2e3a602-7564-5e1a-adc8-a17414949c6e |  | note | Inspection / Test method - USE ITP LABELLED UBG BASECOURSE
label | eee7322a-86ec-5b29-ac24-b6b2e3dd309c |  | note | Acceptance Criteria - NZTA M04 / Project Spec
label | c1fcd9e5-5903-51e4-aeaf-f55b8cdbb0aa |  | note | Record documents - Certificate in contractor's site folder
label | 2cf42e8b-400a-573f-968d-84271c8dce34 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | 4.2. CONSTRUCTION - SUBBASE / BASECOURSE
checkpoint-status |  |  | checkpoint | 4.2.1 - Modified Subbase / Basecourse
label | c4b55151-078b-5776-9467-77ba9beb996e |  | note | Detail of Activity - Spreading of powdered stabilising agent
label | 90fbcf52-bb06-562b-8d23-ea5fa0765413 |  | note | Action (Hold, Monitor, Witness) - M
label | 02851871-9200-5f7f-99a0-fac669ddf09a |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer/load cells
label | f0bbe1d0-5072-55ff-bc83-42e7183844bc |  | note | Inspection / Test method - Measurement each run
label | 680de5e6-7623-5289-8b69-a2e7398db053 |  | note | Acceptance Criteria - ± 5% of specified rate
label | f4af7f8d-2c47-51c8-a085-76cb7ad41926 |  | note | Record documents - Worksheet
label | eb2c7d73-80d9-5aba-a702-6f1edb6417e4 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.2 - Modified Subbase / Basecourse
label | 39d14918-6b46-53ea-85b8-081f66b1aa20 |  | note | Detail of Activity - Mixing process
label | 3b5c4d95-face-5668-961f-d890ddf64708 |  | note | Action (Hold, Monitor, Witness) - M
label | 432647e3-1258-5a22-8130-9d2d41acb8ae |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going visual assessment
label | 87837963-5eaf-5e09-885f-7603a69b3a81 |  | note | Inspection / Test method - Visual Inspection
label | f614bf3c-5268-509e-bfd6-0c97ac0352fe |  | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps and construction joints as per spec
label | d5a4e8fd-9f9c-502d-82b6-44f4c8f75c60 |  | note | Record documents - ITP / Daily work Log
label | 58b264e5-90e2-50c0-9cc0-4b6cabccad3d |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.3 - Modified Subbase / Basecourse
label | 5e0c7d69-ae56-5c9a-bb56-c517f45f61b9 |  | note | Detail of Activity - Bitumen Injection
label | 3500c8a0-623d-5b42-ae3b-b15a20c31814 |  | note | Action (Hold, Monitor, Witness) - M
label | 94bbf7a5-afd3-586f-88ef-7212998a3d92 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer supplemented with tanker dips at the end of each run
label | cd4dc782-6192-57c7-a8e3-34fbfd0da157 |  | note | Inspection / Test method - Measurement each run
label | f0d46db4-77a5-508d-84bf-288ac097dc37 |  | note | Acceptance Criteria - ± 5% of specified rate
label | facce857-e400-547a-a0c8-c4a616de9c37 |  | note | Record documents - Worksheet
label | 0a8133bc-dd72-5a1e-8712-e7c9f08635fe |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.4 - Modified Subbase / Basecourse
label | a841bf0a-96c6-5ae2-a292-c25d4ea86224 |  | note | Detail of Activity - Depth of stabilisation
label | ac2b0a25-5ac8-5133-8ec0-b967513e0e04 |  | note | Action (Hold, Monitor, Witness) - M
label | 4b22b9e3-2f7b-54ce-9b1f-a95f424910e3 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | 60bceb2c-b8f1-5c9f-be2e-939384563abf |  | note | Inspection / Test method - Measurement
label | b9f1e11b-3c31-5686-bfc9-c38657872043 |  | note | Acceptance Criteria - +15mm / -5mm from specified depth
label | d65bc65d-1bff-5140-98a3-a9deb69c4ae3 |  | note | Record documents - Daily work Log
label | f52f5dca-1c53-52de-8e4f-34f2b2d9c659 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.5 - Modified Subbase / Basecourse
label | 90a39156-75b7-53e1-95d0-302d8de0b880 |  | note | Detail of Activity - Modified Maximum Dry Density
label | ff1dfe01-df6b-50ab-99e8-b45143a5decf |  | note | Action (Hold, Monitor, Witness) - M
label | 0c0ac0df-947e-5497-83c9-6f83d20d1d42 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 3 per Lot
label | 2fee96d8-15b4-5edc-ba1c-e4bd4b546539 |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 65f29c5f-48c5-5de3-8bc4-38f5e8c883a0 |  | note | Acceptance Criteria - For analysis of DoC
label | 86f3b2ff-916b-5ac0-af0d-3d02656a4ac7 |  | note | Record documents - IANZ Report
label | 213ff160-d540-59dd-83f2-da6dcf8c092d |  | note | Responsibility - Contractor
label | 6e1690b9-ef98-5e0b-810f-de1bd38d4141 |  | note | Comments - Basecourse only
checkpoint-status |  |  | checkpoint | 4.2.6 - Modified Subbase / Basecourse
label | 31b27c89-5d48-5439-82a1-6ef4b993d517 |  | note | Detail of Activity - Degree of Compaction
label | 647af9f9-3630-58f5-8627-19c1d17f6a15 |  | note | Action (Hold, Monitor, Witness) - H
label | 27271422-d00c-5617-afe0-ff22bf074c85 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | 436b5cd9-5bd6-5763-8a20-bb89a4f556ce |  | note | Inspection / Test method - NZS 4407.4.2.1
label | 67e35b38-5b59-5140-88ab-61909d25e2bc |  | note | Acceptance Criteria - NZTA B/5:
label | c4db9df7-bd18-5479-8c6e-30b111d81995 |  | note | ○ Subbase DoC Mean ≥95%, Miin ≥ 92%
label | d6342e93-c0cf-57fd-87e6-1632111b6503 |  | note | ○ Basecourse DOC Mean ≥98%, Min ≥ 95%
label | c2494b12-7728-5df7-8cd0-3eca0f2dde1c |  | note | Record documents - IANZ Report
label | 5c78e449-f29e-5f9f-a3a7-0067d718034c |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.7 - Modified Subbase / Basecourse
label | 4fd532a2-51cd-5389-bf50-b6c238a8e1b3 |  | note | Detail of Activity - Layer Width
label | a212aab3-81fb-54e5-9fbb-fed6b491022c |  | note | Action (Hold, Monitor, Witness) - H
label | 35fc2eda-13e7-534d-91d3-6b0b0f8bf42d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | cd2fe7d7-2cfe-5938-a611-3724f1e23085 |  | note | Inspection / Test method - Measurement
label | 414f4303-6870-5e96-93ba-f212d7b6e0e4 |  | note | Acceptance Criteria - ± 10 mm
label | 3ea77464-fe08-58c9-9e2d-65941cf1eada |  | note | Record documents - Survey
label | 70a44bf7-695a-57aa-816c-fcd81aec8ef2 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.8 - Modified Subbase / Basecourse
label | 3ff36b47-ed79-51a0-b9b2-0cf57d9c5f7e |  | note | Detail of Activity - Surface Shape
label | 1115356f-1ce8-51f4-a9e0-1b00021009c5 |  | note | Action (Hold, Monitor, Witness) - H
label | 78a1dabe-888f-5563-9e21-fbfb3055de80 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | 1042b239-d0b3-5667-845f-e8ad0ebe2cce |  | note | Inspection / Test method - Measurement
label | 9ce694cc-63b5-5d2e-8828-fc629fdf9e0d |  | note | Acceptance Criteria - < 6mm using 3m straight edge
label | 61801355-404d-5978-b666-0a4699e6ed22 |  | note | Record documents - Worksheet
label | 026d7883-d4a7-5376-bb01-d2c70fb0df23 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.9 - Modified Subbase / Basecourse
label | 85fde303-71cc-5082-95b8-61bcf4b2799a |  | note | Detail of Activity - Surface Levels
label | 70e2df83-a65a-5727-b577-d21c66e076e8 |  | note | Action (Hold, Monitor, Witness) - H
label | a969eef0-1609-5fe1-8ff6-d57fff73f0c0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | 2a1304b5-6f80-5ceb-aa6c-3edaefda3667 |  | note | Inspection / Test method - NZTA Z/16
label | 450f87ec-44fb-5493-821f-5ec941d7237c |  | note | Acceptance Criteria - Subbase:
label | 95b25ec7-271d-56c4-9f5a-f2662d68442f |  | note | ○ No Concrete Channel: -25mm + 5mm with Concrete Channel: -25mm + 5mm
label | b91210e2-ad7e-5636-9cd7-7f92c67eb296 |  | note | Basecourse:
label | d41fb179-80e9-547a-ad5b-322d221bc6ad |  | note | ○ No Concrete Channel: -5mm + 15mm with Concrete Channel:
label | b61e0b08-c292-5f55-b15d-cf904f7d0c33 |  | note | – within 1m from channel: -5mm + 5mm
label | d86954d8-d645-5b92-8025-0f0a6ac22ed7 |  | note | – other locations: -5mm + 15mm
label | a0aa715d-eb63-5a79-8e92-1b1eb8c6a2b1 |  | note | Record documents - Survey
label | 9ad5f545-8672-5dce-b9db-650f901bdf6a |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.10 - Modified Subbase / Basecourse
label | 72b7bacf-129e-5a6a-8c89-0a2b9bbfcc88 |  | note | Detail of Activity - Stabilised material strength - ITS
label | a6a5605a-4b4b-5f89-a008-50ef580634c8 |  | note | Action (Hold, Monitor, Witness) - S
label | b134fd32-94ac-5be3-a0ed-81f471315597 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 3 soaked ITS + 3 dry ITS per Lot
label | bd5d6b04-13fb-5413-b99c-4df5f6d9096e |  | note | Inspection / Test method - NZTA T/19
label | e5063bc5-0a80-5851-bab1-06f5b9875366 |  | note | Acceptance Criteria - Modified:
label | 92a13790-07c9-5b67-b2f1-e33f9ad715d1 |  | note | ○ Dry ITS: 150kPa to 350 kPa
label | bff23d3b-1e15-5548-8a63-28db106128c6 |  | note | ○ Soaked ITS: 100 kPa to 300 kPa
label | ecb7058b-1810-549c-b679-dbb1791183e8 |  | note | Bound Subbase:
label | 7c7cc5f3-1baf-5c54-851e-2b9eb9863997 |  | note | ○ Dry ITS > 500 kPa
label | 95fee2f8-93c8-56cc-a1ec-2d9ab722ec31 |  | note | ○ Soaked ITS > 450 kPa
label | 5656ce9f-a574-56ec-9d75-e3a9cf9df289 |  | note | Record documents - IANZ Report
label | 6ff95290-2fa2-544d-8fd4-c17fca26ac0e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.11 - Modified Subbase / Basecourse
label | 640f4ab7-34da-56dd-bb40-7321430d5af8 |  | note | Detail of Activity - Stabilised material strength - UCS
label | 0e1debca-3037-5703-8cd2-7ee406d4bc60 |  | note | Action (Hold, Monitor, Witness) - S
label | 7b7c193d-8ac8-5b56-8476-79298d6041c2 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 3 per Lot
label | d5bf98de-e0ca-5b45-ac47-ae3b9cd171c2 |  | note | Inspection / Test method - NPTG Guide
label | 202b8f5a-625f-5873-b871-2af823ee8dd0 |  | note | Acceptance Criteria - UCS < 0.75 Mpa
label | 980dee47-9fad-5896-a5bb-99e38311c175 |  | note | Record documents - IANZ Report
label | 34d5f2d2-e578-5ca8-9483-8de4b5b37727 |  | note | Responsibility - Contractor
label | 2cc0007b-f75c-56b2-9062-3389ba39efc5 |  | note | Comments - If ITS testing is not available
checkpoint-group |  |  | section | 4.3. CLOSE OUT MODIFIED LAYER LOT
checkpoint-status |  |  | checkpoint | 4.3.1 - Non-conforming results
label | c84ab176-1e86-59ad-9315-7fd1aed131f7 |  | note | Detail of Activity - Assessment of all test results for conformity
label | 999eb18a-661a-5a3c-b0c8-66faf0060eaa |  | note | Action (Hold, Monitor, Witness) - H
label | 299ad3b1-9966-51a3-9d87-b877948430c0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | 4f002b5c-3ef8-52ce-b8d1-668813edafdf |  | note | Inspection / Test method - Site Inspection
label | 62aa7735-538d-59bc-b804-214dc6169e12 |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | f0a4c066-7a76-50da-b212-4460187537c3 |  | note | Record documents - NCR
label | 698edbc9-aad7-5681-8e69-9d9dad29001e |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 0c7e0ada-8499-51b0-84ec-b418e6219475 |  | textbox | Contractor's Rep Name:
text | 195a2fac-7eb5-552e-aa17-f94f2760ad34 |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Verified Program |  |  |  |  | Yes | Verified Program | a3ce49c5-a4d1-42f2-95c4-acf61bdfbb16
checkpoint-status |  |  | checkpoint | Verified Program
checklist-sectioned |  |  | checklist | ITP - Sealing - Bituminous Seal Coat | itp |  |  |  | Yes | ITP - Sealing - Bituminous Seal Coat - Abattoir Road | ab29821d-d425-4deb-a6af-39510d9c7ee9
checkpoint-group |  |  | section | 6.0. SETOUT AND PREPARATION
checkpoint-status |  |  | checkpoint | 6.0.1 - Seal Design
label | 7af6dc3f-f831-59cb-8cc7-b1cc74cfed84 |  | note | Detail of Activity - Seal design outlining all design assumptions
label | cb3520e5-8203-5535-add3-013c5328fdf3 |  | note | Action (Hold, Monitor, Witness) - H
label | bb90a0d0-9cd3-5612-9685-ae181902c692 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per seal application type
label | 89a9dc92-3ce8-581b-b09e-3023e563e7c7 |  | note | Inspection / Test method - Project Specification
label | 0e12e9f8-f5f6-5b35-840a-00574a9e93d7 |  | note | Acceptance Criteria - New Zealand Chip Sealing Handbook
label | e723bf1e-65a8-524c-ae3d-8609d3e6c0cc |  | note | Record documents - Seal design in contractor's site folder
label | e1cc3568-4051-52b5-bd48-ffacf5862ada |  | note | Responsibility - Designer / Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6.0.2 - Bitumen Distributer Certification
label | 37b4a424-9f5e-5f0c-a09a-4a1495d3b563 |  | note | Detail of Activity - E2
label | 182c0af5-6510-5e4a-8ec8-2490d08a919b |  | note | Action (Hold, Monitor, Witness) - M
label | 79e7d946-ed92-5cc1-bd4e-3b402669a320 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per annum
label | a740265b-7245-571f-896e-6996ed64c89b |  | note | Inspection / Test method - CCNZ E2
label | 8fa8c235-0f8d-576a-ae16-dc6dfb83a325 |  | note | Acceptance Criteria - Must be operated as per CCNZ E/2
label | 2c3a91d1-1503-57ed-8ba3-72358a93ea39 |  | note | Record documents - Record Distributor #
label | 02ad4ee0-21a3-5aa9-bf5d-9dbc7f973cc4 |  | note | Responsibility - Contractor
label | cab6df3f-e82c-54c9-a887-183695defc2e |  | note | Comments - Certified Distributor is on the CCNZ website
checkpoint-status |  |  | checkpoint | 6.0.3 - Pre-Seal requirements
label | dd528d5d-3e28-5fa4-aab9-49c5d8e43d62 |  | note | Detail of Activity - Visual inspection of surface to be sealed
label | 91deae14-dd07-5248-b6b5-ad97e2b1c83a |  | note | Action (Hold, Monitor, Witness) - W
label | 117506c5-472d-53b4-a271-92ec7ec39efe |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - per sealing schedule.1 Lot = 1 day's production and < 1500m2
label | d5b51c36-5afd-586d-b0ae-9361a738570a |  | note | Inspection / Test method - Visual Inspection
label | 2d11766e-98b2-5d03-9cfa-7f10fef2f4ab |  | note | Acceptance Criteria - NZTA B/2, B/5, B/6, B/7, B/8 or M/10 (whichever is applcable)
label | 61e679e2-ce0e-5766-9f8a-2adebdeb6f32 |  | note | Record documents - Contractor's site diary
label | df703fad-7923-5c3a-b05e-c10064f8741b |  | note | Responsibility - Engineers Rep
label | a5b27e43-eefa-597e-a8ab-266bfb5d5b07 |  | note | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint-status |  |  | checkpoint | 6.0.4 - Pre-Seal requirements
label | 7ae4b53f-9bf7-54c2-a291-91a7fc951236 |  | note | Detail of Activity - Dry back Moisture Content (if 1st coat)
label | 495601dd-b9bf-5843-a9ff-6fe6b33bad91 |  | note | Action (Hold, Monitor, Witness) - H
label | d7693671-560f-5bb1-924a-afaccfe2f337 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | f442d23f-8100-5378-847c-ae74c54d1598 |  | note | Inspection / Test method - NZS 4407.4.2.1
label | 67fdf0fe-0677-5d5a-acfd-292c28a81014 |  | note | Acceptance Criteria - DOS ≤ 80% preferably ≤ 70%
label | c8d24c97-5bb7-56f7-bda3-2995457312f8 |  | note | Record documents - IANZ Report
label | ebce6892-bec9-5e85-b30a-822b7fbcbffd |  | note | Responsibility - Contractor
label | 504e28d0-fc01-528d-b8e7-c7c95a367030 |  | note | Comments - Only required if pavement widening extends into trafficked lane
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6.0.5 - Pre-Seal requirements
label | dc0b0af8-a97e-536f-9809-a065ea564221 |  | note | Detail of Activity - Clegg Hammer (if 1st coat)
label | 2d6f4989-1f78-5c73-8c4e-5d02c6f46e41 |  | note | Action (Hold, Monitor, Witness) - M
label | 6e9b2559-174a-5250-b742-71403b7919e0 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 CIV per 10m, 1 Lot < 300m
label | 7e56815b-6cf8-5e58-9135-d96cd2a2bbe5 |  | note | Inspection / Test method - Clegg Impact Value Test
label | 29d290da-5357-5056-a56b-c5e10e914429 |  | note | Acceptance Criteria - Average CIV > 40, Min. CIV > 35
label | 55a3f92d-2de6-50f4-81d1-5dc2b7f7a9ee |  | note | Record documents - Contractor's CIV form appended to Contractor's daily diary
label | 65ae2ada-e107-5aee-983d-7a1a0ddf96d3 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | 6.1. MATERIALS - PRIOR TO CONSTRUCTION PHASE
checkpoint-status |  |  | checkpoint | 6.1.1 - Source Properties (All aggregate)
label | 1aa463fb-9986-527e-b8df-5638f30b000b |  | note | Detail of Activity - Crushing Resistance
label | c4456bb0-c32e-5205-8198-5ca04ace3a38 |  | note | Action (Hold, Monitor, Witness) - M
label | 0c062d60-b006-5a5e-9363-f597617bdeba |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2009
label | cc7726a8-4c72-5220-b71d-ab37b89e6f9f |  | note | Inspection / Test method - NZS4407: 3.10
label | 0c0cd26b-9ce0-5746-bd79-41bbcf3b13d7 |  | note | Acceptance Criteria - < 10% under load of 230kN
label | 9bd10638-b094-57a9-81b8-8b1cc97c490f |  | note | Record documents - IANZ Report
label | 9c0baffe-5931-5fad-a1aa-6da4db5d3e0c |  | note | Responsibility - Contractor
label | 5e0ab8e6-7cd5-565e-b877-754760888c06 |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.2 - Source Properties (All aggregate)
label | dceba8fc-6396-5ff6-817c-6ba5b1b6b9ef |  | note | Detail of Activity - Weathering Resistance
label | 96d218f7-f1be-5796-935a-254112c695a9 |  | note | Action (Hold, Monitor, Witness) - M
label | 2fc019e4-a5c3-503b-8f6e-6f793b814ce9 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2010
label | 019bc777-1c6f-5b93-8215-8c8204fc71d2 |  | note | Inspection / Test method - NZS 4407: 3.11
label | 8f77db5e-e555-5b3e-ade4-e33343cabd89 |  | note | Acceptance Criteria - AA or BA
label | 25f76203-bb45-5257-a020-27d662fdae9a |  | note | Record documents - IANZ Report
label | b262cf0d-0e16-50c4-93f1-198811630ad4 |  | note | Responsibility - Contractor
label | d464dc2b-f6f2-52c1-af5d-7ce1b743d883 |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.3 - Source Properties (All aggregate)
label | 86ec5e13-ef67-5aef-b712-b1e40894a265 |  | note | Detail of Activity - Weak Particle Test
label | fdbc964d-ba58-540e-b1e5-f5a179a1d3aa |  | note | Action (Hold, Monitor, Witness) - M
label | d36a17c3-c0eb-5ec7-84e7-eba5e6c0bbcc |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | bea816f4-5e29-52b3-a17d-e584414bf3c1 |  | note | Inspection / Test method - AS 1141.32 - 1995
label | 17b6c24a-b082-5ab7-a403-67aa8d3d72bf |  | note | Acceptance Criteria - Max of 1% of unsound material
label | 35150fed-8378-57eb-841c-d7d1107800ad |  | note | Record documents - IANZ Report
label | d7c9169e-9083-554a-b0f3-1e9a99f3acc7 |  | note | Responsibility - Contractor
label | 1cda18ae-529d-5209-9d1a-59a708af122c |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.4 - Source Properties (All aggregate)
label | 189b0f21-3e00-55cc-b6f4-10d991208c98 |  | note | Detail of Activity - Polished Stone Value (PSV)
label | 2d189bc7-8e01-5e35-bac6-16eb30251e0b |  | note | Action (Hold, Monitor, Witness) - M
label | f8db0784-2359-529c-839e-516941791289 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per year
label | 3c91fc9e-f389-50fe-a8aa-a6abfbdd62db |  | note | Inspection / Test method - BS EN 1097-8:2009
label | 9400497c-2e8e-5cc4-8833-93758dcb4ff6 |  | note | Acceptance Criteria - Lower value of 2 tests (or median value if more than 3 tets are available) ≥ NZTA T/10 and/or project specifications. 2 tests must be < 2 years old
label | 1d6da195-1fef-5c75-b5a6-9ea05236232c |  | note | Record documents - IANZ Report
label | d44c9c4f-5602-5389-9fa0-67dc2516a884 |  | note | Responsibility - Contractor
label | e88c731c-332f-5528-bf07-3fdbe5a9c81c |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.5 - Production Properties Grades 2, 3 and 4
label | c644e66d-5209-5101-8f7c-4c0837759682 |  | note | Detail of Activity - Cleanness
label | 34b8346d-4dc7-5596-adb3-d5ca59b35488 |  | note | Action (Hold, Monitor, Witness) - M
label | c75e9a59-f918-50d5-b1d3-3bfa126d623b |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | 07262e84-e842-51e1-a97d-e7df9fc5f1d6 |  | note | Inspection / Test method - NZS 4407: 3.9
label | 55fa32f7-881e-58aa-9221-94109517dea6 |  | note | Acceptance Criteria - Gr.2 ≥ 89; Gr.3 ≥ 87; Gr.4 ≥ 85
label | 9c4b3c3d-7b1f-5b5f-b7e2-b153d961b152 |  | note | Record documents - IANZ Report
label | 12f4df84-6233-56e7-87e4-06da396a215c |  | note | Responsibility - Contractor
label | 4a9e6bda-d546-582c-abda-4ca7ac5ee54c |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.6 - Production Properties Grades 2, 3 and 4
label | bc319fc7-eff0-5f91-a574-1b3396c7abbc |  | note | Detail of Activity - Size and Shape
label | 89201187-6c43-5419-8ba4-d171c6f9cc70 |  | note | Action (Hold, Monitor, Witness) - M
label | ef873fe9-0fd6-5f28-8410-4c0572be1b46 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | 1f5005d3-7ccf-5f35-8eae-1d1591b8ae09 |  | note | Inspection / Test method - NZS 4407: 3.13
label | 38f53a23-3870-5ce0-a583-d1daba9baa30 |  | note | Acceptance Criteria - NZTA M/6 - Table 2
label | f6c0749c-6dcf-5ff4-84a6-f2171a02d754 |  | note | Record documents - IANZ Report
label | 86a8e4b8-3901-52e1-a771-b05e140a046e |  | note | Responsibility - Contractor
label | 23874459-92eb-58dd-8b7f-027ca7e6ac3f |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.7 - Production Properties Grades 2, 3 and 4
label | 085feede-cf39-5aa3-a3a1-e82bde0b31f5 |  | note | Detail of Activity - Broken Faces
label | 290520bd-b2f3-5ed5-b109-3bbb7cd5e6f7 |  | note | Action (Hold, Monitor, Witness) - M
label | 5e288da2-432f-58c2-969e-513b690921d3 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | 27465857-f428-5e02-ab63-40d52c3cea32 |  | note | Inspection / Test method - NZS 4407: 3.14
label | f4220a35-d213-5890-9880-7cc439933228 |  | note | Acceptance Criteria - ≥ 98% with at least two broken faces
label | 8069a561-f172-51b0-b6bd-9ee7f2aafb32 |  | note | Record documents - IANZ Report
label | a21625b6-faac-53c6-a356-b340dff7dc05 |  | note | Responsibility - Contractor
label | 615584e2-ac5b-5263-b44b-c09eb82414d5 |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.8 - Production Properties Grades 5 & 6
label | b74f8e45-ebd9-5009-8cd0-3851187a7098 |  | note | Detail of Activity - General Soundness
label | a9193d85-2e16-5e3c-8c3d-291bd4cf8e12 |  | note | Action (Hold, Monitor, Witness) - M
label | 7ec575e6-f677-5051-82b9-16be08a10191 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | 0700be5c-8358-560f-b389-db1753faed22 |  | note | Inspection / Test method - Visual
label | 19799e74-34ec-5937-9944-83423d058f3f |  | note | Acceptance Criteria - Clean, tough particles, free of soft, weathered, disintegrtaed or deleterious material.
label | 507cfec6-02ff-5535-8529-6e19b82d1a56 |  | note | Record documents - IANZ Report
label | 7d90f9fe-f160-5921-b676-8276f35c0ead |  | note | Responsibility - Contractor
label | a2dd7c9e-a55d-541e-8550-9556b444d404 |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.9 - Production Properties Grades 5 & 6
label | 45fc000b-434f-517b-b032-030cf24178fa |  | note | Detail of Activity - Grading
label | a36d3b24-5d7d-506b-b58e-9f8a7bdd4bf1 |  | note | Action (Hold, Monitor, Witness) - M
label | bb1f366f-947f-5fdf-aa50-2c91a74345eb |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - RNZ 9805:2011
label | 498213b5-13bd-52aa-9a32-8d2b6e8d709d |  | note | Inspection / Test method - NZS 4407: 3.8
label | 3d62e460-985c-58f3-8c93-ac1a09003604 |  | note | Acceptance Criteria - NZTA M/6 - Table 3
label | 63c68b56-ab16-55c3-80e4-c17022da02a2 |  | note | Record documents - IANZ Report
label | cf1152c1-1ba2-560d-889a-5dd747d05345 |  | note | Responsibility - Contractor
label | 3d019583-c3cd-5def-83d4-08ea3f602697 |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.10 - Bitumen Properties
label | 30871d8d-825e-5533-a679-a4720423966d |  | note | Detail of Activity - As per ITP 5 (previous Tab)
label | 1ac80e1e-def7-5df5-8233-3943f7559559 |  | note | Action (Hold, Monitor, Witness) - M
label | 2ea8e379-0577-500a-81c7-d77a3bf4c162 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - refer to ITP 5
label | aa365508-29bb-5671-bfdb-bbc220b1a36c |  | note | Inspection / Test method - Various
label | aab1feec-e5bb-5c0e-8928-4fabca933fe2 |  | note | Acceptance Criteria - Various
label | 92c7f458-8937-55aa-a2d8-156fb19abb5e |  | note | Record documents - Various
label | e943166e-db55-5673-8969-3e7842dfa19d |  | note | Responsibility - Contractor
label | 4463e391-de36-5b4b-a4fa-c5589903f3f7 |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-group |  |  | section | 6.2. CONSTRUCTION
checkpoint-status |  |  | checkpoint | 6.2.1 - Bitumen Sample
label | e9ce2371-c06b-51ea-ae4e-6bb5aaa0bd35 |  | note | Detail of Activity - Audit sample(s)
label | 3a497ec4-d4ca-5e2c-8fb4-a8b2dcec0df6 |  | note | Action (Hold, Monitor, Witness) - M
label | bc144530-794d-5222-83de-199a27109bda |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per sprayer
label | 80a1f791-50a2-50cc-b37a-79d10bdff08c |  | note | Inspection / Test method - ASTM D140 or AS2008
label | d48a187d-96bc-5e24-988e-4a667c9f90e2 |  | note | Acceptance Criteria - N/A
label | 6b4ac462-bb63-5a45-8a0b-0b4f88aceb18 |  | note | Record documents - Contractor's site diary
label | f9c072ce-b2ae-57a2-b2d2-09fae048ea77 |  | note | Responsibility - Contractor
label | 95e730fb-43d3-52c0-b3d8-a6314d81e4b7 |  | note | Comments - Retain for duration of DLP
checkpoint-status |  |  | checkpoint | 6.2.2 - Adhesion Agents
label | 9f1c51ad-fdeb-5889-b259-224b5b6614e3 |  | note | Detail of Activity - Adhesion Agents
label | 80aaf298-aa89-5db8-b786-c5da39b8a9bc |  | note | Action (Hold, Monitor, Witness) - M
label | 2a614439-ef29-588e-a6d7-de234380dec6 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to use
label | 4f52c1df-1951-530e-9b06-d423635b151d |  | note | Acceptance Criteria - NZTA M/13
label | 77160c76-3312-54f3-a69e-39a670330cdb |  | note | Record documents - Certificate in contractor's site folder
label | eda36209-57f2-51e5-bef2-12e41c401a89 |  | note | Responsibility - Contractor
label | 6e2e196b-d903-5ef2-b28c-7557d2deda5d |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.2.3 - Aggregates
label | f5191152-109b-5d78-92d5-1b2666285c1a |  | note | Detail of Activity - Audit samples
label | 927b5f37-17af-565a-a795-56eced5ff750 |  | note | Action (Hold, Monitor, Witness) - M
label | 1fd0c203-5eee-5afe-906a-452752abef7d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 20 kg per stockpile
label | 92141f7c-bab2-59f4-9391-b24a240a69fd |  | note | Inspection / Test method - N/A
label | 0acaaead-a032-52b9-8d79-883b5ffa0e1b |  | note | Acceptance Criteria - Stored in a sealed plastic bag in a covered environment
label | 5ec223b8-f541-5a23-9ec9-cb50959a7d1b |  | note | Record documents - Contractor's site diary
label | e228c486-c688-54f4-bcd9-97d0ec89a7e2 |  | note | Responsibility - Contractor
label | 3b5beaec-f7b4-5edd-8a9e-6f457e341422 |  | note | Comments - Retain for duration of DLP
checkpoint-group |  |  | section | 6.3. CONSTRUCTION - 1st Coat as per TNZ P/3
checkpoint-status |  |  | checkpoint | 6.3.1 - Bitumen application
label | 37edace3-c2dd-5f47-b9d1-8c22e98eb0ea |  | note | Detail of Activity - Bitumen Spraying Temperature
label | e84621ef-1e24-5fc5-85ac-2d6e146826c8 |  | note | Action (Hold, Monitor, Witness) - M
label | e7ce2880-1f37-5821-8d18-0831fd6b62f8 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Ongoing with non-going heat sensing gauge
label | 852b2503-8b3c-5c80-8412-3a906a32a075 |  | note | Inspection / Test method - Non-contact heat sensing gun
label | 999fcc59-5c03-5123-b9ce-0503792ab4b7 |  | note | Acceptance Criteria - NZTA P/3 - Table 2
label | a26db8c2-1177-5986-a58a-808dd05ca368 |  | note | Record documents - Contractor's Spray sheet
label | d3b1d6ac-5d23-5084-bd8f-a7d9ba7d0063 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 6.3.2 - Bitumen application
label | 89cf47b3-7c84-5539-aeec-45de9c237dc8 |  | note | Detail of Activity - Bitumen Application rate (BAR)
label | bbd81ad1-bc2b-501c-ade9-93f095661290 |  | note | Action (Hold, Monitor, Witness) - M
label | f7ae5706-0d84-5a12-8a3f-80dc8a1dfdc5 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every sprayer run
label | 2f97420c-2a6d-5008-b797-952fa921452f |  | note | Inspection / Test method - Dip sprayer
label | 3387c986-e3ba-5421-a43d-e4f6072fd7e7 |  | note | Acceptance Criteria - TNZ P/3
label | 755763d8-750c-5806-b803-4382c58db361 |  | note | Record documents - Contractor's Spray sheet
label | fbb9e43c-9eb6-511f-a3bf-8cecfaae5327 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 6.3.3 - Sealing Aggregate application
label | c47819e3-6bd3-5e5d-a03b-256bba8e7d36 |  | note | Detail of Activity - Application rate (m2/kg)
label | befdc96c-1f54-5702-ad11-fa5a7128ab7d |  | note | Action (Hold, Monitor, Witness) - M
label | a0207865-e126-5e94-986a-88e0aafb4a2d |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Continous
label | 90065a33-a8c7-5252-ad5a-d26916dbef10 |  | note | Inspection / Test method - Calculation
label | 96fbb9a6-a06a-5863-9776-af0a6e99def0 |  | note | Acceptance Criteria - Refer TNZ P/3 - section 28
label | e68c46fa-d3a4-5b16-bcc7-aee5c421c9b7 |  | note | Record documents - Contractor's site diary
label | 92d72363-b780-5d1a-8cfd-30204cc315d3 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | 6.4. CLOSE OUT SEALING LOT
checkpoint-status |  |  | checkpoint | 6.4.1 - Non-conforming results
label | b2d5113a-d828-5cbf-bd96-fd047ee319fb |  | note | Detail of Activity - Assessment of all test results for conformity
label | 00a0b8d2-58c9-599c-b452-90552eaa561d |  | note | Action (Hold, Monitor, Witness) - H
label | f1d70d96-ca68-55c7-b36b-7ba892db7026 |  | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | 6e807a67-4452-55ba-b49b-2b1d672749f2 |  | note | Inspection / Test method - Site Inspection
label | b119359d-14d0-5e30-8e0a-ab4c4d6cc77c |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 85ad8aab-7111-54f3-8657-a116264b2291 |  | note | Record documents - NCR
label | 802827b8-abe8-5715-a746-6c7cd625c2fa |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 52c27d59-4f80-5fcc-9650-ee40ee4c97c6 |  | textbox | Contractor's Rep Name:
text | 7aac8142-60fb-5fbe-a0d5-31979001e5af |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Approved JMF |  |  |  |  | Yes | Approved JMF | b8eb8d25-6b00-4555-88b1-fd1d5c217015
checkpoint-status |  |  | checkpoint | Approved JMF
checklist-flat |  |  | checklist | QMP |  |  |  |  | Yes | QMP | dd354f9d-68fb-42bb-bddc-cadbbf7b50ae
checkpoint-status |  |  | checkpoint | QMP