## Folder Structure
QA Folder Structure
Facade
| Zone A (Building B) | Leave as a folder
| Zone B (Building A) | Leave as a folder
| Zone C (Buildings C, D & E) | Leave as a folder

## Matrices
Matrices - One for each of the 3 folders in folder structure tab - layout as per below
Dynamic row ----> | Facade Inspections - Zone # (Building #) | CP1 | CP2 | CP3 | CP4 | CP5 | CP6 | CP7 | CP8 | CP9 | CP10 | CP11
ITP (added as they go)
ITP (added as they go)
ITP (added as they go)
ITP (added as they go)

## checklist
type | name | values | prefix | postfix | usage count | user addable
checklist-flat | Facade QAQC Checklist
checkpoint | Check for any visual defects (scratches, dents, marks, discolouration, oxidisation) |  | Mandatory Photo
checkpoint | Ensure tek screws have been removed from panels prior to installation |  | Mandatory Photo
checkpoint | Ensure there are no visible gaps in sealant, caulking and waterproofing components.
checkpoint | Ensure weep holes are present and are free of blockages
checkpoint | Ensure gaskets run the full length of the panel and are not cut, or falling away from the panel
checkpoint | Ensure no additional cuts have been made for lifting purposes and if so, remedial action has been implemented.
checkpoint | Torque testing of brackets are present once installed - photo of spray painted evidence |  | Mandatory Photo
checkpoint | Gutter plate and sleeve installed in correct position and sealed |  | Mandatory Photo
checkpoint | No loose items on panel that could come loose whilst lifting (i.E. Gutter sleeves, clip on extrusions, etc.)
checkpoint | Ensure end dams are present in areas adjoining other elements |  | Mandatory Photo
checkpoint | Check for low-e coating glazing