## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-028
[11 empty] | Revision : 1 | 2024-02-15
Client: |  | Wyndham City Council |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | K Rd |  | River Edge Terrace |  | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  | N400378 |  | Specifications:
|  |  |  | Structure / Component: Beaching |  | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : | 2024-08-20 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Construction Works
1.1 | Induction and safety measures are in place, safe work method statement (SWMS) undertaken |  | Prior to Commencing | All personnel on site have been inducted to the K Rd Project site and are informed of all relevant environmental management plans. Additionally, all necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS | Inductions Register/OH&S Co-Ordination Plan | Document review | Site Induction Signed. SWMS Signed | IP | Site Engineer / Site Foreman | N/A
1.2 | Relevant Permits Issued |  | Prior to Commencing | All relevant and/or applicable permits have been submitted and approved including details of all areas to be affected by works. | Permit Review | Document review | Excavation Permit # | IP | Site Engineer | N/A
2 | Construction Works
2.01 | Survey set-out |  | Prior to Commencing Excavation | Survey activities undertaken to ensure all works meet level and location requirements. Establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. | Document Review | Site Inspection | Survey records & pegs on the ground | IP | Site Engineer & Surveyor | N/A
2.02 | Conformity with Drawings |  | Prior to Commencing Excavation | The finished surface of the river edge terrace shall conform with approved levels, lines and grades as shown on the drawings or as specified placement in accordance with section 210. | Document Review | Site Inspection | Signed ITP | IP | Site Engineer | N/A
2.03 | Material Source Management |  | Prior to Commencing Excavation | Supply of crushed rock bedding material is from one source and will not change without first advising the Company’s Representative and agreeing with them the volume of fill to be obtained from that source. | Document Review | Document Review | Signed ITP | AP | Site Engineer | N/A
2.04 | Granatic Gravel |  | Prior to Commencing Excavation | Granatic gravel used for river edge terrace meets project requirements (size, type and quality). Material sample provided to client for rview and approval | Document Review | Site Inspection | Signed ITP | AP | Superintendent
2.05 | Feature Rock |  | Prior to Commencing Excavation | Rock material used for river edge terrace meets project requirements (size, type and quality). Material sample provided to client for rview and approval | Document Review | Site Inspection | Signed ITP | AP | Superintendent
2.06 | Enviromental & Cultural Heritage Factors |  | Prior to Commencing Excavation | Work affecting surrounding environment which is not pre-planned/approved in either Cultural heritage management plan (CHMP), Root Mapping Report, or Geotechnical reports is approved by client representative. | CHMP, Root Mapping Report, Cliff stability Report, Geotechnical Report | Site Inspection | Signed ITP | HP | Superintendent
2.07 | Preperation of underlying surface |  | Prior to Commencing Excavation | Areas on which feature rocks & granetic gravel are to be placed shall be compacted and trimmed as required to provide a finished surface level in accordance with the drawings. | Document Review | Site Inspection | Signed ITP | IP | Site Engineer | N/A
2.08 | Geofabric & Bedding |  | During Excavation | Geofabric to be placed on excavated surface, followed by 100mm (compacted) crushed rock bedding as per design drawings. | Document Review | Site Inspection | Signed ITP | IP | Site Engineer | N/A
2.09 | Feature Rock Placement |  | During Excavation | Feature rocks are placed as per design drawings. | Document Review | Site Inspection | Signed ITP | IP | Site Engineer | N/A
2.1 | Granatic Gravel Placement |  | During Excavation | Granatic gravel is placed as per drawings and spead to level at 50mm depth. | Document Review | Site Inspection | Signed ITP | IP | Site Engineer | N/A
2.1 | Final Inspection |  | After Excavation | client sign off to confirm river rock terrace meets design and quality. | Document Review | Site Inspection | Signed ITP | HP | Superintendent
2.11 | Environmental Impact Assesment |  | After Excavation | The installation has not negatively impacted the surrounding environment. No signs of instability or erosion post installation. | Document Review | Site Inspection | Signed ITP | IP | Site Engineer | N/A
COMMENTS |  | ______________________________________________________________________________________________________________________________________________________________________________________ ______________________________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent