## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1.28 - River Edge Terrace | itp |  |  |  |  | 1.28 - River Edge Terrace
section | 1.0 Construction Works
checkpoint | 1.1 - Induction and safety measures are in place, safe work method statement (SWMS) undertaken
label | Frequency - Prior to Commencing
label | Acceptance Criteria - All personnel on site have been inducted to the K Rd Project site and are informed of all relevant environmental management plans. Additionally, all necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | Reference Documents - Inductions Register/OH&S Co-Ordination Plan
label | Inspection / Test Method - Document review
label | Record of conformity - Site Induction Signed. SWMS Signed.
label | IP
label | Responsibility - Site Engineer / Site Foreman
checkpoint | 1.2 - Relevant Permits Issued
label | Frequency - Prior to Commencing
label | Acceptance Criteria - All relevant and/or applicable permits have been submitted and approved including details of all areas to be affected by works.
label | Reference Documents - Permit Review
label | Inspection / Test Method - Document review
label | Record of conformity - Excavation Permit #
label | IP
label | Responsibility - Site Engineer
section | 2.0 Construction Works
checkpoint | 2.01 - Survey set-out
label | Frequency - Prior to Commencing Excavation
label | Acceptance Criteria - Survey activities undertaken to ensure all works meet level and location requirements. Establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Survey records & pegs on the ground
label | IP
label | Responsibility - Site Engineer & Surveyor
checkpoint | 2.02 - Conformity with Drawings
label | Frequency - Prior to Commencing Excavation
label | Acceptance Criteria - The finished surface of the river edge terrace shall conform with approved levels, lines and grades as shown on the drawings or as specified placement in accordance with section 210.
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer
checkpoint | 2.03 - Material Source Management
label | Frequency - Prior to Commencing Excavation
label | Acceptance Criteria - Supply of crushed rock bedding material is from one source and will not change without first advising the Company’s Representative and agreeing with them the volume of fill to be obtained from that source.
label | Reference Documents - Document Review
label | Inspection / Test Method - Document Review
label | Record of conformity - Signed ITP
label | AP
label | Responsibility - Site Engineer
checkpoint | 2.04 - Granatic Gravel
label | Frequency - Prior to Commencing Excavation
label | Acceptance Criteria - Granatic gravel used for river edge terrace meets project requirements (size, type and quality).
label | ○ Material sample provided to client for rview and approval
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | AP
label | Responsibility - Superintendent
checkpoint | 2.05 - Feature Rock
label | Frequency - Prior to Commencing Excavation
label | Acceptance Criteria - Rock material used for river edge terrace meets project requirements (size, type and quality).
label | ○ Material sample provided to client for rview and approval
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | AP
label | Responsibility - Superintendent
checkpoint | 2.06 - Enviromental & Cultural Heritage Factors
label | Frequency - Prior to Commencing Excavation
label | Acceptance Criteria - Work affecting surrounding environment which is not pre-planned/approved in either Cultural heritage management plan (CHMP), Root Mapping Report, or Geotechnical reports is approved by client representative.
label | Reference Documents - CHMP, Root Mapping Report, Cliff stability Report, Geotechnical Report
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | HP
label | Responsibility - Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Preperation of underlying surface
label | Frequency - Prior to Commencing Excavation
label | Acceptance Criteria - Areas on which feature rocks & granetic gravel are to be placed shall be compacted and trimmed as required to provide a finished surface level in accordance with the drawings.
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer
checkpoint | 2.08 - Geofabric & Bedding
label | Frequency - During Excavation
label | Acceptance Criteria - Geofabric to be placed on excavated surface, followed by 100mm (compacted) crushed rock bedding as per design drawings.
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer
checkpoint | 2.09 - Feature Rock Placement
label | Frequency - During Excavation
label | Acceptance Criteria - Feature rocks are placed as per design drawings.
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer
checkpoint | 2.10 - Granatic Gravel Placement
label | Frequency - During Excavation
label | Acceptance Criteria - Granatic gravel is placed as per drawings and spead to level at 50mm depth.
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer
checkpoint | 2.10 - Final Inspection
label | Frequency - After Excavation
label | Acceptance Criteria - client sign off to confirm river rock terrace meets design and quality.
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | HP
label | Responsibility - Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Environmental Impact Assesment
label | Frequency - After Excavation
label | Acceptance Criteria - The installation has not negatively impacted the surrounding environment.
label | ○ No signs of instability or erosion post installation.
label | Reference Documents - Document Review
label | Inspection / Test Method - Site Inspection
label | Record of conformity - Signed ITP
label | IP
label | Responsibility - Site Engineer
checkpoint | Final Inspection
label | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
textbox | Print Name:
textbox | Position:
date | Date:
holdpoint | Sign ITP