## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | ef210d16-5af8-4b2b-ba9a-d86044d882e0 |  | checklist | Seismic Suite (non curtain wall) + Auto Door |  |  |  |  | Yes | Seismic Suite (non curtain wall) + Auto Door | 22fccd71-6f1e-41d4-9b95-8f1064e74cc7
checkpoint-status | 4b63d0fe-c07f-4786-b728-841197433550 |  | checkpoint | Opening Prepared, Wrapped & Datums
checkpoint-status | 85311c00-699d-4b91-9e10-cb53a892068b |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 65ff0138-1588-4ca3-b386-dbec4db4ecd9 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 52d888c2-3349-4603-8806-59723848a535 |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 8a6b8dcb-59f5-46f8-bb26-3db9d1431a65 |  | checkpoint | Airseal and Internal Flashings (Photo)
checkpoint-status | e831df05-3522-4222-a040-afaee0741d98 |  | checkpoint | External Flashings / Weather Seals / Drainage
checkpoint-status | b03122bc-6701-4603-a8fc-401f559b512d |  | checkpoint | Site Glazing Completed
checkpoint-status | 2e2e189e-372d-4229-a3ad-08859b35f7cc |  | checkpoint | Auto Door Installed
checkpoint-status | 7fb841e6-703f-48c2-8aff-c85d3e1aa9f2 |  | checkpoint | Trade Clean
checkpoint-status | cc9beadc-d8f0-4ec1-8c67-ea61d94625dc |  | checkpoint | Wights - Sign Off
checklist-flat | b32f0332-f9c4-4e8b-a216-dfe434cba8ea |  | checklist | Seismic Suite (Curtain Wall) |  |  |  |  | Yes | Seismic Suite (Curtain Wall) | 37720227-3ab4-4639-99a2-34be78362491
checkpoint-status | d6cd87f2-1523-49ed-be9a-a2e3a5bb443d |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | b116b686-6bad-4263-9c21-87ff43bb25ad |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 1bb08395-2b61-4c95-8608-8dc03b26549c |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 1b5b1e92-421d-4d68-b132-96228691b25b |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 9b56c83b-019a-4538-a75f-54a8ad346a77 |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 0831a441-438c-4111-a6be-f8f967393c5e |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | c3d451f2-dcc6-4e8d-88d2-24bb7891e583 |  | checkpoint | Airseal and Internal Flashings (photo)
checkpoint-status | 76f6b715-f0e9-495c-aeef-c234bfe838ac |  | checkpoint | Smoke Seal Complete (photo)
checkpoint-status | d47b80a1-f95b-4c73-92b8-8721f827b093 |  | checkpoint | External Flashings / Weather Seals/Drainage
checkpoint-status | b9d21b38-ff32-477c-a80a-e720ab822bf0 |  | checkpoint | Trade Clean & Sign Off
checklist-flat | 4e15ac60-ec28-49ed-8a54-3f5433964b50 |  | checklist | Seismic Suite (non curtain wall) |  |  |  |  | Yes | Seismic Suite (non curtain wall) | 5a4f9e0e-66e1-405b-8ae5-202c55b176cd
checkpoint-status | fabb5670-bb75-4ea0-9524-3662d23fb387 |  | checkpoint | Opening Prepared, Wrapped & Datums
checkpoint-status | 2d1258ce-1cff-4abc-8a63-fbba7aee2754 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 3efeb6bf-51a4-4068-b91c-dffdfdee83ec |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 9dc27528-87fb-4423-936e-4ad4b0df8d82 |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 012e8193-c73d-4827-b9a6-db4b22713924 |  | checkpoint | Airseal and Internal Flashings (Photo)
checkpoint-status | 162923ac-0fb9-436c-bfbc-b5fe250ad283 |  | checkpoint | External Flashings / Weather Seals / Drainage
checkpoint-status | d0ad6f2e-db50-4224-a0ef-9275e9de7467 |  | checkpoint | Site Glazing Completed
checkpoint-status | 704a2c29-66e6-461b-9181-1b63f684bba3 |  | checkpoint | Trade Clean
checkpoint-status | 5e958f94-cac8-49c0-b302-99bf54fc9b6e |  | checkpoint | Wights - Sign Off
checklist-flat | abefc3ef-d27f-4800-b704-17f5bb76f89f |  | checklist | Commercial/Domestic |  |  |  |  | Yes | Commercial/Domestic | 663ef09f-fbc7-4d4c-8135-f67fecf41664
checkpoint-status | 7f99a476-09b1-45d4-a7f3-1ab403fa8858 |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint-status | 650220ab-2b16-412d-a586-59817e21dc31 |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing
checkpoint-status | 85f1bea9-590b-4b7d-a052-49b18879407f |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | b1a1220f-fe54-44f9-bc3f-7cebfe0b8a2b |  | checkpoint | Airseals Completed (photo)
checkpoint-status | e3d8a3c9-864f-4a5f-9119-4be58d468595 |  | checkpoint | Site Glazing Completed
checkpoint-status | e8afa1a1-7e3c-4302-8ee3-7ad62ee61b49 |  | checkpoint | Trade Clean & Sign off
checklist-flat | a2427bf8-e738-4ad2-a08e-227f9f4e97a4 |  | checklist | Plant Room Screens |  |  |  |  | Yes | Plant Room Screens | 983c7112-428f-4910-a857-5c2441e1b012
checkpoint-status | e8ba1ce9-6d0b-414c-b34f-4f2d10587c14 |  | checkpoint | SHS Installed by Main Contractor
checkpoint-status | 66081b22-18fd-48bd-9c11-861779e623f1 |  | checkpoint | Installed/Fixed as Per Shop Drawings (Photo)
checkpoint-status | 430a1505-8d31-467b-b56f-f0f13c2ab049 |  | checkpoint | Wights - Sign Off
checklist-sectioned | 46b63876-2b0d-4345-8a5c-3ff8f7845404 |  | checklist | ST - S - Punch Window Frames |  |  |  |  | Yes | ST - S - Punch Window Frames | b54323f2-19d8-4098-9b88-268feac10e11
checkpoint-group | 1f74dc3e-6b5a-4690-adcf-6459775f1d33 |  | section | Glazing Install
checkpoint-no-status | ba743105-29f6-427e-b2b3-827463e6c1b7 |  | checkpoint | Glazing Install
label | 76600269-2c76-5ded-900c-f8c92e43caed |  | note | Window # / Elevation / Level
checkpoint-status | 0be62b4b-601f-4e21-80f4-6ec15c3d1389 |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status | 1b8bde2f-57c4-48b4-abaa-b8bf90f9d945 |  | checkpoint | Check the joinery is free from damage
checkpoint-status | e1200a44-6e19-4800-b2fb-946b12376d18 |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status | 9da6b04d-dcc2-4d4f-a0cb-33b7b0599911 |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status | ad7b237d-3bba-4406-8fb7-4dc5ef110164 |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status | 4a2b2268-102b-4aeb-87b2-e1b549e01f5f |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status | f6e8edbc-ad6d-47e4-8806-2016487b57f5 |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status | 095f92af-ef5f-46ab-88ab-b8d42bbf04da |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status | 742483ac-b116-4f23-979d-ed9cceb8aebe |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status | 3096019b-875a-4684-a161-45e5ae4891e9 |  | checkpoint | Glass Stickers removed
checkpoint-status | 4c19456d-6803-4931-ae10-2ef970ddd09e |  | checkpoint | Trade Clean
checkpoint-status | 93017edb-6c45-4eab-8432-1210af90a9fc |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status | a083aba8-31f6-4086-be02-c982c244726a |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint | 466fd562-366d-4f17-9bd0-f3386d9ffb8c |  | signoff | Raise Remedial
checklist-flat | 13ee89eb-b4ea-4c3c-bc6d-19e835b5f3e4 |  | checklist | Commercial/Domestic (Internal) |  |  |  |  | Yes | Commercial/Domestic (Internal) | bffa25f0-c767-404f-942b-98c8f1888a99
checkpoint-status | 5dfd69b2-622d-4121-9ad3-9aba178887a3 |  | checkpoint | Opening Prepared Correctly
checkpoint-status | 924661e6-ca77-40b8-a633-72a0701ddae0 |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | a7e67963-3e72-4672-b58d-4a483246a3a0 |  | checkpoint | Site Glazing Completed
checkpoint-status | 67df7aef-2fce-4bbe-a840-d8ef9b02cac7 |  | checkpoint | Trade Clean & Sign off