## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 1c3962fd-612a-4455-b7d4-2355f4b23ec9 |  | checklist | ST - S - Punch Window Frames |  |  |  |  | Yes | ST - S - Punch Window Frames | 0c481574-a46f-4236-a7c2-86899301f891
checkpoint-group | 8d999105-b7b4-43f8-88ed-1b9290f6ea31 |  | section | Glazing Install
checkpoint-no-status | 7f7a09c8-79c9-4c54-a55c-9ecd4c310215 |  | checkpoint | Glazing Install
label | 45d3284e-7779-5ae0-8f76-92eaaf7ba798 |  | note | Window # / Elevation / Level
checkpoint-status | 1b489ef6-1473-4da2-855e-0e53f866038d |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status | bcf2e019-05a4-41e0-8c55-5bb9d5fb5798 |  | checkpoint | Check the joinery is free from damage
checkpoint-status | 65430eaf-798e-44d3-b88a-d71f80540326 |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status | 67152315-8bd5-4b27-b0c5-5e1fe97003d2 |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status | d0314bfc-0f4c-4737-943a-b8a6cdd78d53 |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status | 6215ffad-aef3-462d-93c5-818d0798c251 |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status | 009b8d92-083a-45b1-b30c-d6f2e84c8dad |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status | 5f1c54f6-f7e9-4208-8164-f514eb469bef |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status | b030644e-2bed-4463-a1b0-d49d084e33bc |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status | 77618cb1-677e-4d9d-9b02-a8aee88024d1 |  | checkpoint | Glass Stickers removed
checkpoint-status | 72402f6d-bca6-459e-a410-d01b9b91c18e |  | checkpoint | Trade Clean
checkpoint-status | 92d9d3a7-a243-4baa-82bf-e87b4417600b |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status | e2474c49-b938-4456-84f8-8edbfd456229 |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint | bd343928-d15e-49e1-9740-e6986984193c |  | signoff | Raise Remedial
checklist-flat | 31f738d6-e0cc-4df8-b013-224193a45d49 |  | checklist | 100mm Flushglaze |  |  |  |  | Yes | 100mm Flushglaze | 0fb45f84-fcb5-4e86-9f82-9b180d649de3
checkpoint-status | a0299712-6019-4b14-8231-80020e216b82 |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | f06b70aa-c29b-4fb5-b7d1-da9a7040b26c |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | a6c7e6e0-24d6-49ef-8cab-49a348f2a71a |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 58257f47-5d1b-4080-93a6-0c0b31238be6 |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 7218b7cd-1584-49a5-a9c3-194e96f9db2c |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 6ebf9ce3-2dd4-42c5-80bc-dccf5fe52965 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | fbff1565-b774-4a1a-9419-bf1c7fa2778e |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | 9a515951-5705-4db6-9606-5c03a45566f0 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | 8df2b1a3-38d9-4793-bfd0-92e556798aa2 |  | checkpoint | Site Glazing Completed
checkpoint-status | 64e9a9f9-3547-46c7-99d0-aa2da41687d9 |  | checkpoint | Trade Clean
checkpoint-status | a5a1a8d1-cd3a-46a4-a2fd-11b1315a0434 |  | checkpoint | Wights - Sign Off
checklist-flat | cf939e98-479d-4d98-ac54-1247d81f5ea2 |  | checklist | Magnum Suite |  |  |  |  | Yes | Magnum Suite | 14c3818f-e8aa-443a-998b-a7faf597b6c4
checkpoint-status | 76553f27-9361-41b9-982b-722cc29e723d |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint-status | 2f275183-9371-4c0e-affe-1bcf4a3bde9e |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 4530717e-608f-4e8a-8915-739e65560b1a |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
checkpoint-status | b046461e-0528-4995-8f1c-08b6b3c5bea5 |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | 2c78dff0-1910-414c-a6b7-5420e27e9069 |  | checkpoint | Airseals Completed
checkpoint-status | 88e2382d-c568-4515-84b8-3f2f766497b8 |  | checkpoint | Trade Clean
checkpoint-status | 3331a707-b087-4f21-b12f-2aeb7b7b0a0b |  | checkpoint | Wights - Sign Off
checklist-flat | 4a82ed0d-b5ca-48c3-b244-ebd62c1d4e59 |  | checklist | 40mm Metro |  |  |  |  | Yes | 40mm Metro | 241a87d8-e825-4a3e-9610-d7c7d04d2164
checkpoint-status | 485690da-1a9b-4054-b382-12ac54b1f0ad |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint-status | 76f3c92d-182d-4cb7-9806-7e86321b1c93 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 478a7698-9902-46bb-8587-fa32387f77a8 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | d7003c40-2752-4d4a-aac6-1bc1c4dfe77b |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | af0006d3-f3b8-4a7e-9149-931a76751070 |  | checkpoint | Airseals Completed
checkpoint-status | 2c3c1c3d-8639-4aba-bb97-3079577c7571 |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint-status | dde224b5-d08e-48d9-aba5-1db729d055b2 |  | checkpoint | Trade Clean
checkpoint-status | dcd31286-abbd-44d2-acb6-8e8ed3b6e541 |  | checkpoint | Wights - Sign Off
checklist-flat | 37124504-10ea-40ff-b07f-3359be2d929f |  | checklist | 100mm Shopfront |  |  |  |  | Yes | 100mm Shopfront | 284f9789-f8c0-46af-a4a9-3a4162d20cc4
checkpoint-status | 4b47c64a-b9c7-4ff1-a1bd-09e10994f05e |  | checkpoint | Opening Prepared By Main contractor
checkpoint-status | b32d2e1f-d49a-427a-823a-9a1b8f15feaf |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | dc137093-9b86-41c1-a8e4-2c35abfcfd31 |  | checkpoint | Installed / Fixed as per Shop Drawings
checkpoint-status | 17f8e7f8-8049-41d3-adef-04a62a6f1d3b |  | checkpoint | Panel installed and working . Locking correctly
checkpoint-status | 3a9e89b5-c1ea-4782-9257-b561e80e35af |  | checkpoint | Airseals Completed
checkpoint-status | 4e505b60-5416-4c8b-9781-078bf5eae88c |  | checkpoint | Site Glazing Completed
checkpoint-status | 1f65bb44-b968-4786-924c-2ebb0a2787c7 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | 0b236eb3-126f-41bf-9956-e7052c31f0b9 |  | checkpoint | Trade Clean
checkpoint-status | 6ecc1479-5d0b-4cec-9986-5848eee8385c |  | checkpoint | Wights - Sign Off
checklist-flat | 03e7869b-9bab-496e-a3fb-5c73c237eddb |  | checklist | Thermal Heart Suite |  |  |  |  | Yes | Thermal Heart Suite | 33f33de4-ca7e-451c-94d7-a8c831a478b0
checkpoint-status | 623725a6-214b-4784-b799-913e2ebb33c9 |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint-status | dbf28996-b62a-40aa-b8f6-d17712bdb978 |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
checkpoint-status | fc71c907-aacc-4bd1-aa35-c8cbf092536a |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | df2b7277-5eac-4e61-84bb-5b3981309804 |  | checkpoint | Airseals Completed
checkpoint-status | e2069ca0-a5a1-454b-8f82-ca7a492882de |  | checkpoint | Site Glazing Completed
checkpoint-status | 6d17e5bd-4023-4858-832d-7e56b1634ae9 |  | checkpoint | Trade Clean
checkpoint-status | d8fc1fb3-f852-444c-834c-4b1dd9820b76 |  | checkpoint | Wights - Sign Off
checklist-flat | 4d772135-188e-4e02-9781-0baabf3ee082 |  | checklist | Commercial/Domestic |  |  |  |  | Yes | Commercial/Domestic | 3de88fb6-2dcd-4ced-b8b7-42e01f4a2f31
checkpoint-status | e1ef2e58-12e6-4cf4-a913-2d44b08a7320 |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint-status | 91650241-c624-4a9e-8953-d1f0ea3ae0d0 |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing
checkpoint-status | 6b9e290c-0698-488b-805f-3e8c06f92ed3 |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | d5d196fc-6aab-4950-b13c-27a9fcda34b3 |  | checkpoint | Airseals Completed (photo)
checkpoint-status | 5249ca81-16cb-4f8a-8f66-257308c0ce99 |  | checkpoint | Site Glazing Completed
checkpoint-status | 0dc93ebe-de71-4312-80e0-c7042d698d1c |  | checkpoint | Trade Clean & Sign off
checklist-flat | 67347c4f-454b-4ca0-b8dd-c60deb5f4928 |  | checklist | 150mm Flushglaze - With Window Controls |  |  |  |  | Yes | 150mm Flushglaze - With Window Controls | 5c24a98a-ca8f-4a33-a95a-8f0e58f67777
checkpoint-status | f05e1a34-9838-44f3-93d2-65a18361c9fe |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | f9c76458-1fb9-4d00-a2e0-5011fc4b9ca3 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 7b843f27-fe5f-44af-b66f-004f2c795a71 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 6a428dc5-a0e9-4a68-9a00-799003b8125d |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 002b7343-04d0-4dff-9e0a-a34d3bdae19a |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | d1ff40b1-f168-4571-8ef7-722bba3e75df |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | cc7d1958-add6-4d32-bc35-f68594808b63 |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | af77befe-15bf-4c8c-97ee-596ad52dbd24 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | 284f49f7-c5cd-46fc-8b60-f2b238d11886 |  | checkpoint | Autodoor Unit Installed - Window Control Systems
checkpoint-status | 3460a941-fa79-4e84-925d-abeb9da8d809 |  | checkpoint | Autodoor Unit Commisioned - Window Control Systems
checkpoint-status | 6ae3f5ac-461b-48f4-950d-9622d82a2cff |  | checkpoint | Site Glazing Completed
checkpoint-status | 065fe241-5269-4d5c-abaa-3f26df44b551 |  | checkpoint | Trade Clean
checkpoint-status | 09727541-094a-4eb0-ab96-c40f7e5049ee |  | checkpoint | Wights - Sign Off
checklist-flat | a9f4a303-23a3-4087-9f8d-e95ebde435da |  | checklist | Architectural |  |  |  |  | Yes | Architectural | 69e09ba1-e985-448c-95ad-364e7bf7fe48
checkpoint-status | 43e6ff93-8639-4273-9e51-305061768f27 |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint-status | 27aee0ba-df9c-41f4-8646-480ac3e559e7 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | b7c87995-bba2-4639-82f1-54b489133118 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | de7256c4-64ef-41e4-9742-9556430d54ce |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | 94999e39-8ec1-4396-bc8c-6b027024b0c0 |  | checkpoint | Airseals Completed
checkpoint-status | ad8c6b96-7da2-47e4-bd81-3c390a4ecbd3 |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint-status | 665f67ca-f6c0-401d-8196-68f53d22bcea |  | checkpoint | Trade Clean
checkpoint-status | 31a45fa2-0bf3-4def-8c24-d97b7b3b53a7 |  | checkpoint | Wights - Sign Off
checklist-flat | c2048031-88cb-4113-8ff7-ecd1594c8c78 |  | checklist | Seismic Suite (non curtain wall) |  |  |  |  | Yes | Seismic Suite (non curtain wall) | 81f5c67e-e40a-4878-aa2b-442da0463254
checkpoint-status | 94c221fc-9698-431f-aeda-00919d990fc4 |  | checkpoint | Opening Prepared, Wrapped & Datums
checkpoint-status | 463047b2-d38e-4fa3-8759-dfb6036b0f02 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 84943713-0ab9-4c32-ab26-f4c66ece3cfe |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | dc7f15f7-05de-4639-b9ea-db347dd2542f |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 85e82671-ba7d-48df-aae9-1e98050efd1b |  | checkpoint | Airseal and Internal Flashings (Photo)
checkpoint-status | a7ffe02d-1632-4d48-8cfe-38b5ddc4e31f |  | checkpoint | External Flashings / Weather Seals / Drainage
checkpoint-status | 57315ed7-5a9e-432d-ab45-b6b4b602af2c |  | checkpoint | Site Glazing Completed
checkpoint-status | f5e70ff8-fd1a-4c05-9e82-77064b57fe49 |  | checkpoint | Trade Clean
checkpoint-status | f41b5d2a-5197-4879-a728-01493934eb36 |  | checkpoint | Wights - Sign Off
checklist-flat | 7bf2620e-4ded-4875-ba84-bd24578adc7f |  | checklist | 125mm Flushglaze - With Window Controls |  |  |  |  | Yes | 125mm Flushglaze - With Window Controls | 8c312cf5-32fc-439a-a0c3-d273da5b9e39
checkpoint-status | 27214e97-1dc2-40f4-a47c-5ac5d4745c99 |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | 722294d6-53f3-41f0-8224-6897de0247b0 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 359bddc3-ad89-4348-aacc-ccd9218d1c71 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 1a26d497-7ee4-4a5b-b91f-74293aea1a27 |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 002cd54f-f0ba-4ad5-bf4b-76a659dc8bfe |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | a291bed8-1883-4d2a-8eb6-2da9951034e3 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 5309c58c-4515-4260-aa31-3801ad59905f |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | 4179f415-6c18-4a86-98ef-00e25d036253 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | d1020779-725e-45dc-9807-cb38456e3726 |  | checkpoint | Autodoor Unit Installed - Window Control Systems
checkpoint-status | 7095fe12-bec1-46a9-a11f-8f7b139e3e41 |  | checkpoint | Autodoor Unit Commisioned - Window Control Systems
checkpoint-status | e8e9c4f3-1caa-4d92-8083-447a058548f3 |  | checkpoint | Site Glazing Completed
checkpoint-status | d61cfa26-7f17-49ae-b4d4-678d248896df |  | checkpoint | Trade Clean
checkpoint-status | 230f1153-6c0c-4b7e-88d6-f7b9a48b8955 |  | checkpoint | Wights - Sign Off
checklist-flat | e3463a16-65a7-4b31-b7bc-65e84c1aeaef |  | checklist | Seismic Suite (Curtain Wall) |  |  |  |  | Yes | Seismic Suite (Curtain Wall) | a8b75d18-f054-417a-a72c-4ab6b0729a2f
checkpoint-status | b92b95e8-43b7-4258-b429-a2f072de779f |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | ac76ebbd-7c33-459c-871d-6aef7832f9d9 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | d805a178-48bd-4752-9265-051438c269fb |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | cc87a166-f34d-4111-acbf-c6b8efdd6073 |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | c353310e-8b03-444a-bcad-9034afe84450 |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | d741bd2c-253a-4168-9cf3-d51b99df8efc |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | ee184d92-e16e-47ca-9a63-93ce326ed999 |  | checkpoint | Airseal and Internal Flashings (photo)
checkpoint-status | 9b93c2e2-d885-445a-a4d0-473c4049424e |  | checkpoint | Smoke Seal Complete (photo)
checkpoint-status | 9b587556-49d9-4e11-bcd2-bbfd8b9496f7 |  | checkpoint | External Flashings / Weather Seals/Drainage
checkpoint-status | 3a1e094b-e586-4b09-8644-c22617791db3 |  | checkpoint | Trade Clean & Sign Off
checklist-flat | dcb4981f-be21-4d91-8ef1-9ea4c2fcfd25 |  | checklist | 168mm Structural glazed |  |  |  |  | Yes | 168mm Structural glazed | ac47931e-553b-4e59-83ba-f6f227343e01
checkpoint-status | 0914ef5a-b55d-4e0e-9f87-8011357d21bc |  | checkpoint | Opening Prepared By Main contractor
checkpoint-status | de153037-aaec-45f7-a122-bdc2a7528091 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 96cf2586-2888-4658-9dc9-a97c28f1c516 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | ce4551b0-11a5-4dfe-a488-219c27c2cb0b |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 19528459-8267-4439-8dd1-339b6812b2c5 |  | checkpoint | C.W Visual Panel Insert Check
checkpoint-status | 20973226-e558-424b-ab69-6a1aea888a14 |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 1a8f288f-1a63-4ca9-8f86-50bfebd0b63f |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 3ec3000b-623a-4cb6-924f-42f2e3c40c90 |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | 5774db7f-2ae8-4761-8b0f-af5c156a2d54 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | 13a3930f-7110-482d-9c1c-e429e8add84b |  | checkpoint | Site Glazing Completed
checkpoint-status | bdf293b7-3989-48f5-9387-3ee34169daa3 |  | checkpoint | Trade Clean
checkpoint-status | a68baad1-f7b1-4b8a-8774-54d5b82e95a6 |  | checkpoint | Wights - Sign Off
checklist-flat | 678b5167-313a-47fd-a997-c9319bb07d91 |  | checklist | Residential Suite |  |  |  |  | Yes | Residential Suite | d98bd32e-2c12-4129-b6e2-7809abc15283
checkpoint-status | 10027eb7-a80d-40ed-8add-98d944db7ad4 |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint-status | c5e095f3-90a7-4f5d-a634-b3c74a0f4617 |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
checkpoint-status | 07783eed-3a0a-44d9-950a-dac013b7ac64 |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | 75d9a173-a3b0-421c-9de0-710badd0953e |  | checkpoint | Airseals Completed
checkpoint-status | c1eeea69-efd6-4456-8e80-172bdf6aba05 |  | checkpoint | Site Glazing Completed
checkpoint-status | 1671b721-d22f-4f63-a888-83700d2e568d |  | checkpoint | Trade Clean
checkpoint-status | b0061179-df6a-4e60-8843-5428ac590569 |  | checkpoint | Wights - Sign Off
checklist-flat | 2b057858-122f-427c-8eb5-9937f0d89f98 |  | checklist | 125mm Flushglaze |  |  |  |  | Yes | 125mm Flushglaze | dc01e8aa-6b7f-43f1-be69-fa6e058bce57
checkpoint-status | 1c5e7b0e-9be3-4e5e-8fb3-771e82c44390 |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | 386442b7-547d-4abc-9db7-d26efc66df60 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 875aaa4f-345d-4e9d-8f7a-919536479447 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 1aa995eb-1539-4b4f-b315-70d5776cfdcf |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 9021650c-5618-4b4f-89b9-78ce35450d57 |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 82b08068-c257-4cbb-a5dc-dd2d07e62b65 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 0d9378d8-b275-460f-9c8c-8603dc520477 |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | de1b5eec-e40d-46ce-b488-e592e3b76e26 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | 3b238d25-6237-45a9-924f-7f8d3b0640d7 |  | checkpoint | Autodoor Unit Installed - Dormakaba
checkpoint-status | 3c741637-b126-4e88-a5e9-59292890917c |  | checkpoint | Autodoor Unit Commisioned - Dormakaba
checkpoint-status | b1d462a2-844f-40cf-b31c-56a0aa108b94 |  | checkpoint | Site Glazing Completed
checkpoint-status | 244b1626-38e5-48d8-be32-cd59070cc2e0 |  | checkpoint | Trade Clean
checkpoint-status | 9a3e792c-37de-44a7-820a-27ad109101e9 |  | checkpoint | Wights - Sign Off
checklist-flat | d13ad491-8bff-4c6d-9a9a-03f908843ada |  | checklist | Skylite |  |  |  |  | Yes | Skylite | e736e3cf-2b0b-4bc1-9353-751fbe21df07
checkpoint-status | 1e21e547-18f7-4cab-b345-1e51c531aa8f |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint-status | 554892e7-a92e-45c7-af49-b19a95575851 |  | checkpoint | Roof frame Installed / Fixed As Per Shop Drawings
checkpoint-status | b2379d0f-36d3-423a-ae78-212b4363ee06 |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | b2f6bcf7-d2ef-49d2-9765-55540655fcc9 |  | checkpoint | External Flashings / Weather Sealas ( Provide photo reference)
checkpoint-status | 4dcbf9ce-5003-40f1-baa9-81d390e06225 |  | checkpoint | Site Glazing Completed
checkpoint-status | de570d16-200b-4368-9b82-24869ccc0587 |  | checkpoint | Trade Clean
checkpoint-status | fc02bdc0-c182-46a8-8d9f-0045edce2b52 |  | checkpoint | Wights - Sign Off
checklist-flat | 4e8a7586-bc3b-4317-863a-77cd2c693d7f |  | checklist | 150mm Flushglaze - With Auto Doors |  |  |  |  | Yes | 150mm Flushglaze - With Auto Doors | ebb36220-55ff-495e-b1e4-d9b3bd21e758
checkpoint-status | 6f5eb1ef-3841-45d3-858f-0e07342e2a26 |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | 3de06959-9232-455f-bb0c-9911a01b1992 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 363cd0e8-cb3b-4ed3-aea8-f3b655a156fe |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 9f70ce0a-7190-4646-a89b-76e941cedd8f |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 5ceb4da0-4381-427a-9d30-9af18c4432e7 |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 65bdee99-02d6-47af-89cf-9b70aef244af |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 5effb036-715a-4036-b671-26e321f22bda |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | 5d9fbe31-5fac-43c8-bd1b-f008c5a3fa22 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | 9a4835db-a77b-4588-81c9-40df1d411294 |  | checkpoint | Autodoor Unit Installed - Dormakaba
checkpoint-status | 05c5c190-2c00-4e27-aa56-79c0835dabe3 |  | checkpoint | Autodoor Unit Commisioned - Dormakaba
checkpoint-status | 4e673cd1-45dd-4c55-b527-722a80802f3e |  | checkpoint | Site Glazing Completed
checkpoint-status | bcea248a-b81a-4373-bfe4-7f19c7d7e8b0 |  | checkpoint | Trade Clean
checkpoint-status | 5af89148-1569-4e34-97f8-9f7bffa1747d |  | checkpoint | Wights - Sign Off
checklist-flat | bce1e185-9ec8-40aa-b81d-03c2db7daa0c |  | checklist | 40mm Seismic |  |  |  |  | Yes | 40mm Seismic | ef251c30-9a91-4e14-9849-0f8595addcef
checkpoint-status | 6d1077f8-4e70-46cf-b026-2241483eba42 |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | 2814870e-7bad-4487-8206-f54bfdeccc30 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 1fc79696-c9b3-4df2-9d7f-852a7e49a43d |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | fd7abbba-d0f7-41c8-afa6-3eb769eb541c |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 24fb2edb-3bcf-46e6-bc8f-59b846c078ac |  | checkpoint | C.W Visual Panel Insert Check
checkpoint-status | 62d60718-defe-4bb0-9140-473667786143 |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | bacb4dd2-570b-4d6e-9fde-1a552318a6d4 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 4acfb299-e127-4ba6-8251-c703d95b5c14 |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | cd511c76-eb62-423b-91de-9624b185c017 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | 48ff0abb-e034-493e-b66e-9d4b26a39632 |  | checkpoint | Site Glazing Completed
checkpoint-status | 5d7d3b7b-4829-44ca-a58e-b63be3c8d8c8 |  | checkpoint | Trade Clean
checkpoint-status | 1a6a09bc-abc7-446b-87a7-4d8972de634f |  | checkpoint | Wights - Sign Off
checklist-flat | f9a2a3f5-33d4-4820-9bb9-93ce035b7f87 |  | checklist | 150mm Flushglaze |  |  |  |  | Yes | 150mm Flushglaze | f5f70fa4-9f50-4deb-aa99-4adff84a92f5
checkpoint-status | fee819f4-557b-4e5d-8ec1-b49ca072a72b |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | 548c13f7-c0ef-4add-b56f-7d9c9811f6e5 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | b214e522-5d94-4e70-8474-14e4c31c96d6 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | dbe06d4b-0537-4846-966d-49c107682295 |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | c30b63ed-d7d5-4c83-8b5f-3de9b1d20c61 |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 45774898-f826-4105-9426-3fbd7d6f4fd6 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | c4d1cd83-d768-4564-9ed3-34dfb9200a27 |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | 92f1643a-6a54-47ff-aa68-c4382c7493e7 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | d82d85b7-901b-4907-863f-405682fc3d2c |  | checkpoint | Site Glazing Completed
checkpoint-status | eddb092d-a865-415c-bbd7-dc3ec3946bb9 |  | checkpoint | Trade Clean
checkpoint-status | 469dbdc0-d4ce-423b-af4c-f324713eb168 |  | checkpoint | Wights - Sign Off
checklist-flat | 4d1a5c85-1972-414b-a64d-7b3a26bf0178 |  | checklist | 125mm Flushglaze - With Auto Doors |  |  |  |  | Yes | 125mm Flushglaze - With Auto Doors | fa7105a5-328d-47b9-a357-4e48ec4004b7
checkpoint-status | bb4f662b-761e-4af9-a4d0-dffc5c466cdc |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | 272f7efb-9db7-4efb-bf82-057e160bf782 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 50e5dd49-9d68-46d2-99ed-ddf54424e904 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 6c9d5386-cfdf-43e1-ae89-bc53bb03d8e6 |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 0c41c451-daa5-487d-9720-f8e12604bd3b |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | b5ac2ee3-75dd-4822-a86c-04723de8675e |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 36448605-4cb2-4cdc-a3ca-8d1fa0a38a79 |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | a3688d2c-e522-4bfa-a408-0b9bd76d091c |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | ce65df93-ce47-4561-83c5-34e711ea9c6c |  | checkpoint | Autodoor Unit Installed - Dormakaba
checkpoint-status | f58a056a-e6d1-40a4-b5f3-6fb850cca4ea |  | checkpoint | Autodoor Unit Commisioned - Dormakaba
checkpoint-status | 127caeb6-4a12-4469-9e7d-85e6e5dfc59f |  | checkpoint | Site Glazing Completed
checkpoint-status | abfe807c-f205-44c9-af4a-9c4e16f51588 |  | checkpoint | Trade Clean
checkpoint-status | cc80b376-2681-490b-bf4d-a884f02a5ca9 |  | checkpoint | Wights - Sign Off