## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | e6d13676-d606-48bb-8fcd-12d828b07bf3 |  | checklist | Seismic Suite (non curtain wall) |  |  |  |  | Yes | Seismic Suite (non curtain wall) | 889bdcde-1667-4edf-9b68-b96bc379f975
checkpoint-status | 2bfc363e-24e9-447d-b48d-5665d24b7006 |  | checkpoint | Opening Prepared, Wrapped & Datums
checkpoint-status | c5e133ae-7b7d-4d2d-80eb-b5ca68fb90ba |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | d274cc1a-06d3-4950-9f1a-73d8601a7248 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 6e4a8ccb-ad1d-4fa5-86fd-20dcd58bf44f |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 93a0a9ad-a3ab-4370-94c8-6f750c8f5633 |  | checkpoint | Airseal and Internal Flashings (Photo)
checkpoint-status | 70ca071f-84af-4526-930a-017bcff40576 |  | checkpoint | External Flashings / Weather Seals / Drainage
checkpoint-status | 0f5017c7-de62-4302-b508-7cb3181ef8c9 |  | checkpoint | Site Glazing Completed
checkpoint-status | 2b7ddfc5-8bf4-4c9b-b321-4ad27e59e552 |  | checkpoint | Trade Clean
checkpoint-status | 27562cd9-362a-4119-ac8c-a4c71bf26ee9 |  | checkpoint | Wights - Sign Off
checklist-sectioned | 2fe1ad27-3eed-4e0c-b804-2c5c42ad8d6c |  | checklist | ST - S - Punch Window Frames |  |  |  |  | Yes | ST - S - Punch Window Frames | a1022b37-47b3-43e6-b7ac-f9b4397abb72
checkpoint-group | 8b8a7b02-0240-4ce8-bcc9-595c25cc5080 |  | section | Glazing Install
checkpoint-no-status | c244c451-a301-4f44-abea-f305243f7fe4 |  | checkpoint | Glazing Install
label | 70d846f4-02c1-59bb-9404-e65961e38e52 |  | note | Window # / Elevation / Level
checkpoint-status | 29f6b198-62d6-433b-81eb-3f38a61f271c |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status | 46452317-4098-4c28-b850-9c39ca7fc1ab |  | checkpoint | Check the joinery is free from damage
checkpoint-status | 9e64a5f6-5b90-4c67-9a62-c6042e7d18b7 |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status | daab08a9-d1d4-4ff1-905c-86d6e4115ed8 |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status | 28fa41cd-4e60-49ea-a97f-8314f21f48c7 |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status | 6603fabf-97bf-4352-a52c-8d091e08c6cc |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status | 1513bb63-6442-48f5-9622-43c30f75fa0a |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status | 204ac132-981c-4e26-a372-bf8e323ae8ad |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status | 90c46f19-70dd-46e8-93a2-c75930bc10c5 |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status | eba07a18-a3f6-4df2-92f8-06de9aca82f7 |  | checkpoint | Glass Stickers removed
checkpoint-status | 52e8b448-c368-4359-b314-248b015ca55e |  | checkpoint | Trade Clean
checkpoint-status | 325308d5-f187-47a0-b1d3-b66fb3e3f51b |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status | fa0fb109-639b-444f-8831-5a9220d6374c |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint | b8eaf50a-3e9f-4b56-a93d-3097859ed72d |  | signoff | Raise Remedial
checklist-flat | 6f501b73-6449-4a21-b97b-f8f7689adcfe |  | checklist | Commercial/Domestic |  |  |  |  | Yes | Commercial/Domestic | e7ea981f-c50f-4388-8dea-53cd7a05d4c3
checkpoint-status | a350ba1f-39d8-4c8d-a7de-87ea88163e92 |  | checkpoint | Opening Wrapped & Prepared Correctly
checkpoint-status | 7f70f8fd-e036-47c8-842a-010c4ec01d25 |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing
checkpoint-status | 02fb8453-b252-4b0c-91ac-d9d6cfe0306c |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | e385f53f-23ff-40f9-a6da-1fe9d1da8097 |  | checkpoint | Airseals Completed (photo)
checkpoint-status | 9990e5ec-03a9-4e63-aeff-cf33e34e0ad2 |  | checkpoint | Site Glazing Completed
checkpoint-status | 5c34f20e-4eb0-41b1-b935-54a62a13d64c |  | checkpoint | Trade Clean & Sign off
checklist-flat | bb2ca34c-af04-418e-aee0-6202888a557f |  | checklist | Seismic Suite (Curtain Wall) |  |  |  |  | Yes | Seismic Suite (Curtain Wall) | f610d3a2-0b0b-4e67-bdb3-92c24459bc14
checkpoint-status | e694c097-ab36-4bc6-bd8b-2f60ead54304 |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | 0dfe2d42-db48-4b86-adec-b64c18100224 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | df50aad1-1766-4e4a-b52e-816922f68505 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 4c6574d5-ee8c-4780-a57c-bfd8a09172e7 |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 7b8a9a54-6577-4088-b4ca-3ee076f331ba |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | d034b0d6-2d82-421e-bb66-cb0f8c1ef264 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 0194f946-7e89-4b24-b17f-43abcb8d6ea5 |  | checkpoint | Airseal and Internal Flashings (photo)
checkpoint-status | 872aa724-5be3-4366-b1b7-4f2c85df3aa8 |  | checkpoint | Smoke Seal Complete (photo)
checkpoint-status | ec8b6775-2daa-4879-bbfd-4bd7697a6183 |  | checkpoint | External Flashings / Weather Seals/Drainage
checkpoint-status | 48b41ad2-8e63-4dec-bea9-6b40da58454e |  | checkpoint | Trade Clean & Sign Off