## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | b95ddd36-ae4b-4449-ab79-f638f8ba9651 |  | checklist | ST - S - Punch Window Frames |  |  |  |  | Yes | ST - S - Punch Window Frames | 6847c5c4-9092-4515-8617-f48fb3e947de
checkpoint-group | 229eb62f-5cf1-4386-bb9c-902ff689ae26 |  | section | Glazing Install
checkpoint-no-status | fa89e3b0-e073-4c79-afb1-50114fefc291 |  | checkpoint | Glazing Install
label | 11178c11-8393-5d40-ba2e-da7743f13616 |  | note | Window # / Elevation / Level
checkpoint-status | e4e4e64b-793d-4eb8-8623-6a96af40f873 |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status | 371adb1d-fe40-472b-9542-7b3aa8241728 |  | checkpoint | Check the joinery is free from damage
checkpoint-status | 39f8ec25-6ee0-4d21-8156-d9e760892271 |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status | 5d0ae8f1-2ba0-4a66-9624-4e32d45f1296 |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status | f5a9bf92-526e-4649-ac5d-7d6387941466 |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status | a0deed65-f770-4eb7-bace-ad357c458e9a |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status | 09b80f34-2d10-4178-91a8-f77e97377b1a |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status | c051f727-8d2b-4733-bcf3-4faa965d869c |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status | d4f33ca3-a604-45ee-b2bb-fe36ac9623e1 |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status | ad710587-efad-47f4-a02f-38749f2b89e2 |  | checkpoint | Glass Stickers removed
checkpoint-status | 4c71a336-770c-467a-af5c-bab2b547e9fc |  | checkpoint | Trade Clean
checkpoint-status | 3de174b6-e405-43e3-b39f-ff0c4ef319e1 |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status | 1396d726-418e-4097-bac1-ae5c8353a5f1 |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint | 955aed02-4011-44b9-a9f2-99c188c57843 |  | signoff | Raise Remedial
checklist-flat | f2a6c258-c167-49f2-935a-4ea5c34e08d3 |  | checklist | Commercial/Domestic |  |  |  |  | Yes | Commercial/Domestic | 8cad8b44-6d8f-4ec2-82b2-68e37294287d
checkpoint-status | d5fd31a4-7d96-4156-b1ec-4d48916fb967 |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint-status | d2bc2f1f-34d9-4fbd-b90c-2dd126e275f0 |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing
checkpoint-status | afd3c5da-1785-4271-90a4-20ef4b66d5d8 |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | a53e2fae-a4d0-4575-b587-0356b364a8d9 |  | checkpoint | Airseals Completed (photo)
checkpoint-status | d2c8f4e8-4fe7-44eb-a9be-f54c9b9a1315 |  | checkpoint | Site Glazing Completed
checkpoint-status | f9e5b615-dc16-4951-8fcd-60a8e6af48fd |  | checkpoint | Trade Clean & Sign off
checklist-flat | 98c28fc0-a350-4988-b2ab-680d8fe3a61e |  | checklist | Seismic Suite (Curtain Wall) |  |  |  |  | Yes | Seismic Suite (Curtain Wall) | a244b6db-d361-4985-913d-8ddbf3f4a9ec
checkpoint-status | 7051d0dc-41a9-4ba3-bfb8-70a62160142c |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | c3611a8e-a133-44c4-8fdf-7b670de1c07c |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 892d2064-cbf5-4834-8c9c-708c78cbcb66 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | b13373fe-6817-4844-a0ef-054e64df16bc |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | adf2d38a-01ae-44f7-86a7-21fd00ba800c |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 7aff6e2e-0d96-4f99-a9f1-8a32d2472bc4 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | e1a1b37a-d767-4dc1-a408-b4b789ca0f75 |  | checkpoint | Airseal and Internal Flashings (photo)
checkpoint-status | 400846b1-2723-4442-af7d-93a330c14595 |  | checkpoint | Smoke Seal Complete (photo)
checkpoint-status | d90bbc69-4d2a-4e8e-9ba3-6d04de581b38 |  | checkpoint | External Flashings / Weather Seals/Drainage
checkpoint-status | d046eae2-845e-4d98-bea4-ba1bb2978455 |  | checkpoint | Trade Clean & Sign Off
checklist-flat | 73431b40-124f-47b0-b414-50f00f58ef45 |  | checklist | Seismic Suite (non curtain wall) |  |  |  |  | Yes | Seismic Suite (non curtain wall) | f9598a34-0ad0-4d2b-aa91-6fab59e52cb1
checkpoint-status | 5daf3176-3b5a-41c2-a79a-6fb661c91389 |  | checkpoint | Opening Prepared, Wrapped & Datums
checkpoint-status | 7be0e6c1-adc1-4a63-ba71-02d976719224 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 1056e2ea-5db0-4d4b-943f-442f8f7752ec |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 90cf925b-8548-435f-aef0-b067e6ffc66c |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | ca84f568-31c8-4449-ad97-956893d64e21 |  | checkpoint | Airseal and Internal Flashings (Photo)
checkpoint-status | 53b704e7-f90e-44dc-9d5f-60d5e143eb78 |  | checkpoint | External Flashings / Weather Seals / Drainage
checkpoint-status | 5535baf7-0a5a-4f35-9ced-d4885e87df2b |  | checkpoint | Site Glazing Completed
checkpoint-status | 0a081146-d065-46eb-8093-fb5a129ad4ea |  | checkpoint | Trade Clean
checkpoint-status | 517d94bb-cca5-475e-a0b8-3529b0dcb989 |  | checkpoint | Wights - Sign Off