## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 15b2c1d5-8488-4bec-8487-f2909ed76b0f |  | checklist | CW |  |  |  |  | Yes | St Pauls | 0351bca0-9628-4867-b9a9-7e46d47e3a6a
checkpoint-group | 072b4f63-2c66-46bf-94df-85112b14a1ae |  | section | External Checks
checkpoint-status | a0e302c0-12f9-4803-a9e7-c9b0f7012da7 |  | checkpoint | SETOUT / GRIDS / DATUM LINES
checkpoint-status | b0cc9745-05df-469c-8c8c-a8bf7d59a338 |  | checkpoint | MARKOUT AND DRILL HOLES: MIN BOLT EMBEDMENT 170mm (CHECK EDGE DISTANCE)
label | a902001f-1391-4103-ab09-2eba1a5925ae |  | note | Photo Required
checkpoint-status | 476dc3b7-f26e-4cbd-a8f3-0bc5d7a7aafd |  | checkpoint | FIT M20 GALVANSED GR.8.8 BOLTS - CLEAN OUT HOLES AND SEAL AROUND STUD - HIT-HY 200-R INJECTABLE EPOXY
checkpoint-status | ddbf2856-636f-4180-927f-e98267c4d25f |  | checkpoint | PLATE BRACKETS FITTED AND BOLTED TO CORRECT TORQUE SETTING
label | b9158003-9774-40eb-9db5-e2b28e04dc50 |  | note | Photo Required
checkpoint-status | e52c730f-00cf-4bd2-a9de-f0f535de0cef |  | checkpoint | BUILDING WRAPS / MEMBRANES CORRECT
checkpoint-status | 83a0bda4-8a1d-454e-83e8-3df7873ab3c5 |  | checkpoint | SUBSILL INSTALLED - IF REQUIRED
checkpoint-status | 155e9c62-cdc6-4004-866b-7baf17a27fa7 |  | checkpoint | SEISMIC FITTED - IF REQUIRED
checkpoint-status | 0869bd19-ddc7-4a02-b67b-979dec0dc042 |  | checkpoint | PANEL FITTED & LOCKED OFF
label | 8c3bdc3a-ca93-4f67-9200-0f1f39ccb79e |  | note | Photo Required
checkpoint-status | 59c53301-f5e4-4958-8c94-ad05d567e6b7 |  | checkpoint | SPLICES & SOAKERS SEALED
label | 3f7b543b-635c-4ff3-b9e0-1976ff8fb450 |  | note | Photo Required
checkpoint-status | 8e67a16a-79ca-40db-842a-83bd4ea85c78 |  | checkpoint | SPANDREL BACKPAN FITTING & AIR SEAL
checkpoint-status | 4edc92f8-40ed-4049-9e40-6bf948cb9854 |  | checkpoint | GLAZE IN INFILL PANELS (METRO)
label | ddd31a21-4b98-475b-83a7-660ef3bb2e77 |  | note | Photo Required
checkpoint-status | 04be1d10-a2d6-458a-a705-55fe86c33dd4 |  | checkpoint | GLAZE IN GLASS PANELS (METRO)
checkpoint-status | fd6362b7-ae64-494b-a3ca-c8e3a92494e7 |  | checkpoint | C.W PANEL COMPLETED
checkpoint-status | 5797fb79-5954-4d3c-bca7-5d8e240e81b5 |  | checkpoint | EXTERNAL FLASHINGS / WEATHER SEALS / SOAKERED JOINTS
label | ec37df9f-b71d-469d-a2ba-bc4591ca86fe |  | note | Photo Required
checkpoint-status | 4530663c-173b-4ee4-9117-ce91c8e413fd |  | checkpoint | PARAPET UNDER FLASHING FITTED / SEALED
checkpoint-status | 1972442a-e9a8-455f-b0dd-9ae9a1657ba3 |  | checkpoint | INSTALL PARAPET CAP FLASHING
checkpoint-status | cc67e7da-5f3b-4a0c-8ec8-3e826436e930 |  | checkpoint | FIT PARAPET JOINT SOAKERS / SEALS
checkpoint-group | bd044bd1-976b-4afe-b7e6-937e453ffb3c |  | section | Internal Checks
checkpoint-status | 0d4f5af0-ccea-49f5-bda6-58867fa65875 |  | checkpoint | PGI SUPPORT CLIPS FITTED
label | e768f6e9-c62d-4c8b-968d-994304e87d09 |  | note | Photo Required
checkpoint-status | 7002bd1f-410f-46cc-825c-ac50ee6697e1 |  | checkpoint | PGI FIRE INSULATION INSTALLED
label | 83b67728-3fba-499a-a64a-d0f2ce4224d6 |  | note | Photo Required
checkpoint-status | 1851fd5e-b478-40bd-b2ab-00eaf137e1b6 |  | checkpoint | SMOKE SEAL TRIMS AND CLOSERS INSTALLED
label | 557ba676-572b-4999-8cb9-370c106e38b5 |  | note | Photo Required
checkpoint-status | 2e1f7100-943a-491a-b0aa-3c7a549e1c1f |  | checkpoint | TRADE CLEAN
checklist-flat | ea25f958-571d-45f7-8b11-bb87b093e762 |  | checklist | Auto Door QA |  |  |  |  | Yes | Auto Door QA Checklist | 08310cb3-49e0-4957-8064-61d3f24b4d90
checkpoint-status | bd659d03-7146-44aa-adbb-8547da37dcaa |  | checkpoint | Opening Prepared By Builders
checkpoint-status | 7ae57ed6-5551-442d-af15-39fcdf0b2202 |  | checkpoint | Window Insert / Door Installed As Per Shop Drawings
checkpoint-status | 1a2f4e1a-1d07-4bdc-8651-e16c9066ed3b |  | checkpoint | Autodoor Unit Installed - Dormakaba
checkpoint-status | 64b3091e-6173-4704-a3cd-1a07434713fe |  | checkpoint | MetroGlass Site Glazing - Photo Required
checkpoint-status | 6e1fd9a8-e39b-4aa9-b842-e7e64e1599ba |  | checkpoint | Trade Clean
checkpoint-status | 051c4a16-b800-492d-9796-aa528902c4fc |  | checkpoint | Autodoor Unit Commisioned - Dormakaba
checkpoint-status | fc559971-1f7e-4d2b-85e0-4feb2bf26b50 |  | checkpoint | Wight Sign Off
checkpoint-status | bf93924f-854f-4ab3-9ea9-87df37d3b03c |  | checkpoint | Arrow Sign Off
checklist-flat | 9833e48b-5254-45f5-829d-2c92393ae3bd |  | checklist | Installation of Curtain Wall Internal |  |  |  |  | Yes | Add Installation of Curtain Wall - Internal Works | 10fa6d55-7821-465d-957f-fcc52583445a
checkpoint-status | 04d82c99-9455-45f3-a916-10246a089ab5 |  | checkpoint | Airseal & Internal Flashings
checkpoint-status | a45c9b84-66f1-4e04-8ff7-f545d5bf6e1a |  | checkpoint | PGI Fire Insulation Installed
checkpoint-status | 8d9024cf-8b8d-450c-a230-27de773759be |  | checkpoint | Trade Clean / Protected
checkpoint-status | 85ef13b5-5fa0-45db-aefe-eba88f8f5bdf |  | checkpoint | PGI Support Clips
checkpoint-status | 7edd61f7-b247-4792-9799-8a6fa64f60db |  | checkpoint | Trims & Closers (Smoke Seal)
checklist-sectioned | 79d5530d-dda1-41ab-9f1c-7c04316b045b |  | checklist | 175mm SG CW QA List |  |  |  |  | Yes | 175mm SG CW QA Checklist | 1b517fec-aceb-42e6-900f-5cbb6e8453c5
checkpoint-group | 6cfda9c5-8929-4b67-8416-81ee4f41a20f |  | section | Internal QA
checkpoint-status | 0f86fd27-e859-426e-8355-9bed5b7258a5 |  | checkpoint | Seismic Head Installed As Per Shop Drawings - Photo Required
checkpoint-status | 8c3b2cbb-ef70-43cb-8fb0-804dafc38e19 |  | checkpoint | Seismic/Stack Sill Installed As Per Shop Drawings - Photo Required
checkpoint-status | cd332de8-a1d4-4738-a321-10bd5fb7c084 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 471e7bff-3a65-4fa9-8ed0-8b5dd9d75e8a |  | checkpoint | Jordahl Cast-in Channel In Place
checkpoint-status | 9f81bd80-77e9-49fe-ab9d-693cb47b22f6 |  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
checkpoint-status | 76ecaf2a-f130-4dc8-9aed-07598acbefa0 |  | checkpoint | C.W Visual Panel Check
checkpoint-status | 2e72fca2-9b0b-4afd-b440-c83aed16f6a6 |  | checkpoint | Panel Locked Off - Photo Required
checkpoint-status | cd45dab0-6acb-4408-9bac-2a5f77fdcba7 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference - required)
checkpoint-status | 7c08e8c9-2b7d-46fc-912e-c479db6b9b94 |  | checkpoint | Airseal and Internal Flashings - Photo Required
checkpoint-status | 60a328c9-68e2-4297-8914-ff3057d4bcf1 |  | checkpoint | PGI Support Clips
checkpoint-status | b704bf37-464b-406a-b6ef-5e8a8187f03b |  | checkpoint | PGI Fire Insulation (provide photo reference - required)
checkpoint-status | 3393c02c-fccb-4dad-b3d4-fe10741a4a61 |  | checkpoint | Trims and Closers (smoke seal) (provide photo reference - required)
checkpoint-status | 5f114548-9377-4c54-9d69-8cbd06f894e9 |  | checkpoint | Trade Clean
checkpoint-status | 2cc037f8-8b62-40a1-b659-00cc90cfc04f |  | checkpoint | Wight Signoff
checkpoint-group | 7f203081-1914-4cf9-b8aa-6b2d21a56621 |  | section | External QA
checkpoint-status | ca2d86c7-09cd-4c26-a185-3b44ce7f734a |  | checkpoint | External Flashings / Weather Seals (provide photo reference - required)
checkpoint-status | 05a874d9-9c13-4504-97d1-b4e1447c05be |  | checkpoint | Wight Sign Off
checkpoint-status | d960a17a-d1f5-460d-b4f8-566ed56cbabf |  | checkpoint | Arrow Sign Off
checklist-flat | a6106d85-d1a9-4ffc-ab30-08067821250e |  | checklist | Installation of Curtain Wall External |  |  |  |  | Yes | Add Installation of Curtain Wall - External Works | 2800bf72-7cc5-4aa8-ae89-8856b6c2e5c9
checkpoint-status | dc5ffe66-b729-4d32-9d1f-0d1c16f3f3f2 |  | checkpoint | Setout / Grids / Datum Lines
checkpoint-status | 81227795-7614-418e-b1be-b25f86a12dae |  | checkpoint | Subsill Installed (Refer Separate QA Form)
checkpoint-status | 18874247-a840-4ab2-8b80-859badfacc8d |  | checkpoint | C.W Panel Checked
checkpoint-status | a31c2627-cda4-45cc-89a4-3693df73994f |  | checkpoint | Splices & Soakers Sealed
checkpoint-status | f38a6918-5bc2-4163-a75e-409b40c89c53 |  | checkpoint | Brackets Welded & Painted
checkpoint-status | e5b6710b-3e3b-482f-8b37-0865cacf058d |  | checkpoint | Glass Fin Fixed As Specified
checkpoint-status | d747d5ae-545c-4d5a-a9d6-6f0d5e0e01d5 |  | checkpoint | Panel Locked Off
checkpoint-status | fc5df22e-4942-46af-b995-4c804947dcac |  | checkpoint | Guardspan Joint Soakers
checklist-flat | 0cd9336a-933d-429c-b34d-3c65c1bf3b8d |  | checklist | Door QA |  |  |  |  | Yes | Door QA Checklist | 283b1fed-9aff-436b-9ce9-f75b78b9f1ec
checkpoint-status | c4a6b3f5-b068-400a-b42f-c10b875fe6de |  | checkpoint | Opening Prepared By Builders - Including Rebates - Photo Required
checkpoint-status | 4e7e0414-48e6-4b4e-84e0-f4ca492cac43 |  | checkpoint | Framless Door Installed As Per Shop Drawings - MetroGlass - Photo Required
checkpoint-status | b1d29d6e-ddb2-4d3c-b91e-f72214da2e03 |  | checkpoint | Trade Clean
checkpoint-status | e973a248-7d3b-4079-bffb-8de9fd8e23ac |  | checkpoint | Wight Sign Off
checkpoint-status | 8df59f5e-ee11-4636-b7b2-e05cf5f134e1 |  | checkpoint | W&W Sign Off
checklist-sectioned | c7a7fa9f-a3d0-4639-8042-e0c83bd8c81e |  | checklist | 100 / 125 / 135mm Flushglaze CW QA List |  |  |  |  | Yes | 100 / 125 / 135mm Flushglaze CW QA List | 30eb4384-0892-4ec0-b479-ec2c98f138fd
checkpoint-group | 6fb1b9d0-c3f7-49d4-a5b1-52cb0fe0ae08 |  | section | Internal QA
checkpoint-status | 0df1fcf1-f1d5-4361-ba16-eadd75ec5b65 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | d55e4941-5532-49c2-ab8c-389b6b350dd5 |  | checkpoint | Seismic Installed As Per Shop Drawings (Photo Required)
checkpoint-status | cd04bbe4-3999-468f-a302-22df8469b3b0 |  | checkpoint | Secondary Steel (By Others) In Correct Place
checkpoint-status | 27e458c3-738e-4f84-b6f6-a4250663de0b |  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
checkpoint-status | 1841cded-0858-4819-94f5-eb233bace5a0 |  | checkpoint | C.W Visual Panel Insert Check
checkpoint-status | 713da29e-490b-4c6a-91d0-e6c4df5a3a63 |  | checkpoint | Panel Fitted & Locked Off (Photo Required)
checkpoint-status | 51fd3742-1e85-4a6c-a88d-011a5d38e9b9 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | b9d44688-cbaf-4f7c-9469-d3244102a37a |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | 01b194f3-d226-4cdd-a9d7-28eb6e6d89db |  | checkpoint | PGI Support Clips
checkpoint-status | 77346b7e-9426-45e5-945a-4094e66f4a11 |  | checkpoint | PGI Fire Insulation (provide photo reference)
checkpoint-status | 5cbb7883-e451-4395-be3a-5238f2146617 |  | checkpoint | Trims and Closers (smoke Seal) (provide photo reference)
checkpoint-status | 3f0043c4-a20d-4ed4-a482-9403c40c9745 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | 182dcfa3-4df2-42d1-9a00-3434d7c74a8d |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint-status | 8ce8ec80-223b-494c-aef1-3b2b39213cad |  | checkpoint | Trade Clean
checkpoint-group | 9165cc5e-328a-4eb6-bf8e-84ed79795da8 |  | section | Sign Offs
checkpoint-status | ba12a62e-41f6-4eaa-942e-475ae36a29c4 |  | checkpoint | Wight Sign Off
checkpoint-status | 7a3aea60-907e-4c51-ae90-01f8ad7d3d44 |  | checkpoint | Naylor Love Sign Off
checklist-flat | 9245b699-776b-49ea-863d-8f6c0d0e4044 |  | checklist | 150mm Flushglaze CW QA |  |  |  |  | Yes | 150mm Flushglaze CW QA | 38a930ab-790e-4771-bc78-9c14e717425a
checkpoint-status | 3850d4e5-28fb-4145-ab5b-91529f89c7cd |  | checkpoint | Opening Prepared By Builders
checkpoint-status | 9385a951-e526-45b1-8919-69be40d36c18 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 2aafbb99-fcc4-4477-a316-344a0c099904 |  | checkpoint | Seismic Installed As Per Shop Drawings (provide photo reference)
checkpoint-status | 59e825b7-11a9-4332-9e5f-587f4ac98a24 |  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
checkpoint-status | 4268b451-f60d-45f0-8344-94c089855487 |  | checkpoint | C.W Visual Panel Insert Check
checkpoint-status | 45d48957-ad68-444d-ba38-9ab433443a22 |  | checkpoint | Panel Fitted & Locked Off (provide photo reference)
checkpoint-status | f3d28319-106d-41a5-bc00-c92ba5b019a8 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | df868d32-3167-47a6-a624-355fce8b72e9 |  | checkpoint | Airseal and Internal Flashings (provide photo reference)
checkpoint-status | 97f274fd-1aff-4bc7-b9e2-6025090ffff4 |  | checkpoint | Window Insert / Door Installed As Per Shop Drawings
checkpoint-status | be23d9c6-b6e9-4323-a0f5-a3d99cd96f07 |  | checkpoint | Autodoor Unit Installed - Dormakaba
checkpoint-status | d7cc1f8f-56cc-40b5-8ff9-133cc69e0002 |  | checkpoint | Autodoor Unit Commisioned - Dormakaba
checkpoint-status | 481eacf0-a9ed-40fa-947d-dc8f252a3b02 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | 0205af3f-a686-4aa5-bc8f-2b583c0e31bd |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint-status | 4999df92-c90a-414f-8559-7f62cd779fd0 |  | checkpoint | Trade Clean
checkpoint-status | 8c340bc7-463a-4da9-8200-aa5e264f625f |  | checkpoint | Wights - Sign Off
checkpoint-status | 1e0c0567-eb3d-4bce-9c40-8988a9f320b3 |  | checkpoint | Holmes Wellington - Sign Off
checklist-sectioned | fa31e814-0bff-49ee-9b21-ab9840400c74 |  | checklist | Auto Doors |  |  |  |  | Yes | Auto Doors | 54e3b286-4e16-4c49-99b1-00156eff0631
checkpoint-group | 2b5164b4-e45a-42ce-9f4f-601200a6a70b |  | section | Auto Door QA
checkpoint-status | f65cad39-5f35-4b56-9c68-51e346fbb76c |  | checkpoint | Opening Prepared By Builders
checkpoint-status | 6ffc7864-a319-434a-8164-7f5566ab5659 |  | checkpoint | Window Insert / Door Installed As Per Shop Drawings
checkpoint-status | 5904e67a-a978-412f-bb4e-bae3805b888d |  | checkpoint | Autodoor Unit Installed - Arabian
checkpoint-status | 6a367732-7418-4814-9ac8-ea0b5b6c110b |  | checkpoint | MetroGlass Site Glazing
checkpoint-status | ab87e0df-4573-42db-9f91-e37b77c582ef |  | checkpoint | Trade Clean
checkpoint-status | 9687d18f-f13a-4281-8c0f-f97adfdd5bd9 |  | checkpoint | Autodoor Unit Commisioned - Arabian
checkpoint-group | 5023c56d-2bfa-46f3-a59d-a43eec7acf04 |  | section | Sign Offs
checkpoint-status | 9af4ad45-ada4-40e9-b761-177cc926e44a |  | checkpoint | Wight Sign off
checkpoint-status | c72976ce-dc5f-4f2a-8f17-b6718f5aefe4 |  | checkpoint | Arrow Sign off
checklist-flat | 21930a13-ba97-49a9-ad02-5ae6649c4671 |  | checklist | Windows & Doors |  |  |  |  | Yes | Add Windows and Doors Manufacture Checklist | 699102e3-d2a4-4779-a8c1-505ef8fb50e9
checkpoint-status | d08114e9-fcf8-4e78-80a6-4ff841396661 |  | checkpoint | Cut & machine frame check drain holes
checkpoint-status | 8a4b3630-581c-4fcf-8673-bc9bf4ff5de5 |  | checkpoint | Screw frame together
checkpoint-status | cae2faf5-da8b-47ab-9441-d01916c63ee0 |  | checkpoint | Back seal frame
checkpoint-status | 833747e0-40ac-49a8-9411-5810ecfbf6ad |  | checkpoint | Hardware fitted, strikers, door stops etc
checkpoint-status | f30a7cf4-8281-4f53-ba8a-b5dfe8497974 |  | checkpoint | Support blocks fitted
checkpoint-status | 391e8c11-79a4-43fb-af07-4ca3e7e13728 |  | checkpoint | Wipe off over seal
checkpoint-status | eec55cdd-15dc-4e77-8d14-1ccaef59b958 |  | checkpoint | Fit hinges
checkpoint-status | c03d6f2b-2e6a-4b39-9d07-3502f4fd1d2b |  | checkpoint | Read notes on manu sheet
checkpoint-status | 1acfd9a1-7a0f-4863-8cd5-0ded1e9b38fb |  | checkpoint | Final QA sign off complete
text | 5dac8885-54da-4541-a965-b9cd226c0eb2 |  | textbox | Date completed
checklist-sectioned | 5695a22d-8b0b-472a-866c-78ff466561c8 |  | checklist | 125mm Seismic Strip Windows QA |  |  |  |  | Yes | 125mm Seismic Strip Windows QA Checklist | 69981fd8-d084-449d-a77c-066a5176bc30
checkpoint-group | 6218ab76-0b02-47b0-be68-fb561bbbe120 |  | section | Internal QA
checkpoint-status | c1b4bb8d-dafe-4fdd-abaa-587f0ebc41b9 |  | checkpoint | Opening Wraped & Prepared By Builders
checkpoint-status | cd10c521-1a7d-485a-bcf5-a15ab3b46aff |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 211b629f-5c88-4eff-b98e-0ecca79b66e8 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 0cc9fd19-fa69-4aff-9857-8fe2ba828238 |  | checkpoint | Splices & Soakers Sealed (provide photo reference - required)
checkpoint-status | 7d623cee-fbf1-4ba6-a436-40e38eb3e94f |  | checkpoint | Window Inserts Installed As Per Shop Drawings
checkpoint-status | 513af279-8c9a-4c84-ab9b-3eee666a929e |  | checkpoint | Airseals Completed - Photo Required
checkpoint-status | 1584e9b9-dd00-485c-8c1c-98df41961cbb |  | checkpoint | Trade Clean
checkpoint-status | fb1a5e6c-31b5-4cce-8f18-3c45d92737ba |  | checkpoint | Wight Signoff
checkpoint-group | b42e83dd-b566-4e7d-8f2e-ae692d6769e7 |  | section | External QA
checkpoint-status | caf1301c-8336-420f-8d42-deabf18b3a28 |  | checkpoint | External Flashings / Weather Seals (provide photo reference - required)
checkpoint-status | 5c6bb50e-c1c3-4839-9a9c-40f7d9903fa6 |  | checkpoint | Sun Fin Fitted & Bolted to Correct Torque Setting
checkpoint-status | 0e5c7b89-15d2-4076-9fcd-b10169773e6d |  | checkpoint | Wight Sign Off
checkpoint-status | ec8404ac-d899-4964-9cab-9691c6acbbcb |  | checkpoint | Arrow Sign Off
checklist-sectioned | 7ce9d6f9-a22b-4faa-ab3c-11c09ba09730 |  | checklist | APL 100mm Shop Front |  |  |  |  | Yes | APL 100mm Shop Front | 6e58ae38-18ff-4d95-96a2-ec3272dbdc6f
checkpoint-group | cca8745a-38cf-4275-9425-617e785f0a45 |  | section | Internal QA
checkpoint-status | fc4fb1ef-21da-4d51-bf38-a1088f694f30 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 27ea81a0-4187-4cea-a6e0-b9e185bc41f2 |  | checkpoint | Seismic Installed As Per Shop Drawings (Photo Required)
checkpoint-status | 35ceb3ac-17a7-494a-b254-ce251111086b |  | checkpoint | Secondary Steel (By Others) In Correct Place
checkpoint-status | 12f59993-7057-4bb1-8508-7c4e9f64debe |  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
checkpoint-status | bb50a885-f522-4e81-81b6-ca9c90e0a741 |  | checkpoint | C.W Visual Panel Insert Check
checkpoint-status | d36b13c0-9826-4288-8719-a0146f7381a7 |  | checkpoint | Panel Fitted & Locked Off (Photo Required)
checkpoint-status | 68527759-0eec-4887-a030-ef1208b267f4 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 90f83fdf-14f5-42f0-bdca-5d0394f63781 |  | checkpoint | Airseal and Internal Flashings
checkpoint-status | a0b1004e-3ac8-42fb-9b85-ce2b5c964502 |  | checkpoint | PGI Support Clips
checkpoint-status | 58dab8b1-a9a5-42af-a133-b447fceba080 |  | checkpoint | PGI Fire Insulation (provide photo reference)
checkpoint-status | 2a620e3b-bdcd-4a80-a55a-ba96ce577408 |  | checkpoint | Trims and Closers (smoke Seal) (provide photo reference)
checkpoint-status | cf5427bf-ab7c-4995-907c-b74b2b2fe9c8 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | a8ccb422-3fb7-4a1f-b831-e878df304751 |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint-group | 704b6dfe-8df9-446c-98c8-b84eb0e8e3cd |  | section | Sign Offs
checkpoint-status | feabdc85-ec5b-4cae-b4c0-9a248e3449f5 |  | checkpoint | Wight Sign Off
checkpoint-status | 6b1ad13d-bbae-45f4-a13f-12992303f382 |  | checkpoint | Naylor Love Sign Off
checklist-flat | 3f076237-61af-4040-874d-dc92bea3084b |  | checklist | Installation of Subsill |  |  |  |  | Yes | Add Installation of Subsill | 7303c120-4c44-4207-a9b7-3285e03911b5
checkpoint-status | dc277340-f0b3-4ab9-9ed9-25cb5b399782 |  | checkpoint | Setout / Grids / Datum Lines
checkpoint-status | 426b780d-a0ea-46e4-8f01-b7f1450f72ac |  | checkpoint | Markout & Drill Holes (Check Edge Distance)
checkpoint-status | e7782f06-76be-4ac3-b78f-6f07ddcd11bd |  | checkpoint | Apply Duo Kit to Hole / Around Stud
checkpoint-status | ddfe3f6d-e632-4216-b966-bf4a0587510e |  | checkpoint | Install Backer Rod
checkpoint-status | 13d7a530-1623-495e-9227-c5b991580e34 |  | checkpoint | Inspection of Membrane / Sign Off From Builder
checkpoint-status | fb41318d-b0ad-48ed-9db8-f9b9f1f4122c |  | checkpoint | Apply Epistik Primer
checkpoint-status | af542795-3442-403f-818e-4ba6df443f52 |  | checkpoint | Install Subsill / Splices / Soakers
checkpoint-status | 2a2d8c0d-5f0a-436d-a6bb-38bb2a533aba |  | checkpoint | Complete Airseal Within Application Time Allowed
checklist-flat | c55d7a0d-1e1b-4924-9544-0c3313a5f1bd |  | checklist | Wight Area Completion |  |  |  |  | Yes | Wight Area Completion | 7b42e619-d031-4d82-acb8-ae1e3ae1f09f
checkpoint-status | e9391c03-fd46-4b0a-b0e0-d726050c1e71 |  | checkpoint | All elements completed correctly as per specification, reviewed and approved
holdpoint | 7f0b2600-179c-4452-821d-1a0752da518f |  | signoff | RAISE REMEDIAL / REQUEST SIGN OFF
checklist-sectioned | dc2626c7-8dbe-4780-8026-f9b14330faa8 |  | checklist | Parapet Checklist |  |  |  |  | Yes | Add Parapet | 7ceceb6d-ab5f-4bb6-973a-8f48cdd2ee8a
checkpoint-group | c23812e3-c6b4-41da-97db-df1a193b5726 |  | section | Parapet
checkpoint-status | 3ff29404-0a84-4db2-a6ca-e82dfa9e530a |  | checkpoint | Parapet Cap Delivery
checkpoint-status | e0ef50bf-95c0-4c59-be7d-bdc75b7abc8a |  | checkpoint | Inspection of Membrane / Signoff from Builders
holdpoint | e919a09e-7803-4f2c-a70a-19d2c1602c4f |  | signoff | Lt McGuinness Signoff
checkpoint-status | 77ebf5a5-3294-489a-afba-be5f5dd274c6 |  | checkpoint | C.W. Panel Gutter Drainage Checked / Cleaned
checkpoint-status | 649c18a6-03ed-49ef-8cb8-9afa10ea6f91 |  | checkpoint | Parapet Under Flashing Fitted / Sealed (provide photo reference)
checkpoint-status | a68188fd-5909-43d8-8c6c-29ac596b3fec |  | checkpoint | Fixing Bracket Installed / Fixings Oversealed
checkpoint-status | 0b79cbef-502b-48cd-8671-8e59c60ae4a1 |  | checkpoint | Fit Parapet Jo Soaers / Seals
checkpoint-status | 7f76c888-f997-42e2-9e5f-e1d9e566aa1e |  | checkpoint | Install Parapet Cap Flashing
checkpoint-status | 359726b0-ff06-4fa3-88bd-28bd55569bd0 |  | checkpoint | Trade Clean (provide photo reference)
checklist-flat | c8bcfdcc-5459-4df1-a8a3-c23610d3e0bf |  | checklist | 40mm Seismic Strip Windows QA |  |  |  |  | Yes | 40mm Seismic Strip Windows QA Checklist | 888440ae-b49c-4ede-96b4-811e9bfc6c07
checkpoint-status | 194c0c7c-c77b-4f66-8da2-87787be2abe5 |  | checkpoint | Opening Correctly Prepared By Builders
checkpoint-status | 7017fb65-3407-4ace-b151-a99d13c9a5ff |  | checkpoint | Seismic & Window Inserts Installed As Per Shop Drawings
checkpoint-status | a01e3c05-4ef6-460b-a64b-910c36276a0e |  | checkpoint | Acoustic Batts & Perforated Sheet Installed As Per Shop Drawings
checkpoint-status | c42f8946-eb9d-4a10-bb92-3b1bf0203cc9 |  | checkpoint | MetroGlass Site Glazing - Photo Required
checkpoint-status | c842a18f-7d86-4355-b5da-28f36f607589 |  | checkpoint | Trade Clean
checkpoint-status | 336bd4b7-7733-4c20-b3fa-cfed2fd69c5f |  | checkpoint | Wight Sign Off
checkpoint-status | 0d8d1258-7cfa-4cda-8ad1-32a4147e4f41 |  | checkpoint | Arrow Sign Off
checklist-flat | b4d96b33-71f1-4b46-a412-b00bec92abfd |  | checklist | Seismic Suite (non curtain wall) |  |  |  |  | Yes | Seismic Suite (non curtain wall) | 8a6675fa-fd99-4585-b1ff-799d33d7c5a1
checkpoint-status | 1b4b41cd-f38b-486c-adfe-c642b127a240 |  | checkpoint | Opening Prepared, Wrapped & Datums
checkpoint-status | a892e3b3-75c7-472d-9b56-5c6decd976b8 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | b216feb6-7ead-485b-868c-aab592679bc7 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 58b24c1d-450d-46bf-94a2-fbcf890988bc |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 49750c47-6ca0-4191-8ede-40bef7b9e8a9 |  | checkpoint | Airseal and Internal Flashings (Photo)
checkpoint-status | 1bd6f9ff-d10f-4df5-99b5-b95ba07fcd01 |  | checkpoint | External Flashings / Weather Seals / Drainage
checkpoint-status | 0ce8cc57-26da-4f90-b7e7-d290c8da23be |  | checkpoint | Site Glazing Completed
checkpoint-status | 8a01d6c4-82e0-47fa-b6ff-cc11d7ecf3e3 |  | checkpoint | Trade Clean
checkpoint-status | 88e5fe84-1b29-4a8d-91db-10dc41553300 |  | checkpoint | Wights - Sign Off
checklist-sectioned | 9f16995c-5178-48dd-9f22-f74316ae346e |  | checklist | 40mm Metro - Thermal Heart QA |  |  |  |  | Yes | 40mm Metro - Thermal Heart QA | 8c91a106-ef56-4b6b-a2be-48c6a46e04ad
checkpoint-group | 4b5fd2e7-6187-40c4-b1b0-2dba4884d68f |  | section | 40mm Metro - Thermal Heart QA
checkpoint-status | a89c1d05-9447-4d24-8c3b-a41129df1649 |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint-status | fea7cb2e-f887-47f6-89b5-92b23b6ad939 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | aa791b37-aa1f-4e5e-95da-28e19fb32620 |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
checkpoint-status | 30a3af13-cb70-4f8f-bd58-fc5bf7dead23 |  | checkpoint | Window Installed / Fixed As Per Shop Drawings
checkpoint-status | 236236b4-58dc-40c5-a326-304140330781 |  | checkpoint | Airseals Completed
checkpoint-status | 67bf2fdb-5e68-4c9c-82bb-c49e32e204d5 |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint-status | d7ffc04b-b9c9-49d9-b7f2-3206e8eb1bce |  | checkpoint | Trade Clean
checkpoint-group | a08b4f3b-56ed-4c1b-8791-8a3623333810 |  | section | Sign Offs
checkpoint-status | 983dd9f3-7144-4527-9790-61043052508b |  | checkpoint | Wight Sign Off
checkpoint-status | f55e2023-4949-4a44-a222-03f58c4ea210 |  | checkpoint | Naylor Love Sign Off
checklist-sectioned | 684eb11d-0aa4-406d-a787-2f9b86a6ad24 |  | checklist | Glazing Checklist |  |  |  |  | Yes | Add Glazing Checklist | a8b0b33c-0b79-43cb-8e8c-5781603b7b8b
checkpoint-group | b16caa5f-63d6-4d83-aa82-1e6c7bd2177f |  | section | Panel
checkpoint-status | adf92c18-8817-42d7-bfd3-964c8aaa8d9d |  | checkpoint | Check Frame Square
checkpoint-status | ea3608e4-5ab3-4641-b794-fed55125bed6 |  | checkpoint | Check Drain Holes
checkpoint-status | 0c2e82a9-1514-4673-ab7e-48b161cfb5ea |  | checkpoint | Air Blow Frame Down
checkpoint-status | 580b2767-76ef-4985-97c6-9b8290ef32de |  | checkpoint | 2 Rag System Isopropyl
checkpoint-status | dbf20097-00d1-46cd-86cc-69776c56d1e4 |  | checkpoint | Primer Wipe Only
checkpoint-group | 3dbffbe2-0429-4736-88d5-1b2a754a8701 |  | section | Glass
checkpoint-status | 9b847159-fcc2-47ff-8877-93cf63b2a194 |  | checkpoint | Inspect / clean glass
checkpoint-status | 94b169b9-1849-4d2e-b5ef-a6aa2e18bc52 |  | checkpoint | Glass Strength check
checkpoint-status | b87937a8-5c35-4a5a-8bde-25f1f5113dc4 |  | checkpoint | Outer lite
checkpoint-status | 6b1d7ac1-186b-4122-ac2e-49b7b17c3aee |  | checkpoint | Inner lite
checkpoint-status | 9c1d59bf-0045-4290-a1a6-90c54fcf99a5 |  | checkpoint | Tape Glass
checkpoint-status | 99501778-b190-47b0-9eb6-d88969e8c911 |  | checkpoint | Prep glass edge iso
checkpoint-group | 8c0b2bdb-eb39-4d66-b3f7-f7b1f9af0126 |  | section | Glazing
checkpoint-status | b25daaea-7c0b-4f33-ae31-18ff18bca8a8 |  | checkpoint | Install Structural Tapes
checkpoint-status | 3e80c35c-7d90-4cda-bfda-e0bdf4113462 |  | checkpoint | Install Structural Bit Sealant
text | 52db8474-c72c-43dc-965d-f4b8d8d35c00 |  | textbox | Batch number
checkpoint-status | ed8169b9-d425-4906-b3b7-7f10f479cf59 |  | checkpoint | Install Setting blocks
checkpoint-status | 1198150f-2115-4788-bff4-6ce1a4b1e0ae |  | checkpoint | Install PEF Rod
checkpoint-status | 9a6a0286-5c4a-41f5-9397-927a820c0a47 |  | checkpoint | Install Wealther Seal
text | 48344404-1f8f-4e13-9ab9-7cd75070fc51 |  | textbox | Batch Number
checkpoint-status | c270d5a2-db16-490b-949e-a50ffc72008f |  | checkpoint | Install ACM PEF Rod
checkpoint-status | 4bf1d369-4a28-4e5a-8258-c87044c958be |  | checkpoint | Install ACM Weather Seal
text | 7e236acf-098e-4380-badc-c94724cca61d |  | textbox | Batch Number
checkpoint-status | 9aa2fca8-9785-4db6-ad3c-2735d788f090 |  | checkpoint | Clean Frame Down
checklist-flat | aedd3760-8093-4ab5-80c3-b0dbda66d748 |  | checklist | 168mm SG CW QA |  |  |  |  | Yes | 168mm SG CW QA Checklist | a95c7c2a-8486-4f8b-87e5-fc7bf58c6a23
checkpoint-status | 7c3ddc56-e487-42a3-b742-a888a7c7ad84 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | a5534efa-0045-451f-b9ff-b09c0ea20060 |  | checkpoint | Seismic Sill / Jamb Installed As Per Shop Drawings - Photo Required
checkpoint-status | c768b842-7bf6-4875-b257-fded99555c52 |  | checkpoint | DL Brackets Fitted & Bolted to Correct Torque Setting
checkpoint-status | 62c4959e-ef37-42d9-ab5f-89f3f217b936 |  | checkpoint | C.W Visual Panel Check
checkpoint-status | 6b3ae377-d7ab-4aff-8598-732b1512d55e |  | checkpoint | Splicers & Soakers Sealed (provide photo reference - required)
checkpoint-status | eed6095e-7758-4cb3-b4c2-9bab1a33e667 |  | checkpoint | Airseal and Internal Flashings - Photo Required
checkpoint-status | 46d5a4a2-9daf-413d-940c-d3f501c5e305 |  | checkpoint | Trims and Closers (provide photo reference - required)
checkpoint-status | 4961f6d7-3e28-40e5-ab97-ef2f5b8b7f58 |  | checkpoint | Parapet Flashing Installed As Per Shop Drawings
checkpoint-status | e47d1785-ea50-4263-80a5-45c9270b077b |  | checkpoint | External Flashings / Weather Seals Completed (provide photo reference - required)
checkpoint-status | c85b349b-7fe9-425f-9fcf-c7e5b0792c38 |  | checkpoint | Trade Clean
checkpoint-status | ae28b110-b42b-4134-9c09-999f6e62cc8f |  | checkpoint | Wight Sign Off
checkpoint-status | 28f4ff70-9cdb-4bfd-944b-9a7cbfd3d2de |  | checkpoint | W&W Sign Off
checklist-sectioned | 02d5ad58-68d2-494e-8aef-fb69ac540a5d |  | checklist | 40mm Metro QA |  |  |  |  | Yes | 40mm Metro QA | c33cefea-724d-4d1c-ae5c-a8d5b90f8acc
checkpoint-group | e8b80c8c-466e-4d9b-a6f2-2ab246a9d20a |  | section | 40mm Metro QA:
checkpoint-status | 19146f12-4c82-40ce-bbc8-fc253d840559 |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint-status | eda8269b-6d64-4dbe-8de5-4b2bbf617f2f |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 97e7ec98-234c-4701-8534-38a9a714da9c |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
checkpoint-status | 6f8f9bd0-3219-4e0a-9533-71cdbb41ba09 |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | 9ceaacda-c251-44c7-b861-9e7279491fd8 |  | checkpoint | Airseals Completed
checkpoint-status | 7cbacb94-eb89-4df8-920b-054f1cf3a373 |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint-status | c9f42457-e35b-4322-99fb-c552842c3c3b |  | checkpoint | Trade Clean
checkpoint-group | 11e9cc94-e7e2-43c1-926e-d85c0b87f1dd |  | section | Sign Off
checkpoint-status | eac9884c-0064-419a-bbcc-0301cfe85d03 |  | checkpoint | Wight Sign Off:
holdpoint | 078743f3-3211-4b2d-927f-2aad0eae085c |  | signoff | Wights - Sign Off
checkpoint-status | c2792548-0e33-4910-950b-b2ecee1284fb |  | checkpoint | Builder Sign Off:
holdpoint | 600cfa7f-fae0-4074-b312-90c2b823b771 |  | signoff | Builder - Sign Off
checklist-sectioned | 622202d1-29a5-4778-ae56-b4a01655f83c |  | checklist | ST - S - Punch Window Frames |  |  |  |  | Yes | ST - S - Punch Window Frames | ca50f8ce-6f6a-4599-ad19-3e5d6bde9f67
checkpoint-group | d8b7ebdd-66b6-4038-be8c-81d2b2c20d3f |  | section | Glazing Install
checkpoint-no-status | 5947f253-b354-4a3d-91cc-f3caffe8e36e |  | checkpoint | Glazing Install
label | 9d7bf985-b665-5019-81cf-52bef8d0492b |  | note | Window # / Elevation / Level
checkpoint-status | 3c0101d3-4c6e-4d0a-8da0-6569b07a3cb7 |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status | dd76003c-e73d-4d41-b772-3f9694a8e006 |  | checkpoint | Check the joinery is free from damage
checkpoint-status | 1db9121b-123c-4d0f-b0d8-c0cc1a2a91eb |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status | 3b52cf8c-d0eb-4dc9-90e8-d39024eb64d4 |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status | c282e45e-834c-4b3d-b8e7-3daf6f063ed2 |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status | f758f35b-40cc-48dd-a70d-b4d1916693b5 |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status | 04be2a85-7151-49e8-b2e8-127b903a1ed7 |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status | 9dbae2ad-f135-4443-9d1a-756ace7680e6 |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status | 3297b727-d695-4674-8948-d7a849e9c77e |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status | 1ab20020-ceaa-4b30-b150-3d277829627d |  | checkpoint | Glass Stickers removed
checkpoint-status | 7dddca91-08d3-45b2-92ce-16933ac02fd7 |  | checkpoint | Trade Clean
checkpoint-status | 2ed17911-3c35-4fc9-8b22-b2b53deebcca |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status | b41cd18b-361b-497c-8be4-fd0bf1fff2e5 |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint | 4d364ddb-0535-4e03-9585-32a5cedc75fe |  | signoff | Raise Remedial
checklist-flat | 1faf1e8e-f99f-4f39-984c-7d914ba95459 |  | checklist | Installation of Window Units / Doors (General) |  |  |  |  | Yes | Add Installation of Window Units / Doors (General) | ccb4edda-7a45-4ed3-9e79-5a4eb9b5bb7c
checkpoint-status | 1cbdd829-3ac3-4d21-ace1-8af5319463f4 |  | checkpoint | Structural Tolerances Correct
checkpoint-status | 53d236c3-2c9f-4a7b-b8b0-472fe7c9d3d4 |  | checkpoint | Building Wraps / Membranes Correct
checkpoint-status | 06eebc0d-fc8d-4c55-b075-24d1960902cd |  | checkpoint | Sill Plates Right Height / Screws Sealed
checkpoint-status | 30084615-aa6e-43a7-9c55-43d8a822ba78 |  | checkpoint | Sill Installed / Screwed / Sealed to Frame / Structure
checkpoint-status | 8da9532f-96df-4cde-8ebf-33d738f7ba23 |  | checkpoint | Window Frame Installed Plumb / Screws Sealed
checkpoint-status | ca2b3ac9-c61d-4724-b000-3ae9b4d1047c |  | checkpoint | Internal Perimeter Air Seal
checkpoint-status | 18ffac3f-dbbf-494c-9d0e-b521e9413219 |  | checkpoint | Head Flashing Fixed / Taped / End Stops
checkpoint-status | 308b9222-0f39-4b88-a988-c9c518db6a5a |  | checkpoint | Fixed Lite Frame Gasket Installed
checkpoint-status | 980e11e4-21e4-4ba3-8b95-82139825609a |  | checkpoint | Sliders Are Adjusted / Operable
checkpoint-status | 9483937c-7c55-4bd0-b476-2d65d668bf8d |  | checkpoint | Hardware / Door Stops Complete / Infills
checkpoint-status | c8936a7b-9511-47ba-b821-28bbb8c149e5 |  | checkpoint | Trade Clean / Protection
checklist-flat | a7c38a9c-3367-4bb5-bc6e-e2780dc5dfb3 |  | checklist | Installation of Parapets |  |  |  |  | Yes | Add Installation of Parapets | d48af44e-9b78-48c2-9775-d187d8f303e0
checkpoint-status | b167f68a-b8a9-4f6b-bd07-f94e0dcacc71 |  | checkpoint | Parapet Cap Delivery
checkpoint-status | 5ca18b5d-c646-43de-913c-d56bd89b2037 |  | checkpoint | C.W. Panel Gutter Drainage Checked / Cleaned
checkpoint-status | 63946ac9-3244-4c1b-8e6d-4d21f083085e |  | checkpoint | Fixing Bracket Installed / Fixings Oversealed
checkpoint-status | b4c8ee85-6a31-4c6a-8196-f6a7b4306e0b |  | checkpoint | Install Parapet Cap Flashing
checkpoint-status | 5ead1b61-4309-4f4f-9af2-8804d7f913d6 |  | checkpoint | Inspection of Membrane / Sign Off From Builder
checkpoint-status | fb7bae94-c8dc-4786-a76a-3fc2a2b0841c |  | checkpoint | Parapet Under Flashing Fitted / Sealed
checkpoint-status | 6cb2d6df-6386-45f9-a797-10dda86e5020 |  | checkpoint | Fit Parapet Joint Soakers / Seals
checkpoint-status | 8abcbba5-1d9f-4b87-ab48-52f30a71f9f8 |  | checkpoint | Trade Clean
checklist-flat | 6c120dbe-b2ec-4044-a0aa-db2efd3d3e68 |  | checklist | Commercial/Domestic |  |  |  |  | Yes | Commercial/Domestic | dfaafb36-6ee3-4850-be74-15dc8e9e0e81
checkpoint-status | abb65ac5-bd41-40be-aea1-0f52c2f177b3 |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint-status | 83fadfac-6e12-4fb1-a433-7185be918a2a |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing
checkpoint-status | c39c702b-9304-48e0-bc75-fc311ba4e898 |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | f5804fab-9491-4578-a33c-8cdf762aa6a3 |  | checkpoint | Airseals Completed (photo)
checkpoint-status | b4011034-e7b9-42ff-b612-018da12e793b |  | checkpoint | Site Glazing Completed
checkpoint-status | b0cac73a-ab69-4bfa-bd5e-4d0973a8d3e2 |  | checkpoint | Trade Clean & Sign off
checklist-flat | a560609b-b844-42d5-baef-1990d897d2d1 |  | checklist | Metro - Metro Thermal Heart Windows QA |  |  |  |  | Yes | APL Metro - QA | e1a2383d-7d06-4361-8725-4bd577fc8d21
checkpoint-status | 3c5326c7-1f22-4c69-8413-c9deebc17b5a |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint-status | 5ee7ca4e-6ab3-4d02-b9c1-cbe084cdf597 |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | e9e84026-8536-4e0b-90fd-7f937d7f9f25 |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
checkpoint-status | eea777af-7b1b-4b0c-ad9d-8f98529fa3c7 |  | checkpoint | Window Installed / Fixed As Per Shop Drawings
checkpoint-status | 80df2670-ae5e-431d-9a23-9e4446248d12 |  | checkpoint | Airseals Completed (provide photo reference)
checkpoint-status | a0071f55-b411-4542-b009-a3dffb508e8f |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint-status | 0f6b7377-c9a2-4712-9cc8-c2da2a628666 |  | checkpoint | Trade Clean
checkpoint-status | 1eb1f8f0-0744-41f5-b952-b854cffe9579 |  | checkpoint | Wight - Sign Off
checkpoint-status | 33de34d5-5546-4238-a670-d924339eaecc |  | checkpoint | Holmes Wellington - Sign Off
checklist-flat | 466818af-9533-4eb5-bcb0-aec46e6a0d6e |  | checklist | Seismic Suite (Curtain Wall) |  |  |  |  | Yes | Seismic Suite (Curtain Wall) | e8a99dfd-0fce-4e5c-b339-dabdfbe05cbe
checkpoint-status | 62a9355b-2867-4071-bbe1-bf01456ff9cb |  | checkpoint | Opening Prepared By Main Contractor
checkpoint-status | 402f05e2-a6c0-4d28-8592-51c4c10a132a |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 29ce3160-4558-4b77-a8a1-04a79df2efe5 |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint-status | 35537aab-2c88-41c3-9dbc-71dd7f37e547 |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint-status | 00c3554a-20de-4d72-be0f-691506e4060a |  | checkpoint | Panel Fitted & Locked Off
checkpoint-status | 77a428b4-ead3-4b49-8b87-fa0cac31e7d8 |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint-status | 344e7a06-ffaf-4d74-ac52-2beca65503e1 |  | checkpoint | Airseal and Internal Flashings (photo)
checkpoint-status | f7cded34-2708-4239-ac20-5ee13dee409c |  | checkpoint | Smoke Seal Complete (photo)
checkpoint-status | ae5f4ace-8515-4ef6-b5b2-e94fd2e9cdac |  | checkpoint | External Flashings / Weather Seals/Drainage
checkpoint-status | 48b4defa-3d6d-466c-ba12-3129e7d7ff23 |  | checkpoint | Trade Clean & Sign Off
checklist-sectioned | 15819fc6-f7f1-49f5-b620-a4741233a1d4 |  | checklist | Unit - |  |  |  |  | Yes | Add New Window or Door Unit | ef46890d-4ca2-4058-b965-6c17352657e6
checkpoint-group | cffbedee-91d8-4178-8d36-caf1d68e30b8 |  | section | Window & Door Manufacture QA
checkpoint-status | 791c503d-d486-45e3-bd78-260f2de0264b |  | checkpoint | Cut & machine frame check drain holes
checkpoint-status | 84c4ea95-d869-4a37-9ae1-92f04b11554d |  | checkpoint | Screw frame together
checkpoint-status | ea47921b-4e6a-4a22-8ad6-ca934870a712 |  | checkpoint | Back seal frame
checkpoint-status | d4401d17-bc77-4add-93f6-9c2ca76c3405 |  | checkpoint | Hardware fitted, strikers, door stops etc
checkpoint-status | 452dc490-dcd1-4dd2-a8f9-811e15bf7c73 |  | checkpoint | Support blocks fitted
checkpoint-status | 01b7339c-7831-429a-b8c3-8f759b2b33d9 |  | checkpoint | Wipe off over seal
checkpoint-status | bf8e8618-d373-4a40-9ea6-1a05ca6f8f9e |  | checkpoint | Fit hinges
checkpoint-status | 17432fc5-ceb1-4182-af43-9f378c6fccee |  | checkpoint | Read notes on manu sheet
checkpoint-status | 588eefe3-78f7-4069-b408-eea3a4c1ac1b |  | checkpoint | Final QA sign off complete
text | 5dac8885-54da-4541-a965-b9cd226c0eb2 |  | textbox | Date completed
checkpoint-group | 1153ad75-533c-490f-a063-eaf73841705a |  | section | Dispatch
checkpoint-status | 3c8ca705-d799-4de7-93a7-6fd2e77c509e |  | checkpoint | Panel ready for dispatch - Photo Required