## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 33a56314-b94f-4663-9774-6a726df57971 |  | checklist | ST - S - Punch Window Frames |  |  |  |  | Yes | ST - S - Punch Window Frames | 341e67b2-ade8-4d97-86a1-ad001493b78b
checkpoint-group | eee0c650-ac12-4dd3-9272-374d6266c571 |  | section | Glazing Install
checkpoint-no-status | 69d31234-4b3d-457f-b6a1-0e08d80f7680 |  | checkpoint | Glazing Install
label | 39d4b016-4427-5dd9-b5cd-6180dfcc1fd7 |  | note | Window # / Elevation / Level
checkpoint-status | 8da8c3eb-c640-4b53-979d-34521062605c |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status | bb1c40a0-e613-4904-b24e-860680e6a26c |  | checkpoint | Check the joinery is free from damage
checkpoint-status | baf6f344-84b1-4ff7-8aa9-d6bdf36d64f9 |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status | fd27ee29-8b3d-4169-aa7a-d531e2224fc8 |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status | 05ba92da-585e-4134-a762-c4e2bd6aff4c |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status | be0b06e1-cee6-4aae-9de4-5616591e87f3 |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status | 6ee176ef-b519-410f-88cc-7ffbf7039776 |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status | 7004447a-0270-47ba-b453-02285ea10a27 |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status | d09f6171-a844-4fc6-b4a6-19a2182f5c58 |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status | 9ccc8d4f-d522-4719-a0b5-4c1954567314 |  | checkpoint | Glass Stickers removed
checkpoint-status | b050d3d8-322e-4631-92c0-e721c9247f7a |  | checkpoint | Trade Clean
checkpoint-status | 677a2ff6-547b-49c8-8015-b881a277f506 |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status | fe3f38b5-8fe9-4347-9e1a-11f07a4f07a4 |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint | 5ef7c34f-b25e-4bca-981a-cf719863bb14 |  | signoff | Raise Remedial
checklist-sectioned | a079eab2-6985-45e4-a064-4fd29fbaed4e |  | checklist | 40mm Metro |  |  |  |  | Yes | 40mm Metro | f4178e5c-29ae-4a39-8fd5-72fcd9fed407
checkpoint-group | 078b0132-aca6-4111-95b9-a4a2d83a2afc |  | section | 40mm Metro
checkpoint-status | 7e4e87a5-87f9-40db-bf04-3a1aa0bdda85 |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint-status | 3ef96103-7e88-49e1-b7e7-dacc08570b4a |  | checkpoint | Setout/Grids/Datum Lines
checkpoint-status | 6b62f802-36f9-4ced-aa49-dfd2f24b2df1 |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint-status | f53edd29-ab99-4f7e-9fe9-7969703d80a2 |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint-status | ef677b2a-5690-44a3-8eb4-56045f7f1a36 |  | checkpoint | Airseals Completed
checkpoint-status | 7bac99a2-c5f6-46cc-b072-179b389dac6f |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint-status | 0edaffdc-3958-4369-ad65-8777d98a3b2b |  | checkpoint | Trade Clean
checkpoint-group | cd09190a-f54e-4f67-aa7b-c66055c87c90 |  | section | Sign Off
checkpoint-status | 66ae68b0-7d13-4f2b-aa1f-8132286874a5 |  | checkpoint | Wights - Sign Off