## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Project Overview
Scope
Rows
|  | FHC-ITP-001 - Subgrade Preparation | dynamic | FHC-ITP-001 - Subgrade Preparation
|  | FHC-ITP-003 - Track Placement | dynamic | FHC-ITP-003 - Track Placement
|  | FHC-ITP-004 - Concrete Track Slab Pour | dynamic | FHC-ITP-004 - Concrete Track Slab Pour
|  | FHC-ITP-005 - Subsurface Drainage | dynamic | FHC-ITP-005 - Subsurface Drainage
|  | FHC-ITP-006 - Kerb and Channel | dynamic | FHC-ITP-006 - Kerb and Channel
|  | FHC-ITP-007 - Structural Concrete Construction | dynamic | FHC-ITP-007 - Structural Concrete Construction
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | Date | Date Completed: | 1.1 Check for correct documentation
|  | Final Inspection |  | Final Inspection
|  | Print Name: | Print Name: | Final Inspection
|  | Position: | Position: | Final Inspection
|  | Date | Date: | Final Inspection
FHC-ITP-001 - Subgrade Preparation
| Scope |  |  | FHC-ITP-001 - Subgrade Preparation
Rows
|  | FHC-ITP-001 - Subgrade Preparation | dynamic | FHC-ITP-001 - Subgrade Preparation
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation | Preliminary Works
|  | Date | Date Completed: | 1.1 Check for correct documentation | Preliminary Works
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls | Preliminary Works
|  | Date | Date Completed: | 1.2 Implementation of all measures and controls | Preliminary Works
|  | 1.3 Selection and approval of Disposal Site |  | 1.3 Selection and approval of Disposal Site | Preliminary Works
|  | Date | Date Completed: | 1.3 Selection and approval of Disposal Site | Preliminary Works
|  | 2.1 Excavation |  | 2.1 Excavation | Construction Works
|  | Date | Date Completed: | 2.1 Excavation | Construction Works
|  | 2.2 Inspection of Subgrade Material |  | 2.2 Inspection of Subgrade Material | Construction Works
|  | Date | Date Completed: | 2.2 Inspection of Subgrade Material | Construction Works
|  | 2.3 Width and Level conformity |  | 2.3 Width and Level conformity | Construction Works
|  | Date | Date Completed: | 2.3 Width and Level conformity | Construction Works
|  | Final Inspection |  | Final Inspection | Construction Works
|  | Print Name: | Print Name: | Final Inspection | Construction Works
|  | Position: | Position: | Final Inspection | Construction Works
|  | Date | Date: | Final Inspection | Construction Works
FHC-ITP-003 - Track Placement
| Scope |  |  | FHC-ITP-003 - Track Placement
Rows
|  | FHC-ITP-003 - Track Placement | dynamic | FHC-ITP-003 - Track Placement
Columns
|  | 1.1 Check for Correct Documentation |  | 1.1 Check for Correct Documentation | Preliminary Works
|  | Date | Date Completed: | 1.1 Check for Correct Documentation | Preliminary Works
|  | 1.2 Check Materials |  | 1.2 Check Materials | Preliminary Works
|  | Date | Date Completed: | 1.2 Check Materials | Preliminary Works
|  | 1.3 Check Special Works Components |  | 1.3 Check Special Works Components | Preliminary Works
|  | Date | Date Completed: | 1.3 Check Special Works Components | Preliminary Works
|  | 1.4 Check Curved rail |  | 1.4 Check Curved rail | Preliminary Works
|  | Date | Date Completed: | 1.4 Check Curved rail | Preliminary Works
|  | 1.5 Welders Qualifications |  | 1.5 Welders Qualifications | Preliminary Works
|  | Date | Date Completed: | 1.5 Welders Qualifications | Preliminary Works
|  | 1.6 Ultrasonic Testers Qualifications |  | 1.6 Ultrasonic Testers Qualifications | Preliminary Works
|  | Date | Date Completed: | 1.6 Ultrasonic Testers Qualifications | Preliminary Works
|  | 2.1 Installation of Sleeper |  | 2.1 Installation of Sleeper | Construction Works
|  | Date | Date Completed: | 2.1 Installation of Sleeper | Construction Works
|  | 2.2 Placement of Rail |  | 2.2 Placement of Rail | Construction Works
|  | Date | Date Completed: | 2.2 Placement of Rail | Construction Works
|  | 2.3 Placement of Jewellery |  | 2.3 Placement of Jewellery | Construction Works
|  | Date | Date Completed: | 2.3 Placement of Jewellery | Construction Works
|  | 2.4 Rail End Preparation |  | 2.4 Rail End Preparation | Construction Works
|  | Date | Date Completed: | 2.4 Rail End Preparation | Construction Works
|  | 2.5 Welding of Rail |  | 2.5 Welding of Rail | Construction Works
|  | Date | Date Completed: | 2.5 Welding of Rail | Construction Works
|  | 2.6 Grinding & Cleaning Welds |  | 2.6 Grinding & Cleaning Welds | Construction Works
|  | Date | Date Completed: | 2.6 Grinding & Cleaning Welds | Construction Works
|  | 2.7 Track Adjustment |  | 2.7 Track Adjustment | Construction Works
|  | Date | Date Completed: | 2.7 Track Adjustment | Construction Works
|  | 2.8 Track Bonds |  | 2.8 Track Bonds | Construction Works
|  | Date | Date Completed: | 2.8 Track Bonds | Construction Works
|  | 3.1 Track Testing |  | 3.1 Track Testing | Testing
|  | Date | Date Completed: | 3.1 Track Testing | Testing
|  | Final Inspection |  | Final Inspection | Testing
|  | Print Name: | Print Name: | Final Inspection | Testing
|  | Position: | Position: | Final Inspection | Testing
|  | Date | Date: | Final Inspection | Testing
FHC-ITP-004 - Concrete Track Slab Pour
| Scope |  |  | FHC-ITP-004 - Concrete Track Slab Pour
Rows
|  | FHC-ITP-004 - Concrete Track Slab Pour | dynamic | FHC-ITP-004 - Concrete Track Slab Pour
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation | Preliminary Works
|  | Date | Date Completed: | 1.1 Check for correct documentation | Preliminary Works
|  | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project |  | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project | Preliminary Works
|  | Date | Date Completed: | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project | Preliminary Works
|  | 2.1 Weather Monitoring |  | 2.1 Weather Monitoring | Construction Works
|  | Date | Date Completed: | 2.1 Weather Monitoring | Construction Works
|  | 2.2 Surface Preperation |  | 2.2 Surface Preperation | Construction Works
|  | Date | Date Completed: | 2.2 Surface Preperation | Construction Works
|  | 2.3 Setting Out |  | 2.3 Setting Out | Construction Works
|  | Date | Date Completed: | 2.3 Setting Out | Construction Works
|  | 2.4 Formwork |  | 2.4 Formwork | Construction Works
|  | Date | Date Completed: | 2.4 Formwork | Construction Works
|  | 2.5 Reinforcement |  | 2.5 Reinforcement | Construction Works
|  | Date | Date Completed: | 2.5 Reinforcement | Construction Works
|  | 2.6 Dowels |  | 2.6 Dowels | Construction Works
|  | Date | Date Completed: | 2.6 Dowels | Construction Works
|  | 2.7 Pre Pour Inspection |  | 2.7 Pre Pour Inspection | Construction Works
|  | Date | Date Completed: | 2.7 Pre Pour Inspection | Construction Works
|  | 2.8 Carry out sampling of concrete |  | 2.8 Carry out sampling of concrete | Construction Works
|  | Date | Date Completed: | 2.8 Carry out sampling of concrete | Construction Works
|  | 2.9 Concrete Placement |  | 2.9 Concrete Placement | Construction Works
|  | Date | Date Completed: | 2.9 Concrete Placement | Construction Works
|  | 2.10 Compaction |  | 2.10 Compaction | Construction Works
|  | Date | Date Completed: | 2.10 Compaction | Construction Works
|  | 2.11 Record location of each batch |  | 2.11 Record location of each batch | Construction Works
|  | Date | Date Completed: | 2.11 Record location of each batch | Construction Works
|  | 2.12 Curing |  | 2.12 Curing | Construction Works
|  | Date | Date Completed: | 2.12 Curing | Construction Works
|  | 2.13 Tolerances |  | 2.13 Tolerances | Construction Works
|  | Date | Date Completed: | 2.13 Tolerances | Construction Works
|  | 2.14 Slab finish |  | 2.14 Slab finish | Construction Works
|  | Date | Date Completed: | 2.14 Slab finish | Construction Works
|  | 2.15 Post Pour Inspection |  | 2.15 Post Pour Inspection | Construction Works
|  | Date | Date Completed: | 2.15 Post Pour Inspection | Construction Works
|  | Final Inspection |  | Final Inspection | Construction Works
|  | Print Name: | Print Name: | Final Inspection | Construction Works
|  | Position: | Position: | Final Inspection | Construction Works
|  | Date | Date: | Final Inspection | Construction Works
FHC-ITP-005 - Subsurface Drainage
| Scope |  |  | FHC-ITP-005 - Subsurface Drainage
Rows
|  | FHC-ITP-005 - Subsurface Drainage | dynamic | FHC-ITP-005 - Subsurface Drainage
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation | Preliminary Works
|  | Date | Date Completed: | 1.1 Check for correct documentation | Preliminary Works
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls | Preliminary Works
|  | Date | Date Completed: | 1.2 Implementation of all measures and controls | Preliminary Works
|  | 1.3 Placement of no fines concrete |  | 1.3 Placement of no fines concrete | Preliminary Works
|  | Date | Date Completed: | 1.3 Placement of no fines concrete | Preliminary Works
|  | 1.4 Material Classification |  | 1.4 Material Classification | Preliminary Works
|  | Date | Date Completed: | 1.4 Material Classification | Preliminary Works
|  | 2.1 Excavation Permit |  | 2.1 Excavation Permit | Construction Works
|  | Date | Date Completed: | 2.1 Excavation Permit | Construction Works
|  | 2.2 Excavation of Trench |  | 2.2 Excavation of Trench | Construction Works
|  | Date | Date Completed: | 2.2 Excavation of Trench | Construction Works
|  | 2.3 Placement of bedding |  | 2.3 Placement of bedding | Construction Works
|  | Date | Date Completed: | 2.3 Placement of bedding | Construction Works
|  | 2.4 Placing pipes and geofabric (if required) |  | 2.4 Placing pipes and geofabric (if required) | Construction Works
|  | Date | Date Completed: | 2.4 Placing pipes and geofabric (if required) | Construction Works
|  | 2.5 Placement of backfill |  | 2.5 Placement of backfill | Construction Works
|  | Date | Date Completed: | 2.5 Placement of backfill | Construction Works
|  | 2.6 Install Pits and Flushouts |  | 2.6 Install Pits and Flushouts | Construction Works
|  | Date | Date Completed: | 2.6 Install Pits and Flushouts | Construction Works
|  | Final Inspection |  | Final Inspection | Construction Works
|  | Print Name: | Print Name: | Final Inspection | Construction Works
|  | Position: | Position: | Final Inspection | Construction Works
|  | Date | Date: | Final Inspection | Construction Works
FHC-ITP-006 - Kerb and Channel
| Scope |  |  | FHC-ITP-006 - Kerb and Channel
Rows
|  | FHC-ITP-006 - Kerb and Channel | dynamic | FHC-ITP-006 - Kerb and Channel
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation | Preliminary Works
|  | Date | Date Completed: | 1.1 Check for correct documentation | Preliminary Works
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls | Preliminary Works
|  | Date | Date Completed: | 1.2 Implementation of all measures and controls | Preliminary Works
|  | 2.1 Setting Out |  | 2.1 Setting Out | Construction Works
|  | Date | Date Completed: | 2.1 Setting Out | Construction Works
|  | 2.2 Temporary Drainage Provisions |  | 2.2 Temporary Drainage Provisions | Construction Works
|  | Date | Date Completed: | 2.2 Temporary Drainage Provisions | Construction Works
|  | 2.3 Bedding |  | 2.3 Bedding | Construction Works
|  | Date | Date Completed: | 2.3 Bedding | Construction Works
|  | 2.4 Pre-concrete check |  | 2.4 Pre-concrete check | Construction Works
|  | Date | Date Completed: | 2.4 Pre-concrete check | Construction Works
|  | 2.5 Concrete Placement |  | 2.5 Concrete Placement | Construction Works
|  | Date | Date Completed: | 2.5 Concrete Placement | Construction Works
|  | 2.6 Finish Surfaces |  | 2.6 Finish Surfaces | Construction Works
|  | Date | Date Completed: | 2.6 Finish Surfaces | Construction Works
|  | 2.7 Tolerances |  | 2.7 Tolerances | Construction Works
|  | Date | Date Completed: | 2.7 Tolerances | Construction Works
|  | 2.8 Joints |  | 2.8 Joints | Construction Works
|  | Date | Date Completed: | 2.8 Joints | Construction Works
|  | 2.9 Backfilling |  | 2.9 Backfilling | Construction Works
|  | Date | Date Completed: | 2.9 Backfilling | Construction Works
|  | Final Inspection |  | Final Inspection | Construction Works
|  | Print Name: | Print Name: | Final Inspection | Construction Works
|  | Position: | Position: | Final Inspection | Construction Works
|  | Date | Date: | Final Inspection | Construction Works
FHC-ITP-007 - Structural Concrete Construction
| Scope |  |  | FHC-ITP-007 - Structural Concrete Construction
Rows
|  | FHC-ITP-007 - Structural Concrete Construction | dynamic | FHC-ITP-007 - Structural Concrete Construction
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation | Design and Submissions
|  | Date | Date Completed: | 1.1 Check for correct documentation | Design and Submissions
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls | Design and Submissions
|  | Date | Date Completed: | 1.2 Implementation of all measures and controls | Design and Submissions
|  | 1.3 Approval of mix design |  | 1.3 Approval of mix design | Design and Submissions
|  | Date | Date Completed: | 1.3 Approval of mix design | Design and Submissions
|  | 1.4 Reinforcement schedule |  | 1.4 Reinforcement schedule | Design and Submissions
|  | Date | Date Completed: | 1.4 Reinforcement schedule | Design and Submissions
|  | 2.1 Excavation |  | 2.1 Excavation | Construction/Erection of Formwork
|  | Date | Date Completed: | 2.1 Excavation | Construction/Erection of Formwork
|  | 2.2 Construction Methodology |  | 2.2 Construction Methodology | Construction/Erection of Formwork
|  | Date | Date Completed: | 2.2 Construction Methodology | Construction/Erection of Formwork
|  | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete |  | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete | Pre-Pour Planning and Inspection
|  | Date | Date Completed: | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete | Pre-Pour Planning and Inspection
|  | 3.2 Formwork levels and position |  | 3.2 Formwork levels and position | Pre-Pour Planning and Inspection
|  | Date | Date Completed: | 3.2 Formwork levels and position | Pre-Pour Planning and Inspection
|  | 3.3 Location of splices |  | 3.3 Location of splices | Pre-Pour Planning and Inspection
|  | Date | Date Completed: | 3.3 Location of splices | Pre-Pour Planning and Inspection
|  | 3.4 Cleaning formwork |  | 3.4 Cleaning formwork | Pre-Pour Planning and Inspection
|  | Date | Date Completed: | 3.4 Cleaning formwork | Pre-Pour Planning and Inspection
|  | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments |  | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments | Pre-Pour Planning and Inspection
|  | Date | Date Completed: | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments | Pre-Pour Planning and Inspection
|  | 3.6 Monitoring weather |  | 3.6 Monitoring weather | Pre-Pour Planning and Inspection
|  | Date | Date Completed: | 3.6 Monitoring weather | Pre-Pour Planning and Inspection
|  | 4.1 Carry out sampling of concrete |  | 4.1 Carry out sampling of concrete | Placing and Finishing Concrete
|  | Date | Date Completed: | 4.1 Carry out sampling of concrete | Placing and Finishing Concrete
|  | 4.2 Discharge time |  | 4.2 Discharge time | Placing and Finishing Concrete
|  | Date | Date Completed: | 4.2 Discharge time | Placing and Finishing Concrete
|  | 4.3 Methodology of placement (structural) |  | 4.3 Methodology of placement (structural) | Placing and Finishing Concrete
|  | Date | Date Completed: | 4.3 Methodology of placement (structural) | Placing and Finishing Concrete
|  | 5.1 Curing |  | 5.1 Curing | Post-Pour Details and Inspection
|  | Date | Date Completed: | 5.1 Curing | Post-Pour Details and Inspection
|  | 5.2 Formwork removal |  | 5.2 Formwork removal | Post-Pour Details and Inspection
|  | Date | Date Completed: | 5.2 Formwork removal | Post-Pour Details and Inspection
|  | 5.3 Positional tolerance and dimensions of concrete members and piles |  | 5.3 Positional tolerance and dimensions of concrete members and piles | Post-Pour Details and Inspection
|  | Date | Date Completed: | 5.3 Positional tolerance and dimensions of concrete members and piles | Post-Pour Details and Inspection
|  | 5.4 Concrete Sampling and Testing |  | 5.4 Concrete Sampling and Testing | Post-Pour Details and Inspection
|  | Date | Date Completed: | 5.4 Concrete Sampling and Testing | Post-Pour Details and Inspection
|  | 5.5 As Built Drawings |  | 5.5 As Built Drawings | Post-Pour Details and Inspection
|  | Date | Date Completed: | 5.5 As Built Drawings | Post-Pour Details and Inspection
|  | Final Inspection |  | Final Inspection | Post-Pour Details and Inspection
|  | Print Name: | Print Name: | Final Inspection | Post-Pour Details and Inspection
|  | Position: | Position: | Final Inspection | Post-Pour Details and Inspection
|  | Date | Date: | Final Inspection | Post-Pour Details and Inspection