## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Project Overview
Scope
Rows
|  | ITP-001 - Clearing & Grubbing | dynamic | ITP-001 - Clearing & Grubbing
|  | ITP-002 - Stripping Topsoil & Topsoil Placement | dynamic | ITP-002 - Stripping Topsoil & Topsoil Placement
|  | ITP-003 - Subgrade Preparation | dynamic | ITP-003 - Subgrade Preparation
|  | ITP-004 - Type A Fill Placement | dynamic | ITP-004 - Type A Fill Placement
|  | ITP-005 - Sub-Base Construction Class 2 | dynamic | ITP-005 - Sub-Base Construction Class 2
|  | ITP-006 - Sub-Base Construction Class 3 | dynamic | ITP-006 - Sub-Base Construction Class 3
|  | ITP-008 - Stormwater Drainage | dynamic | ITP-008 - Stormwater Drainage
|  | ITP-012 - Hot Mix Asphalt | dynamic | ITP-012 - Hot Mix Asphalt
|  | ITP-014 - Subsurface Drainage | dynamic | ITP-014 - Subsurface Drainage
|  | ITP-015 - Kerb and Channel | dynamic | ITP-015 - Kerb and Channel
|  | ITP-019 - Line Marking | dynamic | ITP-019 - Line Marking
|  | ITP-027 - Pile Footing Construction | dynamic | ITP-027 - Pile Footing Construction
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | Date | Date Completed: | 1.1 Check for correct documentation
|  | 1.1 The current revision drawings/documents are being used including subcontractors copy. |  | 1.1 The current revision drawings/documents are being used including subcontractors copy.
|  | Date | Date Completed: | 1.1 The current revision drawings/documents are being used including subcontractors copy.
|  | 1.1 Submission of Mix Design |  | 1.1 Submission of Mix Design
|  | Date | Date Completed: | 1.1 Submission of Mix Design
|  | Final Inspection |  | Final Inspection
|  | Name | Print Name: | Final Inspection
|  | Position | Position: | Final Inspection
|  | Date | Date: | Final Inspection
ITP-001 - Clearing & Grubbing
| Scope |  |  | ITP-001 - Clearing & Grubbing
Rows
|  | ITP-001 - Clearing & Grubbing |  | ITP-001 - Clearing & Grubbing
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation | Preliminary Works
|  | Date | Date Completed: | 1.1 Check for correct documentation | Preliminary Works
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls | Preliminary Works
|  | Date | Date Completed: | 1.2 Implementation of all measures and controls | Preliminary Works
|  | 1.3 Flora & Fauna |  | 1.3 Flora & Fauna | Preliminary Works
|  | Date | Date Completed: | 1.3 Flora & Fauna | Preliminary Works
|  | 1.4 Permit to distrurb flora & fauna |  | 1.4 Permit to distrurb flora & fauna | Preliminary Works
|  | Date | Date Completed: | 1.4 Permit to distrurb flora & fauna | Preliminary Works
|  | 2.1 Define work area |  | 2.1 Define work area | Clear & Grub
|  | Date | Date Completed: | 2.1 Define work area | Clear & Grub
|  | 2.2 Joint Inspection to Mark vegetation or habitat to be removed |  | 2.2 Joint Inspection to Mark vegetation or habitat to be removed | Clear & Grub
|  | Date | Date Completed: | 2.2 Joint Inspection to Mark vegetation or habitat to be removed | Clear & Grub
|  | 2.3 Identify No-go Zones |  | 2.3 Identify No-go Zones | Clear & Grub
|  | Date | Date Completed: | 2.3 Identify No-go Zones | Clear & Grub
|  | 2.4 Clear felling distances of trees are adequate. |  | 2.4 Clear felling distances of trees are adequate. | Clear & Grub
|  | Date | Date Completed: | 2.4 Clear felling distances of trees are adequate. | Clear & Grub
|  | 2.5 Clear and grub trees and vegetation |  | 2.5 Clear and grub trees and vegetation | Clear & Grub
|  | Date | Date Completed: | 2.5 Clear and grub trees and vegetation | Clear & Grub
|  | 2.6 Backfill holes |  | 2.6 Backfill holes | Clear & Grub
|  | Date | Date Completed: | 2.6 Backfill holes | Clear & Grub
|  | 2.7 Dispose of Trees and vegetation |  | 2.7 Dispose of Trees and vegetation | Clear & Grub
|  | Date | Date Completed: | 2.7 Dispose of Trees and vegetation | Clear & Grub
|  | 2.8 Dispose of concrete, bituminous and other recyclable materials. |  | 2.8 Dispose of concrete, bituminous and other recyclable materials. | Clear & Grub
|  | Date | Date Completed: | 2.8 Dispose of concrete, bituminous and other recyclable materials. | Clear & Grub
|  | Final Inspection |  | Final Inspection | Clear & Grub
|  | Name | Print Name: | Final Inspection | Clear & Grub
|  | Position | Position: | Final Inspection | Clear & Grub
|  | Date | Date: | Final Inspection | Clear & Grub
ITP-002 - Stripping Topsoil & Topsoil Placement
| Scope |  |  | ITP-002 - Stripping Topsoil & Topsoil Placement
Rows
|  | ITP-002 - Stripping Topsoil & Topsoil Placement |  | ITP-002 - Stripping Topsoil & Topsoil Placement
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation | Preliminary Works
|  | Date | Date Completed: | 1.1 Check for correct documentation | Preliminary Works
|  | 1.2 Implementation of all measures and controls |  | 1.2 Implementation of all measures and controls | Preliminary Works
|  | Date | Date Completed: | 1.2 Implementation of all measures and controls | Preliminary Works
|  | 1.3 Ensure correct materials are being used |  | 1.3 Ensure correct materials are being used | Preliminary Works
|  | Date | Date Completed: | 1.3 Ensure correct materials are being used | Preliminary Works
|  | 2.1 Survey Set Out |  | 2.1 Survey Set Out | Stripping Topsoil
|  | Date | Date Completed: | 2.1 Survey Set Out | Stripping Topsoil
|  | 2.2 Archaeological monitoring |  | 2.2 Archaeological monitoring | Stripping Topsoil
|  | Date | Date Completed: | 2.2 Archaeological monitoring | Stripping Topsoil
|  | 2.3 Excavation Permit |  | 2.3 Excavation Permit | Stripping Topsoil
|  | Date | Date Completed: | 2.3 Excavation Permit | Stripping Topsoil
|  | 2.4 Designation of stock pile area or disposal site |  | 2.4 Designation of stock pile area or disposal site | Stripping Topsoil
|  | Date | Date Completed: | 2.4 Designation of stock pile area or disposal site | Stripping Topsoil
|  | 2.5 Weed treatment |  | 2.5 Weed treatment | Stripping Topsoil
|  | Date | Date Completed: | 2.5 Weed treatment | Stripping Topsoil
|  | 2.6 Maintenance of stockpiles |  | 2.6 Maintenance of stockpiles | Stripping Topsoil
|  | Date | Date Completed: | 2.6 Maintenance of stockpiles | Stripping Topsoil
|  | 3.1 Surface finish of cut and fill batters |  | 3.1 Surface finish of cut and fill batters | Placing Topsoil
|  | Date | Date Completed: | 3.1 Surface finish of cut and fill batters | Placing Topsoil
|  | 3.2 Topsoil Placement |  | 3.2 Topsoil Placement | Placing Topsoil
|  | Date | Date Completed: | 3.2 Topsoil Placement | Placing Topsoil
|  | 3.3 Surface level |  | 3.3 Surface level | Placing Topsoil
|  | Date | Date Completed: | 3.3 Surface level | Placing Topsoil
|  | Final Inspection |  | Final Inspection | Placing Topsoil
|  | Name | Print Name: | Final Inspection | Placing Topsoil
|  | Position | Position: | Final Inspection | Placing Topsoil
|  | Date | Date: | Final Inspection | Placing Topsoil