## ITC 019
ITC 019 - DE-ENERGISED ISOLATOR/CIRCUIT BREAKER FUNCTIONALITY TEST MAIN SWITCHBOARD
Referenced Drawing and Revision Number |  | text box
Inspection Conditions: Ensure all steps are completed in order.
Equipment number: |  | text box |  |  | Rating: | text box |  | Type: |  | text box |  | Manufacturer: |  | text box
Interlock type: |  | text box
STEP 1 | Open cubicle and undertake a visual inspection | [10 empty] | Yes/ No
STEP 2 | Verify the settings against the single line and the cubicle door | [10 empty] | Yes/ No
STEP 3 | Verification of circuit contacts in Closed Position
Switch Closed | A to E | B to E |  | C to E | A to B | A to C | C to B |  | A to A |  | B to B | C to C | A to N |  | B to N | C to N | N to N
| pass/ fail | pass/ fail |  | pass/ fail | pass/ fail | pass/ fail | pass/ fail |  | pass/ fail |  | pass/ fail | pass/ fail | pass/ fail |  | pass/ fail | pass/ fail | pass/fail
STEP 4 | Verification of circuit contacts in Open Position | [10 empty] | 0
Switch Open | A to E | B to E |  | C to E | A to B | A to C | C to B |  | A to A |  | B to B | C to C | A to N |  | B to N | C to N | N to N
| pass/ fail | pass/ fail |  | pass/ fail | pass/ fail | pass/ fail | pass/ fail |  | pass/ fail |  | pass/ fail | pass/ fail | pass/ fail |  | pass/ fail | pass/ fail | pass/fail
STEP 5 | Visually confirm circuit breaker is in the open position | [12 empty] | Yes/ No
STEP 6 | Visually confirm the door interlock is in the open position and immediately close the cubicle. | [12 empty] | Yes/ No
STEP 7 | Re-confirm the operating mechanism in the open position. | [12 empty] | Yes/ No
STEP 8 | Prove operation of the interlocking device. | [12 empty] | Pass/ Fail
STEP 9 | Document the status of circuit breaker. | [12 empty] | Open / Closed
Test Equipment Type |  |  | Brand/Model |  |  | Serial No. |  |  | Calibration Due
text box |  |  | text box |  |  | text box |  |  | text box
text box |  |  | text box |  |  | text box |  |  | text box
The electricians noted above, working for Grid Electrical Services Pty Ltd, certify that the above inspections/ tests beside their name, has been verified/ tested to ensure it is electrically safe and in accordance with the relevant wiring rules and any other standard applying to the electrical installation under the Electrical Safety Act of that particular State/ Territory at the date the inspection/ test was completed.
FINAL ACCEPTANCE:
final acceptance - email