## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-286-CIV-ADL-Unbound Flexible Pavement-Scale C | itp |  |  |  |  | ITP-286-CIV-ADL-Unbound Flexible Pavement-Scale C Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-286-CIV- ADL-Unbound Flexible Pavement-Scale C
label | ITP Description: ADL-Unbound Flexible Pavement-Scale C
label | Discipline (e.g. CIV/STR/RAIL): 286-CIV-
label | Revision Number: 0
label | Revision Date: 20/06/2025
label | ITP created by: Abhi Patil
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 - Non Dependent
label | Reference - Reference Documents: IFC Drawings
label | 1.2 -
label | Reference - VicRoads Section 173
label | 1.3 -
label | Reference - VicRoads Section 304
label | 1.4 -
label | Reference - VicRoads Section 801
label | 1.5 -
label | Reference - VicRoads Section 812
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Crushed Rock Mix Design
label | Reference - Section 304.04, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
label | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Material conformance as per Table 812.121
label | Category - HP*
label | Responsibility - NA
label | Verifying Documents - TeamBinder Material Approval Number
date | Date Completed:
section | 3. Preliminaries-Documentation
checkpoint | 3.1 - Subgrade Preparation
label | Reference - 304.05
label | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
textbox | Enter Subgrade Lot No:
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - Underlying layer Lot number
date | Date Completed:
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-out and Lot size
label | Reference - IFC Drawings Section 304.07
label | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
label | ○ Clearly mark out limits of works as per IFC Drawings and VR 304.07.
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | Method - Survey, Document Review, Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Surveyor, SE
label | Verifying Documents - Sign ITP
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Placement of Material
label | Reference - Section 304.08
label | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | Method - Visual and Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.2 - Construction - Jointing
label | Reference - Section 304.08
label | Acceptance Criteria - The layout of joints shall conform to the following requirements:
label | (a) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (b) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (c) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (d) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | Method - Visual and Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.3 - Compaction test (Frequency)
label | Reference - 304 .09 (b)
label | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | ○ Scale C: 3 samples
textbox | Enter: last tested lot number
label | Method - Visual
label | Frequency - Each Lot Where applicxable
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.4 - Post Compaction Materials Testing (Frequency)
label | Reference - 304.11
label | Acceptance Criteria - SCALE C: Atterberg Limits and Grading
label | Method - Visual
label | Frequency - Each Lot Where applicxable
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.5 - Proof Roll
label | Reference - Section 304.09
label | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | Method - Visual
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Sign ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Protection of compacted layer
label | Reference - Section 304.10
label | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | Method - Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - Compaction Testing (results)
label | Reference - Section 173, Section 304.09 Table 304.091
label | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
label | ○ Scale C:
label | — Subbase Layer CDR ≥ 98%
label | — Base Layer CDR ≥ 100%
label | ○ 3 tests per lot
label | ○ ATTACH: Compaction Test Results
label | Method - Document Review
label | Frequency - Each Lot Where applicxable
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - Compaction Test Rersults
date | Date Completed:
checkpoint | 6.2 - Post Compaction Materials Testing (Results)
label | Reference - Section 304.10, Section 304.11 RC 500.02
label | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | 20mm Class 3:
label | Grading
label | ○ 26.5mm 100%
label | ○ 19.0mm 95-100%
label | ○ 13.2mm 75-95%
label | ○ 9.5mm 60-90%
label | ○ 4.75mm 42-76%
label | ○ 2.36mm 28-61%
label | ○ 0.425mm 14-29%
label | ○ 0.075mm 6-14%
label | PI between 0 to 10
label | 20mm Class 4:
label | Grading
label | ○ 26.5mm 100%
label | ○ 4.75mm 42-76%
label | ○ 0.425mm 10-28%
label | ○ 0.075mm 2-14%
label | ○ PI between 0 to 20
label | ○ PI x % passing 0.425 mm sieve (max) 450
label | Scale C: Post compaction material testing is not required (Choose NA)
label | Method - Document Review
label | Frequency - Each Lot Where applicable
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - Compaction Test Rersults
date | Date Completed:
checkpoint | 6.3 - Survey As-Built - Width and alignment
label | Reference - 304.07 (a)
label | Acceptance Criteria - The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
label | ○ Attach: Survey Report
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/Surveyor
label | Verifying Documents - Survey Conformance Report
date | Date Completed:
checkpoint | 6.4 - Survey As-Built Thickness of Pavement Layers - CARPARK PAVEMENT
label | Reference - 304.07 (c )
label | Acceptance Criteria - Subbase course shall be not less than the specified thickness by more than 15 mm.
label | ○ Base Course shall be not less than the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be less than specified thickness.
label | ○ The combined thickness of subbase and base courses shall be not be less than the specified thickness by more than 15 mm.
label | ○ Attach: Survey Report
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/Surveyor
label | Verifying Documents - Survey Conformance Report
date | Date Completed:
checkpoint | 6.5 - Survey As-Built - Surface Level - MAIN ALIGNMENT ONLY
label | Reference - IFC Drawings Section 304.07 (b), VR 304.07 (d) Table 304.071, Table 304.072
label | Acceptance Criteria - - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | — At no location shall water pond on the surface of any pavement layer.
label | ○ Scale B: A minimum of 40 measurements per lot
label | ○ Subbase: mean range +8mm to -16mm, maximum Standard Deviation of 15mm
label | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | ○ Attach: Survey Report
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/Surveyor
label | Verifying Documents - Survey Conformance Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP