## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-258-CIV-HOP-Behind Structure Drainage
ITP Description: |  | HOP-Behind Structure Drainage
Discipline (e.g. CIV/STR/RAIL: |  | 258-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-06-24
ITP created by: |  | Cedric Guico
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Hopkins Road
Inspection & Test Plan - Installation of Drainage Behind the Structure
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-06-24
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 702 (May '19) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
Non Dependent
2 | Preliminaries-Material
2.1 | Megaflow | IFC Drawiings | Product as required on IFC drawings [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.2 | Pipes | IFC Drawiings VR 702.04 | All subsurface drainage shall be Category 1, 100mm dia. Class 1000 PVC pipe . [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.3 | Perforated Pipes | IFC Drawiings VR 702.05 | All subsurface drainage shall be Category 1, 100mm dia. Class 1000 PVC pipe . Perforations shall be max 1.5mm and minimum length of 150mm per sqm [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.4 | Granular backfill material | IFC Drawings VR 702.05 | The granular backfill material passing a 4.75 mm AS sieve shall have a Sand Equivalent value not less than 80. Shall comply with Table 702.051 [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.5 | Tamseal | IFC Drawings | Tamseal 10GM high performance elastometric liquid membrane [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.6 | Geo textile | IFC Drawings VR 702.06 | Geotextiles: Shall comply with table 702.061 and the IFC drawings [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.7 | Drainmat with geotextile fabric | IFC Drawings VR 702.06 | The Drainmat with geotextile shall comply with table 702.061 and the IFC drawings omply with table 702.061 and the IFC drawings [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
2.8 | Blinding Concrete | IFC Drawings | Blinding Concrete [Text Box]:Reference: Material approval in Teambinder: | Verify, Document Review | When applicable | HP | Nominated Authority | Material approval in TeamBinder This ITP signed off by Nominated Authority
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set Out | Section 702.03 | Survey to set out Subsurface Drainage line. | Visual inspection | Each Lot | HP* | SE/Site Supervisor | This ITP
4 | Construction / Installation Activities
4.1 | Placing Blinding Concrete | IFC Drawings | Minimum 50mm thick blinding concrete | Visual inspection | Each lot | IP | SE | This ITP
4.2 | Application of Tamseal | IFC Drawings | A 2mm thick target dry film to be sprayed in accordance with manufacturers' specifications. | Visual inspection | Each lot | IP | SE | This ITP
4.3 | Placing the Geotextile behind the wall | Section 702.07 | Placing the geotextile filter fabric such a system shall be placed over the full height of fill which is in contact with the structure | Visual Inspection | Each lot | HP | SE/Nominated Authority | Nominated Authorith sign off ThisLine
4.4 | Placing the Megaflow with granular backfill | Section 702.09 IFC Drawings | Megaflow shall be placed centrally in the granular backfill such that the megaflow stands vertical, and held firmly in place. The grade of the megaflow shall be not flatter than 1 in 250. | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP
4.5 | Placing the verical pipes | IFC Drawings | Vertical pipes to be installed as per IFC drawings | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP
4.6 | Placing the slotted pipe | Section 702.09 IFC Drawings SD 1601 | Slotted pipes shal lbe installed as per IFC drawings | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP
4.7 | Installing drainmat | IFC drawings | The drainmat should placed along the verticle wall and ensure it is firmly fixed and no movement happen while placing material. Whenever the drainmat laps, a overlap length of minimum 75mm should be kept. At the top of the drainmat the fabric must either be turned over the core or secured against the wall using tape to prevent ingress of soil into the core | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP
5 | Post-construction / Post-installation Activities
5.1 | As Built Information | Section 702.03 | The invert of the sursurface drainage pipe or the megaflow shall not be more than 25mm from the specified level and not more than 50mm from the specified line Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length | Document Review | Each lot | IP | Surveyor SE/PE/SPE | Attach Survey Conformance Report
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /
Note on D26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @KANKANAMGE, Dhanuka Can you please insert from VR702 the requirements