## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-287-CIV-HOP-Behind Structure Drainage Megaflow | itp |  |  |  |  | ITP-287-CIV-HOP-Behind Structure Drainage Megaflow Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-258-CIV-HOP-Behind Structure Drainage
label | ITP Description: HOP-Behind Structure Drainage
label | Discipline (e.g. CIV/STR/RAIL): 258-CIV
label | Revision Number: 0
label | Revision Date: 24/06/2025
label | ITP created by: Cedric Guico
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 702 (May '19)
section | 2. Preliminaries-Material
checkpoint | 2.1 - Megaflow
label | Reference - IFC Drawiings
label | Acceptance Criteria - Product as required on IFC drawings
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Pipes
label | Reference - IFC Drawiings VR 702.04
label | Acceptance Criteria - All subsurface drainage shall be Category 1, 100mm dia. Class 1000 PVC pipe.
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Perforated Pipes
label | Reference - IFC Drawiings VR 702.05
label | Acceptance Criteria - All subsurface drainage shall be Category 1, 100mm dia. Class 1000 PVC pipe . Perforations shall be max 1.5mm and minimum length of 150mm per sqm
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Granular backfill material
label | Reference - IFC Drawings VR 702.05
label | Acceptance Criteria - The granular backfill material passing a 4.75 mm AS sieve shall have a Sand Equivalent value not less than 80.
label | ○ Shall comply with Table 702.051
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Tamseal
label | Reference - IFC Drawings
label | Acceptance Criteria - Tamseal 10GM high performance elastometric liquid membrane
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Geo textile
label | Reference - IFC Drawings VR 702.06
label | Acceptance Criteria - Geotextiles:
label | ○ Shall comply with table 702.061 and the IFC drawings
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Drainmat with geotextile fabric
label | Reference - IFC Drawings VR 702.06
label | Acceptance Criteria - The Drainmat with geotextile shall comply with table 702.061 and the IFC drawings
label | ○ Comply with table 702.061 and the IFC drawings
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Blinding Concrete
label | Reference - IFC Drawings
label | Acceptance Criteria - Blinding Concrete
textbox | Reference: Material approval in Teambinder:
label | Method - Verify, Document Review
label | Frequency - When applicable
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set Out
label | Reference - Section 702.03
label | Acceptance Criteria - Survey to set out Subsurface Drainage line.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Placing Blinding Concrete
label | Reference - IFC Drawings
label | Acceptance Criteria - Minimum 50mm thick blinding concrete
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Application of Tamseal
label | Reference - IFC Drawings
label | Acceptance Criteria - A 2mm thick target dry film to be sprayed in accordance with manufacturers' specifications.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Placing the Geotextile behind the wall
label | Reference - Section 702.07
label | Acceptance Criteria - Placing the geotextile filter fabric such a system shall be placed over the full height of fill which is in contact with the structure
label | Method - Visual Inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Nominated Authorith sign off ThisLine
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Placing the Megaflow with granular backfill
label | Reference - Section 702.09 IFC Drawings
label | Acceptance Criteria - Megaflow shall be placed centrally in the granular backfill such that the megaflow stands vertical, and held firmly in place. The grade of the megaflow shall be not flatter than 1 in 250.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.5 - Placing the verical pipes
label | Reference - IFC Drawings
label | Acceptance Criteria - Vertical pipes to be installed as per IFC drawings
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.6 - Placing the slotted pipe
label | Reference - Section 702.09 IFC Drawings SD 1601
label | Acceptance Criteria - Slotted pipes shal lbe installed as per IFC drawings
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.7 - Installing drainmat
label | Reference - IFC drawings
label | Acceptance Criteria - The drainmat should placed along the verticle wall and ensure it is firmly fixed and no movement happen while placing material.
label | ○ Whenever the drainmat laps, a overlap length of minimum 75mm should be kept.
label | ○ At the top of the drainmat the fabric must either be turned over the core or secured against the wall using tape to prevent ingress of soil into the core
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-construction / Post-installation Activities
checkpoint | 5.1 - As Built Information
label | Reference - Section 702.03
label | Acceptance Criteria - The invert of the sursurface drainage pipe or the megaflow shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Attach Survey Conformance Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP