## ITP Rev 1
INSPECTION & TEST PLAN
Client: |  | South Taranaki District Council |  |  |  | SCCL Job Number |  |  | ITP Number |  | Client Job Number
[6 empty] | 2025/010 |  |  | 32 |  | Contract No. 25/02
Description: |  | South Taranaki Road Maintenance on Unsealed Roads 2025 - 2028 |  |  |  | Prepared By |  | ITP Revision |  | ITP Date | Code(s)
[6 empty] | Kendall Hale |  | 1 |  | 2025-02-03 | NZTA TQS2:2005
Abbreviations: |  | H = Hold W = Witness R = Review I = Inspection M = Monitor |  | SCCL = Superior Civil Construction Ltd E = Engineer CM = Contracts Manager SUP = Supervisor S = Storeman OP = Operator QA = Quality Manager STMS = Traffic Manager
Hold: Work may not proceed past the hold point without the party imposing the hold point attendance to witness the activity. Witness: An inspection point which will be witnessed or verified. Review: Documentation to be reviewed and approved. Inspection: A formal inspection activity to be undertaken and a report produced. Monitor: An activity which is subject to ongoing monitoring.
Road Name: | [5 empty] | RP Number From: |  |  |  |  | RP Number To:
SEQ NO | TASK | RESPONSIBILITY | INSPECTION FUNCTION | APPLICABLE DOCUMENTS | INSP FREQ | INSPECTOR / RESULT
[6 empty] | SCCL | SCCL SIGN | Engineer | E SIGN | COMMENTS
DOCUMENT REVIEW
1 | Receive work scope and review documents | SCCL | Check contract documents and drawings, note test and inspection requirements, build contract specific test and quality plan. | Contract Documents NZS 3910:2013, Contract Specifications TNZ Specifications | 100% | QA, H |  | R
2 | Submit ITP & Quality Plan for client approval | SCCL | STDC and Engineer to review and approve | Contract Documents NZS 3910:2013, Contract Specifications, TNZ Specifications | 100% | QA, H |  | R
Establishment and material supply
3 | Maintenance Programme | SCCL | Discuss maintenance requirments and Programme roads, as directed by contract engineer | Contract Documents, Specifications and Drawings, Programme | Prior to commencing work | QA, SUP, E H, R, M, W |  | H, R, M
4 | Site Set Up and Establishment | SCCL | Inspect existing road surface concentrating on existing grades/cross falls, ensure they are within specfication 4 - 6%, inspect surface water channels and side drains | Contract Specifications, SCCL Maintenace Grading and Maintenance Aggregates Inspection Form | Prior to physical works commencing | QA, SUP, E H, I, M |  | I
5 | Service identification | SCCL | Locate and pot-hole existing services | Worksafe guide for safety with underground services, NZTA Minimum Standard for Utility Identification and Protection | Prior to side drain clearing and any deep ripping | QA, SUP H, I
6 | Machinery is fit for purpose | SCCL | Ensure machinery is fitted with VHF/UHF and Satellite Phone communication, First Aid Kit, Fire Extenguisher and Spill Kit, Flashing Beacon Light, Required Signage and Alarms and Undertake pre-starts and machinery checksheet via Eroad App | Contract Doucments, CoPTTM, NZGTTM, Worksafe and Eroad prestart method | 3x daily | SUP & QA, M, I |  | R
7 | Traffic Management | SCCL | Establish and maintain generic traffic management plans, ensure signage is highly visable and in qood condition. | Approved Traffic Management Plan | Every two hours during work hours | QA,STMS, SUP, H, M,I |  | H, R
Environmental and Excavation
8 | Environmental and Erosion | SCCL | Installation and maintenance of erosion controlmeasures as required, inspect weather reports and programme works accordingly | Contract Documents, Guidlines for earthworks in the Taranaki Region - October 2006, NZS4404:2010 | Daily | SUP, QA |  | I
9 | Excavation on unmetalled Roads | SCCL | Obtain site access from property owner, inspect existing surface, complete maintenance shaping and side drain clearing/slip removal | NZS4404:2010, TRC & WRC Guidlines (Freshwater Plan) | Prior to and during task | SUP, QA, H, I, M |  | I
Surface and Shape Restoration
10 | Surface and Shape Restoration/Maintenance Grading | SCCL | Confirm grading, size and rock desnity meet specification | Technical Specifications, NZS 4404:2010 | Prior to and during installation | SUP, QA M |  | I, R
Maintenance Aggregates
11 | Spply and Placement of Maintenance Aggregates, AP65 Sub-base | SCCL | Must be approved by Engineer prior to use and inspected via NDM with a minimum MDD of 90% upon completion, to be constructed at 100mm nominal thickness | Contract documents, NZS 4402:2010, NZTA B/2:2005 and NZTA M/4 | Prior to placement | SUP, QA, M, I |  | I, R
12 | Spply and Placement of Maintenance Aggregates, AP40 Basecourse | SCCL | Must be approved by Engineer prior to use and inspected via NDM with a minimum MDD of 90% upon completion, to be constructed at 75mm nominal thickness | Contract documents, NZS 4402:2010, NZTA B/2:2005 and NZTA M/4 | Prior to placement | SUP, QA, M, I |  | I, R
13 | Spply and Placement of Maintenance Aggregates, AP30 | SCCL | Must be approved by Engineer prior to use and inspected via NDM with a minimum MDD of 90% upon completion, to be constructed at 45mm nominal thickness | Contract documents, NZS 4402:2010, NZTA B/2:2005 and NZTA M/4 | Prior to Sealing | SUP, QA M, I |  | I
Completion
14 | Completion of works | SCCL | Punchlist items closed out Tidy area, quality managers final inspection | Contract Documents, technical specifications | On Completion | QA H, I |  | H, I
15 | Complete payment claim requirments, collection of truck docets, completed lengths of surface and shape restoration, RP from - RP to Client for approval | SCCL | Transmit to client for final review | Technical Specifications NZS 3910:2013, Construction Contracts Act, SCCL Claim Format | Upon final inspection | QA, SUP, CM R, M, I |  | I, R